## Finance DRAFT SDBIP 1718
OUTCOME 10 | Administrative and financial capability
NKPA | Municipal Financial Viability and Management
IDP Objective Ref. No. 05 FIN 2016 | To improve the financial affairs and viability of the municipality in order to obtain clean audit by 2030 and beyond | [9 empty] | BUDGET AND TREASURY OFFICE 2017-2018 DRAFT SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
IDP Ref No. | B2B Ref No. | Strategic Objective | Strategy | Project | locality | Source of Funding | Budget Estimate | KPI | RESPONSIBLE DEPARTMENT | BASELINE 2016-17 | Quarter 1 Planned Target | Quarter 1 Evidence | Quarter 2 Planned Target | Quarter 2 Evidence | Quarter 3 Planned Target | Quarter 3 Evidence | Quarter 4 Planned Target | Quarter 4 Evidence | 2017-2018
|  | To improve income control. | By replacing credit meters to smart meters | Debt Collection | All Lms | Equitable share | R0.00 | 1.1 % of customers billed / total number of customers on database 1.2. Number of days outstanding 1.3 % of collection ( amount collected / sales) 1.4. % Monthly reconciled suspence accounts with analysis of balance. 1.5.Monthly reconcilliation / new customers and terminations 1.6 Number of daily reviews | BTO | 118%( receipts/ net billing) | [8 empty] | 80%( receipts/ net billing)
|  |  |  | Indigent register | All Lms | Equitable share | R1 500 000 | 1.2 Number of meetings held to update indigent register | BTO | Indigent register | [8 empty] | 8 Meetings held
|  | To improve income control. |  | Data cleansing | HGDM | Equitable share | R3 000 000 | 1.3. Number of monthly reports on updated data | BTO | New enabler | [8 empty] | 11 225 consumer accounts updated
|  | To ensure sound and credible general financial management principle |  | Debt coverage | All Lms |  | R 0.00 | 1.4 Total oparating revenue received - operating grants received / debts payments due includig interest and capital. |  | New enabler
|  |  |  | Outstanding debtors payment period | All Lms |  | R 0.00 | 1.5 Number of days debtors are outstanding ( Total oustanding debtors / actual revenue received x 365) | BTO | New enabler | [8 empty] | 60
|  |  |  | Cost coverage | HGDM | Equitable share | Salaries | 1.6 All available cash plus investments minus conditional grants / monthly fixed operating expenditure | BTO | New enabler
|  | To ensure compliance with the MFMA and improve budgeting reporting processes |  | Budget preparation |  | E | 150000 | 1.3 Approval of the 2017/18 budget process plan by council in August 2017 | BTO | 1.3.5. Approval of 2017/18 Budget process pan by Council by August 2017, | [8 empty] | 1.3.5. Approval of 2018/2019 Budget process pan by Council by August 2018,
|  |  |  | Budget |  | Equitable share | R 150 000 | 1.4. Approval of 2017/2018 final budget by May 2017 | BTO | Approval of 2016/2017 final budget by May 2016 | [8 empty] | Approval of 2017/2018 final budget by May 2017
|  |  |  | Annual Financial Statemnts |  | Equitable share | R3000000 | 1.5. AFS submitted to Auditor General by 31 August 2017. | BTO | 1.4.5. Preparation, of AFS and submision to Auditor General completed by 31 August | [8 empty] | 1.4.5. Preparation, of AFS and submision to Auditor General completed by 31 August
|  |  |  | Section 71 report |  | Equitable share | R0.00 | 1.6. Number of section 71 report submitted | BTO | New enabler | [8 empty] | 12 Section 71 report submitted to Portfolio committee, Exco and Proviincial Treasury
|  |  |  | Monthly returns |  |  | R 0.00 | 1.7. Number of monthly returns submitted | BTO | New enabler | [8 empty] | 12 monthly returns submitted to Provincial Treasury
|  |  |  | Section 52 (d) report |  |  | R0.00 | 1.8. Number of section 52 (d) report submitted to Council and Treasury | BTO | 4 | [8 empty] | 12 Section 52 (d) report submitted to Portfolio committee, Exco, Council and Proviincial Treasury
|  |  |  | Section 72 report |  |  | R0.00 | 1.9. Number of section 72 report submitted to Council and Treasury | BTO | 1 | [8 empty] | 12 Section 72 report submitted to Portfolio committee, Exco, Council and Provincial and National Treasury
|  | Review financial management policies in terms of the MFMA | By analyzing the existing policies to assess if they are still relevant for operations of the municipality. | Reviewal of finance policies |  | Equitable share | 300000 | 1.5. Adopted Council policies by May 2017 | BTO | 1.5.5. Policies reviewed and adopted by council by May 2017 | [8 empty] | 1.5.5. Policies reviewed and adopted by council by May 2018
|  | To improve internal control environment |  | Bank reconcilliation |  | Equtable | Salaries | 1.6. Number of monthly reconcillations | BTO | New enabler | [8 empty] | 12 monthly reconcillations reports
|  | Improve expenditure control |  | Creditors reconcillation |  |  | Salaries | 1.18. Number of monthly Age analysis reconcilled |  | New enabler | [8 empty] | 12 monthly Age analysis reconcilled
|  |  |  | Statistic SA Report | HGDM |  | Salaries | 1.19. Number of quartely returns submitted |  | New enabler | [8 empty] | 4 quartely returns submitted
|  |  |  | Salaries reconcilation |  | e | Salaries | 1.20. Number of monthly salaries reconciled | BTO | New enabler | [8 empty] | 12 monthly salaries reconciled
|  |  |  | Payment of Creditors |  | Equitable share | Salaries | 1.21.1. Number of days payment period |  | New enabler | [8 empty] | 30 days payment period
|  |  |  | Expenditure on capital projects |  | 1. Water Services Infrastructure Grant(WSIG) 2. Municipal Infrastructure Grant(MIG) 3.Regional Bulk Infratructure Grant(RBIG) |  | Percentage spent(total spending on capital projects/total capital budget) x 100
|  | To improve expenditure control and compliance with MFMA |  | Monthly salaries returns |  | Equitable share and Internal funding | Salaries | Number of salaries monthly returns submitted |  | 12 salaries monthly returns submitted | [8 empty] | 12 salaries monthly returns submitted
|  | To Perform verification, conditional assessment and assessment of useful lives of assets. |  | Asset Verication |  | Equitable share and Internal funding | R3 000 000 | 1.6 Updated fixed asset register | BTO | 1.6.5 Updated fixed asset register by June 2017 | [8 empty] | 1.6.5 Updated fixed asset register by June 2018
|  | To imrove procurement system |  | Bid committees |  | Equitable share and Internal funding | 1.24.1.1.R0.00 | 1.Number of days taken to finalise the specification of bid/tenders 2.Number of days taken to finalise the evaluation of bid/tenders 3. Number of days taken to finalise the adjudication of bid/tenders |  | 1. 2 days taken to finalise the specification of bid/tenders 2. 2 days taken to finalise the evaluation of bid/tenders 3. 1 day taken to finalise the adjudication of bid/tenders | [8 empty] | 1.2 days taken to finalise the specification of bid/tenders 2. 2 days taken to finalise the evaluation of bid/tenders 3. 1 day taken to finalise the adjudication of bid/tenders
|  | To improve the inventory management processes |  | Inventory management |  | Equitable share and Internal funding | R0.00 | number of inventory management reconciled per quarter |  | 0 | [8 empty] | 4 inventory management reconciled
|  | To ensure that procurement of goods and services is aligned with budget and SDBIP |  | Procurement plan |  | Equitable share and Internal funding |  | Preparation and submission of the procument plan to MANCO by June 2017 |  | procument plan submitted to MANCO by June 2016 | [8 empty] | procument plan submitted to MANCO by June 2016
|  | To ensure that appointed service providers complete their projects within the stipulated time frames and spend within the contract ammount |  | Contracts register |  |  |  | Number monthly contracts management reports submitted to Treasury
|  | To ensure that conditional grants are used for their purpose |  | Grants register |  | Equitable share and internal funding | salaries | Number of grants reconciliation reports |  | 12 grants reconciliation reports | [8 empty] | 12 grants reconciliation reports
|  | To fully comply with SCMregulations |  | Irregular expenditure |  | Equitable share and internal funding | salaries | Percentage reduction of irregular expnditure |  | 70% reduction of irregular expnditure
Note on H11: Mthethunzima Mkatu: Advertising Budget Document Printing Postage to NT
Note on H12: Mthethunzima Mkatu: Advertising Budget Document Printing Postage to NT

## Corp Draft SDBIP 1718
OUTCOME 9 |  | Implement a differentiated approach to municipal finance, planning and support
NKPA |  | Municipal Transformation and Institutional Development
IDP REF NO. 02 TRANS 15 |  | To provide administrative support to council and its structures and develop and improve human capital in order to deliver basic services to the communities
B2B REF NO. | Key Peformance Area | Activity | Strategies | Project Name | Budget | Source of Funding | KPI | Indicator Type | Responsible Department | 2013-2014 |  | Baseline 2016-17 | CORPORATE SERVICES 2017-2018 DRAFT SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN | [7 empty] | Annual Target
[11 empty] | 2013-14 |  | Quarter 1 Planned Target | Quarter 1 Evidence | Quarter 2 Planned Target | Quarter 2 Evidence | Quarter 3 Planned Target | Quarter 3 Evidence | Quarter 4 Planned Target | Quarter 4 Evidence | 2017-18
| Municipal transformation and institutional development | To develop the Workplace Skills Plan in order to address skills shortage within the District | By developing the Workplace Skills plan and submitting it to LGSETA | Workplace Skills Plan (WSP) | 1800000 | Internal funding | Number of WSP developed and submitted to LGSETA | Activity | Corp Services | There is a WSP in place for 2013/14 which was submitted to the LGSETA | 1 WSP submitted | 1 WSP submitted | [8 empty] | 1 WSP submitted to LGSETA
|  |  | By collecting information through skills audit | Implementation of workplace skills plan |  |  | Number of people trained | Activity | Corp Services | The municipality budgeted an amounnt of R1 620 000 for training | % of budget spent on training in implementing the WSP | 323 people trained | [8 empty] | 200 people trained
| Employment Equity | Ensure that the number of people from employment equity target groups are employed in the three highest levels of management in compliance with the municipality's approved Employment Equity Plan | Review the current Employent Equity Plan | Employment Equity | Nil |  | 2 people from employment equity target groups employed in the three highest levels of management in compliance with the municipality's approved Employment Equity Plan by June 2015 |  | Corp Services | There are employees employed in the three highest levels of management but improvement is needed | Employees employed in the three highest levels of management | Employees employed in the three highest levels of management | [8 empty] | Employees employed in the three highest levels of management
|  | Ensure that the Employment Equity Report (EER) is complied and submitted to the Department of Labour | Compilation and submission of the Employment Equity Report | Employment Equity Report | Nil |  | 1 Employment Equity Reports submitted to the Department of Labour by 15 January 2016 |  | Corp Services | Employment Equity Report was submitted to the Department of Labour on 15 January 2014 | 1 Employment Equity Report submitted | 1 Employment Equity Report submitted | [8 empty] | 1 Employment Equity Report submitted
| Council Support | Track implementation of Council resolutions | By updating the council resolution register on quarterly basis and submit to council | Council resolutions | Nil |  | 4 progress report against the implementation of Council resolutions submitted quarterly by 30 June 2016 |  | Corp Services | Implementation of Council resolutions is being tracked and reported to Council | Progress report against the implementation of Council resolutions submitted quarterly | Progress report against the implementation of Council resolutions submitted quarterly | [8 empty] | Progress report against the implementation of Council resolutions submitted quarterly
| Municipal transformation and institutional development | To capacitate Supply Chain Management officials and Bid Committee members | By conducting training | Capacity Building | 300000 | Internal funding | Number of officials trained on SCM | Activity | Corp Services | 100% | 100% | 27 officials trained on SCM | [8 empty] | 27 officials trained on SCM
| Municipal transformation and institutional development | To produce accurate leave information |  | Monthly leave reconciliation | Nil | N/A | Number of leave reconciliation reports to the MANCO by 30 June 2018 | Activity | Corp Services | [11 empty] | 10 leave reconciliation reports to the MANCO
| Municipal transformation and institutional development | To ensure effective communication internally and externally | By developing Newsletter on quarterly basis | Newsletter (External) | 1100000 | Internal funding | Number Newsletters developed and published by 30 June 2018 | output | Corp Services | Newsletters are being developed and published for every quarter | Four (4) Newsletters developed and published | Four (4) Newsletters developed and published | [8 empty] | Four (4) Newsletters developed and published
|  |  |  | Newsletter (Internal) | 50000 | Internal funding | Number Newsletters developed and published by 30 June 2018 | output | Corp Services | [11 empty] | Four (4) Newsletters developed and published
|  |  |  | Communications Workshop | Nil | N/A | Number of Communications workshop conducted | Activity | Corp Services | [11 empty] | 3 workshops held
|  |  |  | Stakeholder engagements | 500000 | Internal funding | Number of stakeholders engagement meeting held | Activity | Corp Services | [11 empty] | 2 media engagements
|  | To ensure compliance with relevant legislation and promote high standards of professionalism and efficiently utilise resources and be accountable |  | Records Management | Nil | N/A | Number of records management workshops conducted by 30 June 2018 | Activity | Corp Services | [11 empty] | 6 records management workshops conducted
|  |  |  | PAIA Manual | Nil | N/A | 1 PAIA Manual approved by 30 June 2018 | Activity | Corp Services | [11 empty] | 1 PAIA Manual Approved
| Good governance and public participation | To track implementation of Council resolutions |  | Exco and Council resolutions | Nil | N/A | Number of progress report against the implementation of Council resolutions submitted quarterly by 30 June 2018 | Activity | Corp Services |  |  | 4 Progress reports against the implementation of Council resolutions submitted quarterly | [8 empty] | 4 progress reports against the implementation of council resolutions submitted
| Municipal transformation and institutional development | To ensure a healthy, motivated and dedicated workforce | By appointing the service provider to train the SHE reps and First Aiders | SHE reps and First Aiders training | 100000 | Internal funding | Number of SHE reps and First Aiders trained | Activity | Corp Services | Monthly reports are being submitted to EXCO. | Reports submitted to EXCO | 6 SHE Reps and 7 First Aiders trained. | [8 empty] | 20 SHE reps and 20 First Aiders trained
| Municipal transformation and institutional development | To verify qualifications of employees (that are in the service of the municipality) to ensure that they are not fraudulent. | By verifying qualifications of all senior managers and middle management who are already employed. | Verifications of qualifications | 40000 | Internal funding | Number of verifications of qualifications performed by June 2018 | Activity | Corp Services | Collective agreements from the South African Local Government Bargaining Council are currently being implemented | Implement the signed collective agreements from SALGBC | 24 Verifications of qualifications performed | [8 empty] | 30 qualifications verified by 30 June 2018
| Municipal transformation and institutional development | To develop or review the municipal organizational design |  | Organizational Structure | Nil | N/A | Number of developed or reviewed organizational structure | Activity | Corp Services | [11 empty] | 1 Organizational structure adopted by Council by 30 June 2018
| Good governance and public participation | To develop or review the policies |  | Reviewal of policies |  |  | Number of developed or reviewed administrative and human resource policies | Activity | Corp Services | [11 empty] | 30 policies developed or reviewed and approved by Council
| Municipal transformation and institutional development | To ensure that the number of people from employment equity target groups are employed in the three highest levels of management in compliance with the municipality's approved Employment Equity Plan | By reviewing the current employment Equity plan and ensure that the municipality complies | Employment Equity | Nil | N/A | Number of people from employment equity target groups employed in the three highest levels of management in compliance with the municipality's approved Employment Equity Plan by 30 June 2018 | Activity | Corp Services |  |  | 2 people from employment equity target groups employed in the three highest levels of management in compliance with the municipality's approved Employment Equity Plan by 30 June 2017 | [8 empty] | 2 people from employment equity target groups employed in the three highest levels of management in compliance with the municipality's approved Employment Equity Plan by 30 June 2018
|  | To ensure that the Employment Equity Report (EER) is complied and submitted to the Department of Labour | Compilation and submission of the Employment Equity Report | Employment Equity Report |  |  | Number of Employment Equity Reports submitted to the Department of Labour by 15 January 2018 | Activity | Corp Services |  |  | 1 Employment Equity Report submitted to the Department of Labour by 15 January 2017 | [8 empty] | 1 Employment Equity Report submitted to the Department of Labour by 15 January 2018
| Municipal transformation and institutional development | To provide secure ICT infrastructure which delivers appropriate levels of data confidentiality and integrity | By procuring backup server | ICT Compliance | 949500 | Internal funding | Number of quarterly progress reports submitted to ICT Steering Committee by 30 June 2018 | Activity | Corp Services | [11 empty] | 4 ICT quarterly progress reports submitted to Steering Committee
|  |  |  | Licensing | 2350000 | Internal funding | Number of licenses renewed by 30 June 2018 | Activity | Corp Services | [11 empty] | 1 Microsoft volume license, 1 Anti-virus software license, 1 Orbit sofware license, 1 Printer software license, and 1 Backup software license annual subscriptions
|  |  |  | Off-site data Centre | 5000000 | Internal funding | Installation of off-site backup by 30 June 2018 | Activity | Corp Services | [11 empty] | Functional Data centre
|  |  |  | Network upgrade | 1500000 | Internal funding | Number of networks upgraded by 30 June 2018 | Activity | Corp Services | [11 empty] | Upgraded network
|  |  |  | Telephone System | 3000000 | Internal funding | Number of telephone systems upgraded by 30 June 2018 | Activity | Corp Services | [11 empty] | Upgraded telephone system
| Organisational Structure | Review the Organisational Structure | By consulting all the relevant HODs and municipal structures | Organisational Structure | Nil |  | 1 Organisational Structure reviewed |  | Corp Services | N/A | N/A | 1 Organisational Structure reviewed | [8 empty] | 1 Organisational Structure reviewed
|  | To ensure proper management of municipal fleet |  | Vehicle tracking system | 5000000 | Internal funding | Number of vehicles with upgraded tracker by 30 June 2018 | Activity | Corp Services | [11 empty] | 30 Vehicles fitted with upgraded tracking system
| Municipal transformation and institutional development |  | By monitoring vehicle tracking system | Fuel and maintenance reports | Nil | N/A | Number of reports submitted to EXCO by 30 June 2017 subject to the sitting of the Portolio Committee | Activity | Corp Services |  |  | 11 reports submitted to EXCO by 30 June 2017 subject to the sitting of the Portfolio Committee | [8 empty] | 10 Monthly reports submitted to Exco
|  |  |  | Awareness Campaigns | Nil | N/A | Number of awareness campaigns conducted on fleet management by 30 June 2018 | Activity | Corp Services | [11 empty] | 4 awareness campaigns conducted on fleet management

## ORGANISATIONAL
OUTCOME:O9 | Households progresively receive access to sustainable and reliable basic (water, sanitation, electricity and refuse removal) services
NKPA | Basic Service Delivery
IDP OBJECTIVE REF NO. 01 BSD 2015 | To improve the coverage, quality, efficiency and susutainability of water and sanitation services in all urban and rural communities
B2B REF NO. | Focus Area or Key Challenge | STRATEGIC OBJECTIVE | Strategy | PROJECTS | Locality / Regional indicator | Source of funding | BUDGET ESTIMATE | KPI | RESPONSIBLE DEPARTMENT | BASELINE | ORGANISATIONAL SCORE CARD 2017-2018 DRAFT SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
[10 empty] | 2016-2017 | Quarter 1 Planned Target | Quarter 1 Evidence | Quarter 2 Planned Target | Quarter 2 Evidence | Quarter 3 Planned Target | Quarter 3 Evidence | Quarter 4 Planned Target | Quarter 4 Evidence | 2017-2018
|  |  | To improve the image of the municipality and enhance social cohesion | Mayoral Slots | HGDM | Equitable share/ internal funding | R 1 500 000 | Number of Mayoral slots in SABC Radio stations booked | Office of the Municipal Manager | 12 mayoral slots booked at SABC radio station | [8 empty] | 12 mayoral slots booked at SABC radio station
|  | To gazette municipal health by-laws | By engaging government printers for gazetting the Municipal Health By-laws | Municipal Health By-laws gazetted | HGDM Main Office | 500000 | Internal funding | Completion of gazetting Municipal Health By-laws | Outcome | Social Services and Development Planning Services | [9 empty] | 3.9.5. Amended Municipal Health By-laws
|  | To monitor compliance related risks and provide assurance over compliance |  | Develop a municipal statutory compliance framework |  |  |  | Approved municipal statutory compliance framework | Office of the Municipal Manager | [9 empty] | 1 Reviewed and approved municipal statutory compliance framework by 2018
|  |  |  | Implementation of the risk - based internal audit plan 3) Report to the audit committee regularly |  |  |  | Number of quarterly Internal Audit reports completed as per the approved audit plan submitted to Audit Committee | Office of the Municipal Manager | 4 quarterly Internal audit reports completed submitted to Audit committee as per approved internal audit plan | [8 empty] | 4 quarterly Internal audit reports completed submitted to Audit committee as per approved internal audit plan
|  | To strengthen the legal unit to ensure that it fulfils its mandate which is to provide legal services efficiently and effectively |  | Provision of legal services | HGDM | Equitable share/ Internal funding | Salaries | Completion of provisioning of human capital for legal services unit by March 2017 | Office of the Municipal Manager | Establishment of legal services and labour relations unit completed by March 2017. | [8 empty] | Provisioning of human capital for legal services is completed by 2017
|  | To formulate Service Level Agreements for contracted Service Providers to avoid unnecessary claims. | By ensuring that all Service Level agrreements are being signed by both parties | Service level agreements | HGDM | Equitable share/ Internal funding | 500000 | Percentage of binding service level agreements completed. | Office of the Municipal Manager | 100% of Binding service level agreement completed by June 2016 | [8 empty] | 5.20.5.100% of Binding service level agreement completed by June 2017
B2B REF NO. | Focus Area or Key Challenge | Strategic Objective | Strategy | PROJECTS | Locality / Regional indicator | Source of funding | BUDGET ESTIMATE | KPI | RESPONSIBLE DEPARTMENT | OUTCOME | [8 empty] | 2017-2018
2016-2017
|  |  |  | Monitoring compliance to Blue drop and green drop | HGDM | Equitable share/ internal funding | R4000000 | Percentage improvement in the Blue drop and Green drop status |  | 4.29.1 Percentage improvement in the Blue drop and Green drop status 4.29.2. Completion of analysis BDS, GDS and implemenation of analysis BDS and GDS Action plan
RESEARCH PLANNING AND DESIGN
|  | To have an updated water and sanitation strategic plan |  | Development of (WSDP, water and sanitation master plan | HGDM | Equitable share/Internal funding | R19 000 000 | Completion of the Development of the WSDP by June 2017 |  | 2011 Water Services Development Plan ( WSDP) and water and sanitaion master plan | [8 empty] | Water Services Development Plan ( WSDP) developed by 2018
OPERATIONS AND MAINTENANCE
B2B REF NO. | Focus Area or Key Challenge | Activity | Strategy | Projects | Locality / Regional indicator | Source of funding | BUDGET ESTIMATE | KPI | Responsible Department | 2016-2017 | Quarter 1 Planned Target | Quarter 1 Evidence | Quarter 2 Planned Target | Quarter 2 Evidence | Quarter 3 Planned Target | Quarter 3 Evidence | Quarter 4 Planned Target | Quarter 4 Evidence | 2017-2018
INFRASTRUCTURE SERVICES
|  | To implement and upgrade water infrastructure projects |  | Water |  | MIG,WSIG | 1515265942 | Number of households accessing potable clean drinkable water for the first time | Infrastructure Services | 6377 | [8 empty] | 9119
|  | To ensure that sanitation dignity is restored within rural communities and promoting health and hygiene |  | Sanitation |  | WSIG | 380000000 | Number of households with dry sanitation | Infrastructure Services | 2358 | [8 empty] | 3409
|  | To implement all the VIP sanitation project identified by the business plan by 2018 |  | Sanitation |  |  |  | Number of VIP units completed | Infrastructure Services
|  | To implement water borne sewer by 2016 |  | water borne sanitation |  | MIG | 75000000 | Number of households with water borne sanitatio | Infrastructure Services | 600 | [8 empty] | 400
|  | To improve water supply in Ingwe and uBuhlebezwe areas |  | Steven Dlamini Dam (Greater Bulwer Donnybrook Regional Bulk Water Supply Scheme) |  |  | 1400000 | Water Resource Infrastructure Development | Infrastructure Services | 2% | [8 empty] | 15%
|  | To improve the socio-economic well being of our communities |  | EPWP |  | EPWP GRANT | 18000000 | Number of jobs created through initiatives including capital projects | Infrastructure Services | 1900 | [8 empty] | 1789
[9 empty] | Infrastructure Services | 599 | [8 empty] | 300
|  | To provide proper disposal of waste |  | Integrated Waste Management Plan | HGDM | Equitable share | R 400 000 | Completion of Intergated Waste Management Plan by 30 May 2018 | Infrastructure Services | N/A | [8 empty] | Developed Intergated Waste Management Plan by 30 May 2018
Note on L7: mchunuk: To revise the targets for the first Q
Note on I10: Msizi Mazibuko: To be included at the corporate services operational plan
Note on H22: makwakwab: assumptions 40% MIG Sanitation and 30% WSIG 16/17 294 849 542, 17/18 293 919 000. 18/19 254 497 400 For 1920 2021 20122 rbig will not be there but mig and wisig will remain the same as in 1819
Note on K22: makwakwab: Mnqumeni(Makhaleni,Farm,Khiliva)1229,Mqatsheni P1 338, Mangwaneni 241, Bulwer(Ntokozweni),Mkhunya(Sqndlw,Nkwelet)427,Ufafa P2&3 595, Chibini1162, WSIG NMZ villages identified villages Clysedale 110 house connection, Makhoba Springfontein 400
Note on T22: makwakwab: Mnqumeni(Jericho)600,Mqatsheni P2 1438, KwaSpheni 646,Ufafa P4 465, KwaMeyi/Teekloof 1202, Identified villages NMZ1177, Ncakubana 400, Mariathal Mandilini 355,CentocowMkhazini 300, Mashumi 100, Argylle 100.MbhulelweniNkwezela2000, Stepmore 436

## SSDP DRAFT SDBIP 1718
Outcome 9 |  | An effective climate change and adaptation response
NKPA |  | Local economic development and Social development
REF. NO. 04 LEDSOC 2015 |  | To increase the Gross Domestic Product of the Harry Gwala by 3% in 2030 to improve the socio-economic wellbeing of its citizens | [9 empty] | SOCIAL SERVICES AND DEVELOPMENT PLANNING 2017-2018 DRAFT SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
B2B REF NO. | Focus Area | Activity | Strategies | Project | Locality | Approved Budget | Source of funding | KPI | Indicator Type | Responsible department | Baseline 2016/2017 | Quarter 1 Planned Target | Quarter 1 Evidence | Quarter 2 Planned Target | Quarter 2 Evidence | Quarter 3 Planned Target | Quarter 3 Evidence | Quarter 4 Planned Target | Quarter 4 Evidence | Annual Target 2017/2018
|  | To facilitate the Procurement of fire and rescue equipment | By developing the specification and submitting to SCM unit to facilitate the procurement of fire and rescue equipment | Procurement of Fire and rescue equipment | Areas Prone to Runaway Fires | 750000 | Internal funding | 3.2.1. Number of fire beaters procured procure distributed to relevant stakeholders 3.2.2. Number of knapsack procure distributed to relevant stakeholders 3.2.3. Number of fire and rescue vehicle procured | Activity | Social Services and Development Planning Services | [9 empty] | 3.1. 200 fire beaters procure 3.2. 60 knapsack procured 3.3 1 Fire and rescue vehicle procured.
|  | To prevent disaster incidents and ensure quick response to affected communities | By installing cluster lightning conductors and respond to disaster incidents | Installation of cluster Lightning Conductors and provision of disaster Relief Material | All Local Municipalities affected | 2200000 | Internal funding | 3.3. Number of cluster lighting conductors installed 3.3.1.Turnaround time in responding to Disaster incidents and providing relief material to the affected communities. | Outcome | Social Services and Development Planning Services | [9 empty] | 5 cluster Lightning Conductors Installed. Respond to Disaster incidents within 4 hours to the affected communities and provide relief material
| MUNICIPAL HEALTH SERVICES | To gazette municipal health by-laws | By engaging government printers for gazetting the Municipal Health By-laws | Municipal Health By-laws gazetted | HGDM Main Office | 500000 | Internal funding | Completion of gazetting Municipal Health By-laws | Outcome | Social Services and Development Planning Services | [9 empty] | 3.9.5. Amended Municipal Health By-laws
|  | To coordinate vector and food handling programme, destitude, exhumations and reburials | By coordinate vector control and food handling programme, destitude, exhumations and reburials | Municipal Health Services | All Local Municipalities | 200000 | Internal funding | Number of Programmes coordinated | Activity | Social Services and Development Planning Services | [9 empty] | 4 Programmes coordinated
|  | To Monitor water quality to ensure safety for human consumption and communicate the results to water services | By taking water samples to laboratory for analysis and communicate the results to water services | Water Quality monitoring | All local municipalities | R158 250 00 | Internal funding | 3.14. Number of water samples taken for analysis and communicate the results to water services | Activity | Social Services and Development Planning Services | [9 empty] | 3.14.5. 200 water samples taken for analysis
B2B REF NO. | Focus Area or | Objective | Strategies | Projects | Locality | Budget | Source of funding | KPI | Indicator Type | Responsible department | Baseline 2016-17 | Quarter 1 Planned Target | Quarter 1 Evidence | Quarter 2 Planned Target | Quarter 2 Evidence | Quarter 3 Planned Target | Quarter 3 Evidence | Quarter 4 Planned Target | Quarter 4 Evidence | Annual Target 2017/2018
Key Challenge
| Youth Development | To promote the culture of learning and award good performance | By providing learning aids and financial support to deserving schools and learners | Back to School. | All local municipalities | 900000 | Internal funding | 1. Number of learners supported with learning aids 2. Number of schools and learners awarded | Activity | Social Services and Development Planning Services | [9 empty] | 130 learners supported with learning aids
|  | To co-ordinate youth Indaba to ensure the review of the Youth Development Plan | By engaging all youth structures to partake in the review Youth Development Plan | Reviewed Youth Development Plan | HGDM | 1300000 | Internal funding | Reviewed Youth development plan by June 2018 | Output | Social Services and Development Planning Services | [9 empty] | Youth Development Plan reviewed by June 2018
B2B REF NO. | Focus Area | Objective | Strategies | Projects | Locality | Budget | Source of funding | KPI | Indicator Type | Responsible department | Baseline 2016-17 | Quarter 1 Planned Target | Quarter 1 Evidence | Quarter 2 Planned Target | Quarter 2 Evidence | Quarter 3 Planned Target | Quarter 3 Evidence | Quarter 4 Planned Target | Quarter 4 Evidence | Annual Target 2017/2018
| Special Programmes | To empower and promote healthy living, awareness and moral regeneration amongst the vulnerable and communities | By engaging different social groupings to participate on special programmes | Special Programmes | Identified host LM | R1000 000 00 | Internal funding | Number of Special programmes conducted | Activity | Social, Economic and Development Planning Services | [9 empty] | 6 special programmes conducted
|  | To expose new talent focusing on cultural music | By hosting cultural festival | Cultural Festival | All LMs | R400 000 00 | Internal funding | Completion of the Cultural festival by November 2016 | Activity | Social Services and Development Planning Services | [9 empty] | 3.25.5. 1 cultural festival held November 2017
|  | To ensure that special programmes forums are convened to deliberate on issues facing them | By convening quarterly meeting with the special programmes forum | Special programmes forum meetings | Identified host LM | 900000 | Internal funding | Number of special programmes forum meetings held | Activity | Social Services and Development Planning Services | [9 empty] | 4 special programmes forum
|  | To identify suitable candidates through hosting build up sporting activities so as to participate in Provincial tournaments | By hosting different sporting activities and participating in Provincial tournaments | Sporting Activities | All LMs | 4500000 | Internal funding | Hosting and participating in the Provincial tournaments by December 2018 | Activity | Social Services and Development Planning Services | [9 empty] | Hosting different sporting activities and participating in Provincial tournaments by December 2018
B2B REF | Focus area or Key Challenge | Activity | Strategies | Project | Locality | Budget | Source of funding | KPI | Indicator Type | Responsible Department | Baseline 2016/2017 | Quarter 1 Planned Target | Quarter 1 Evidence | Quarter 2 Planned Target | Quarter 2 Evidence | Quarter 3 Planned Target | Quarter 3 Evidence | Quarter 4 Planned Target | Quarter 4 Evidence | Annual Target 2016/2017
| Geographical information system | To improve Geographical Information System (GIS) data and operational systems | By continuous upgrade of the GIS data and renewal of operating license | Renewal of operating lisences and Geographical Information System(GIS) data update | HGDM | R200 000 00 | Internal funding | Renewed operating lisences and Geographical Information System(GIS) data by June 2018 | Activity | Social Services and Development Planning Services | [9 empty] | Operating lisences and Geographical Information System(GIS) data renewed by June 2018
|  | To develop the Harry Gwala District Municipality strategic planning documents in consultation with relevant stakeholders | By developing a credible Integrated Development Plan and Spatial Development Framework in consultation with relevant stakeholders | Strategic planning documents | HGDM | 1600000 | Internal funding | Number of strategic planning documents developed | Activity | Social Services and Development Planning Services | [9 empty] | 2 Strategic planning documents reviewed
|  | To respond to climate change. | By developing a climate change response strategy | Climate change response strategy | All LMs | 1000000 | Grant Funding | 3.47.Approved climate change response strategy by June 2018 | Approval | Social Services and Development Planning | [9 empty] | 3.47.5. climate change response strategy developed and approved by June 2018
|  | To encourage municipal greening and proper waste management practices | By hosting the Greenest Municipal awards ceremony | Greenest Municipal Competition (GMC) | All LMs | 600000 | Internal funding | Engaging in Municipal greening activities and hosting the greenest Municipal competition | Activity | Social Services and Development Planning Services | [9 empty] | Hosting Municipal greening competition by February 2018
|  | To ensure that the annual report is submitted on time to the AG, National Treasury and to COGTA | By ensuring that the first draft is submitted by the 31 August and the final draft by the 31 January of each financial year. | Adopted Annual Report | IDP Alignment meetings | 300000 | Internal funding | 3.53. Submission of the Annual report( Oversight report) to Council, AG, National Treasury and to COGTA by March 2017 | Activity | Social Services and Development Planning Services | [9 empty] | 3.53.5 Annual report( Oversight report) to Council, AG, National Treasury and to COGTA submitted by March 2018
Note on L7: mchunuk: To revise the targets for the first Q

## SDA 1 (hidden)
Focus Area or | Objective | Strategies | Projects | Locality | Budget Estimate | KPI | Responsible department | Baseline | MTEF Target Date and Budget
Key Challenge | [7 empty] | 2012-2013 | 2013-2014 | 2014-2015 | 2015-2016
Tourism | To increase the number of tourist in the district | By implemnting the tourism stratergy | Tourism Strategy Implementation | District wide | 700 000 00 | Tourism Strategy implemented by June 2016 | Tourism Unit | none | 2014-01-01 | Implemntation | Implementatiomn
500000
| To promote the district as toursm destination | By marketing tourism oportunities and tourism atraction | Tourism marketing | District Wide | 300000 | Tourism broucher developed by June 2016 | Tourism Unit | none | 2013-06-14 |  | Tuorism marketed by June 2016
250000
| To put the district in the world map | By participating in tourism exhibition shows | Tourism exhibition shows | District Wide |  | 4 Exhibition shows | Tourism Unit | New Enabler |  | 4 Exhibition shows | 4 Exhibition shows
| To expand the market of Art and craft | By facilitating support to arts and craft | Art and craft training and expose | District Wide |  | 4 expose and one 1 training | Tourism Unit | New Enabler | 200000 |  | 4 expose and one 1 training
| To ensure operational and finacial stable Eco-Tourism | By providing after care support | Ntsikeni Eco- tourism | District Wide | 300 000 00 | Operational and financialy stable Eco-Tourism by 2016 | Tourism Unit |  | R10 000 |  | Operational and financialy stable Eco-Tourism by 2016
|  |  | Fodo Rustic development project | Umzimkhulu | 100 000 00 | Operational and financialy stable Eco-Tourism by 2016 | Tourism Unit |  |  |  | Operational and financialy stable Eco-Tourism by 2016
| To promote the development of community tourism organisation | By establishing the visitors information centre | Visitors Information centre | GKM | 200 000 00 | Established and operational VIC by June 2016 | Tourism Unit | 4 tourism Awareness campaings held | 100000 |  | Established and operational VIC by June 2016
| To profile and create awareness on district tourism attractions/products | By supporting local tourism marketing events | Local Tousim event | District Wide | 200 000 00 | 4 Local Tourism events held | Tourism Unit |  | 200 000 00 |  | 4 Local Tourism events held
Focus Area or | Objective | Strategies | Projects | Locality | Budget Estimate | KPI | Responsible department | Baseline | MTEF Target Date and Budget
Key Challenge | [7 empty] | 2012-2013 | 2013-2014 | 2014-2015 | 2015-2016
Industrial Developmnt | To maximise block manufacturing | By providing support to block manufacturing co-operatives | Block manufacturing | Umzimkhulu | 200 000 00 | 2 coroperatives to be supported | HGDA | N/A | N/A | N/A | 2 coroperatives to be supported
| To ensure a constant supply of perishables to the farmers market |  | Emerging farmer support | District Wide | 500000
| To produce maize on a massive scale for commercialisation |  | Maize massification | Umzimkhulu | 1500000
| To establish an an animal feed plant in the district |  | Animal feed plant | Umzimkhulu | 300000
| To add value on the milk |  | Business plan for dairy processing | Ingwe LM | 300000
| To promote entrepreneurship |  | Light industry park | Ubuhlebezwe | 200000
| To conduct a feasibilty study on Rail Freight revival |  | Rail Freight revival | District Wide | 300000
Focus Area or | Objective | Strategies | Projects | Locality | Budget Estimate | KPI | Responsible department | Baseline | MTEF Target Date and Budget
Key Challenge | [7 empty] | 2012-2013 | 2013-2014 | 2014-2015 | 2015-2016
| To monitor the district economic initiatives |  | LED and Tourism Forum | District Wide | 50000
|  |  | SSME Networking |  | 200000
|  |  | Contractors development programme |  | 200000
|  |  | Entreprise development strategy and implementation plan |  | 300000
|  |  | Poverty alleviation |  | 500000
|  |  | Highflats pack house and agro-processing |  | 250000
|  |  | Distric wide bee keeping and honey processing | District Wide | 200000

## SDA 2 (hidden)
Focus Area or Key Challenge |  | Objective | Strategies | Projects | Locality | Budget Estimate | KPI | Responsible department |  | Baseline
| Objective Reference | [7 empty] | 2012-2013 | 2013-2014 | 2014-2015 | 2015-2016 | 2016-2017
Growing Sisonke District Economy through Transformation of the local economy | 2013/SDA/011 | To build on profiling informal business stakeholders | By designing a simple excel/Access database template with key relevant fields (business, contact, sector) for population | To develop and populate database | District Wide | R 300 000 | Date on which the database is developed and submitted to SDA Board | Transformation Unit | none | 2014-01-01 | Maintannace R100 000 | Maintenance R100 000
| 2013/SDA/012 | To develop an SMME Development Strategy | By following the SCM processes for procurement of the service provider | To develop SMME Development Programme | District Wide | 200000 | Date on which the SMME Development Strategy is reviewed and adopted by the council and board | Transformation Unit | none
| 2013/SDA/013 | To review District LED Strategy | By following the SCM processes for procurement of the service provider | To review a District LED Strategy | District Wide | R 200 000 | Date on which the District LED Strategy is reviewed and adopted by the council and board. | Transformation Unit
| 2013/SDA/014 | To support SMMEs | By developing the SMME support Programme | To host SMME Seminars | All Local Municipalities | R 200 000 | No of SMME seminars hosted | Transformation Unit | 5 SMME Seminars
| 2013/SDA/015 | To develop a Cooperatives Strategy and Implememntation Plan | By developing the Cooperatives Strategy and Implementation Plan | To develop a cooperatives strategy and implementation plan | District Wide | R 200 000 | Date on which the Cooperatives Strategy and Implementation Plan | Transformation Unit
| 2013/SDA/016 | To support emerging contractors | By following the SCM processes for procurement | To develop a contractor development programme | District Wide | R 200 000 | Date on which the contractor development programme is submitted and adopted by the council and SDA board. | Transformation Unit
| 2013/SDA/017 | To monitor the district economic initiatives | By having quarterly LED Forum | To host LED forums | District Wide | R 200 000 | No of LED Forums held | Transformation Unit | 4 LED Forums

## SDA 3 (hidden)
Outcome 9 | Focus Area or |  | Objective | Strategies | Projects | Locality | Budget Estimate | KPI | Responsible department | Baseline | MTEF Target Date and Budget
Output No. | Key Challenge | Objective Reference | [7 empty] | 2012-2013 | 2013-2014 | 2014-2015 | 2015-2016
| Growing the Economy of Sisonke District Municipality through Rural Development and Land Reform Support | 2013/SDA/018 | To support Rural Development | By establishing Project Management Unit | Fencing Project Livestock Project Maize Macification Sharemilk Scheme Vegitable Production (Hydroponics) Hatchery Establishment Paultry Production | Umzimkhulu Ingwe KwaSani Ingwe Ubuhlebezwe | 3000000 | Number of projects implemented | Sisonke Development Agency | Fencing and livestock project is underway and supported by Department of Rural Development and Land Reform | 3000000 | 4000000 | 5000000
|  |  | By establishing Project Management Unit | Portion 10 of Lot BO No. 7764 Remainder of Lot BO No. 7764 Lot FP 218 No. 8478 Port 1 of Lot FP 219 No. 8481 Port 1 of Lot FP 267 No. 8431 Melviel Park Farm No. 32 Port 6 of Bedfontain No. 159 Port 2 of Tafelkop No. 165 Nyala Valley Farm No. 852 | Umzimkhulu Ingwe KwaSani Ingwe Ubuhlebezwe | Department of Rural Development and Land Reform to confirm the budget | Department of Rural Development and Land Reform to confirm the budget | Number of Initiatives supported | Sisonke Development Agency
|  |  | Fast Track Land Claim Process | By involving research personnel from University of KwaZulu Natal in the establishment of Project Management Unit | Vaalkrans Farm N0. 1035 KwaMadolo Farm No. 11 Hlokozi Farm No. 14234 Kronings Kron Farm No. 173 Modderfontein Farm No. 211 Rem of Lot S50 Farm No. 5216 Sub 1 of Lot S50 Farm No. 5216 Sub 1 of Faraway Farm No. 5145 Sub 1 of Faraway Farm No. 7503 Springfield Farm No. 5297 | Umzimkhulu Ingwe KwaSani Ingwe Ubuhlebezwe | Department of Rural Development and Land Reform to confirm the budget | Number of Initiatives supported | Sisonke Development Agency
|  | 2013/SDA/019 | To establish Agri Co-operatives, Co-operative Development Centres and Market Information Centres | By Implementing Jobs Fund Programme | Establishment of Agri Co-operatives Establishment of Cooperatives Development Centres Establishment of Market Information Centres | Umzimkhulu Ingwe KwaSani Ingwe Ubuhlebezwe | 12000000 | Date in which the Agri Co-ops, CDC and MIC are established | Sisonke Development Agency |  | Establishment of Agri co-operatives, Co-operatives Development Centres and Market Information Centres R4 000 000 | Establishment of Agri co-operatives, Co-operatives Development Centres and Market Information Centres R4 000 000 | Establishment of Agri co-operatives, Co-operatives Development Centres and Market Information Centres R4 000 000
Note on E24: Your User Name:

## SDA 4 (hidden)
Focus area or |  | Objective | Strategies | Projects | Locality | Budget Estimate | KPI | Responsible department | Baseline | MTEF Target Date and Budget
Key Challenge | Objective Reference | [7 empty] | 2012-2013 | 2013-2014 | 2014-2015 | 2015-2016
Growing the Sisonke Economy through Business retention and expansion strategy | 2013/SDA/020 | To establish an animal feeds plant in the district to meet the rapidly increasing demand for feed | By developing a business plan to source funding for the establishment of the feeds plant. | Animal Feeds Plant | uMzimkhulu,Greater Kokstad | R10,000,000.00-Project Cost(R200,000.00-Bus.plan) | Date on which Business plan is adopted by the SDA Board | Trade and Investment | New Enabler
| 2013/SDA/021 | To set up a Concrete products manufacturing plant to leverage opportunities for major civil works within the district | By developing a business and implementation plan,conclude a MOU with a concrete products manufacturer,Conloo | Concrete products manufacturing | uMzimkhulu | R5,000,000.00-Project Cost(R200,000.00-Bus.Plan) | Date on which Business and Implementation Plan and MOU is adopted by the SDA Board | Trade and Investment | New Enabler
| 2013/SDA/022 | To build a vibrant Chemical Industry in Sisonke | By engaging in research,commercial planting,pilot projects and procurement of Distillation Plant | Sisonke Essential Oils Project | uMzimkhulu | R12,000,000.00-Project Cost(R200,000.00-Research Report) | Date on which Business and Implementation Plan and MOU is adopted by the SDA Board | Trade and Investment | New Enabler
| 2013/SDA/023 | To plant vegetables using hydroponic farming methods | By developing a business and implementation plan | Sisonke Hydroponics Farming Project | uBuhlebezwe | R13,000,000.00-Project Cost(R200,000.00-Bus.Plan) | Date on which the Business and Implementation Plan is adopted by the SDA Board | Trade and Investment | New Enabler
| 2013/SDA/024 | To turn the district into an established manufacturing base for school uniforms and work-wear | By supporting cooperatives within the L.M`s;procuring sewing machines and fabric | Clothing and Textiles | Ingwe;uMzimkhulu | R600,000.00 | No.of schools supplied with uniforms | Trade and Investment | New Enabler
| 2013/SDA/025 | To set up a Milk Processing plant in Sisonke to produce cheese,yoghurt,powdered milk etc. | By developing a business plan | Milk Processing(Down-stream beneficiation) | Ingwe;Greater Kokstad | R13,860,000.00-Project Cost(R200,000.00-Bus.Plan) | Date on which the Business plan is adopted by the SDA Board | Trade and Investment | New Enabler
| 2013/SDA/026 | To set up a Chicken slaughter house/Abbatoir in Sisonke | By undertaking a Feasibility Study for the establishment of an abbatoir | Chicken Slaughter house/Abbatoir | District wide | R200,000.00 | Date on which the Feasibility study has been adopted by the SDA Board | Trade and Investment | New Enabler
| 2013/SDA/027 | To raise the profile of the District and makert Brand Sisonke to inspire confidence within the Business Sector. | Develop/ Review the Business Retention and Expansion Strategy | Business Retention and Expansion Strategy and Implementation Plan | Distric Wide | 300000 | Reviewed and approved Business Retention and Expansion Strategy | B.A.R.E | New Enabler
|  |  | Administer the Business Survey | Comprehensive Business Survey Report | District wide | 200000 |  | B.A.R.E | New Enabler
|  |  | Develop a business Data Base | Consolidated Business date Base | District Wide | 100000 | Completed and approved Data base | B.A.R.E | New Enabler | developed and approved datea base
|  |  | Implement the Business Retention and Expansion Visitation Initiative BR&EVI | Business Retention and Expansion Visitation Initiative | District wide | 100000 | No of Business Retention and Expansion Visitation Initiative | B.A.R.E | New Enabler |  | ongoing
| 2013/SDA/028 | To identify and adress barriers that impede business growth. | Implement the Existing Business Initiative(EBI) | Exixsting Business Initiative(EBI) | District wide | 100000 | No of Existing Business Initiatives executed | B.A.R.E | New Enabler |  | Ongoing
| 2013/SDA/029 | To share economic development priorities, investment opportunities and facilitate business acessto state and non- state programmes that are designed to improve their competiveness | Conduct Business Networking sessions | Business Working sessions | Distrct wide | 100000 | No of networking sessions hosted | B.A.R.E | New Enabler | 4 networking sesions hosted. | Ongoing | Ongoing

## MM IA (hidden)
OFFICE OF THE MUNICIPAL MANAGER (INTERNAL AUDIT)
Outcome 9 |  |  | Focus Area | Objective | Strategies | Projects | Budget Estimate | KPI | Responsible department | Baseline
Output No. 6 | NKPA | IDP Objective Ref. No. 04 LEDSOC 2014 | [7 empty] | 2013-14 | 2014-2015 | 2015-2016 | 2016-2017
ADMINISTRATIVE AND FINANCIAL CAPABILITY | MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT | To improve the Financial Affairs and Viability of the Municipality in order to get clean audit by 2014 and beyond | To provide a comprehensive and integrated value-added internal audit services | To add value and improve municipality's operations and help the municipality to accomplish its objectives | by bringing a systematic, desciplined approach to evaluate and improve the effectiveness of risk management, control and governance processes and adhering to all the legislative prescripts governing the internal audit activity. | 1) Development and approval of a risk-based internal audit plan 2) Implementation of the risk-based internal audit plan 3) Report to the audit committee regularly | R500 000 00 | Number of audit assignments completed as per the approved audit plan | Office of the Municipal Manager | 1 | 1 | 1 | 1
|  |  | Oversee all material aspects of the institution's financial reporting, controls and audit functions | To assist the municipality and the accounting officer in fulfilling its oversight responsibility with regard to the integrity of internal control and accounting function, internal auditing and external auditing and reporting practices of the municipality and other such duties as may be directed by the Council and Accounting Officer | Advise the muncipal council, political office bearers, the accounting officer and management staff with regard to internal controls, risk management, accounting policies, performance management, effective governance, performance evaluation and compliance with laws and regulations Review the overall effectiveness and efficiency of the internal audit function. By adhering to all the legislative prescripts governing the establishment of the Audit Committee | 1) Audit committee meetings 2) Submit reports to council | R400 000 00 | Total number of meetings held and reports submitted to council | Office of the Municipal Manager | 4 | 4 | 4 | 4
OFFICE OF THE MUNICIPAL MANAGER (RISK MANAGEMENT)
Outcome 9 | NKPA | IDP Objective Ref. No. 04 LEDSOC 2014 | Focus Area | Objective | Strategies | Projects | Budget Estimate | KPI | Responsible department | Baseline
Output No. 6 | [9 empty] | 2013-14 | 2014-2015 | 2015-2016 | 2016-2017
|  |  | Enterprise Risk Management | To provide a comprehensive approach to better integrate risk management into strategic decision making | By providing a methodology for managing institution-wide risks in a comprehensive and integrated manner. | 1) Development, approval and implementation of a Risk Management Framework and Strategy 2) Establishment of a Risk Management Unit and Committee | R200 000 00 | Approved risk management framework and policy | Office of the Municipal Manager | 1 | 1 | 1 | 1
|  |  | Implementation of effective risk monitoring processes | To identify potential events that may affect the institution, evaluate and address risks on a continuous basis before such risks can impact negatively on the institution's service delivery capacity. | Regular assessment and monitoring of relevant risks by continuously identifying, measuring and managing risks. | 1) Conduct Risk and control self assessment workshop 2) Compile a Risk register and profile 3) Develop and implement a Risk management plan | 100000 | Total number of reports submitted per approved risk management plan | Office of the Municipal Manager | 1 | 1 | 1 | 1
|  |  | Risk Management | To establish the risk the unit management unit | By appointing the risk Manager and interns | Establish the risk management unit | 0 | Date in whicH the risk management unit is established | Office of the Municipal Manager | Establish the Risk management unit by January 2014 | N/A | N/A | N/A
|  |  | Operation Clean Audit | To implement and report to EXCO and MPAC the implementation of Ags action | By tabling audited progress report on the implementation to EXCO and MPAC | Operation Clean Audit | 0 | Number of audited report submitted to EXCO and MPAC | Office of the Municipal Manager | 12 Audited Reports
|  |  | Sisonke Development Agency | To ensure that there is administrative stability in the entity | By attending meetings of the SDM Agency (MANCO and Board as an obersver) | SDA | 0 | Number of meetings attended | Office of the Municipal Manager | 8 meetings
[5 empty] | Cordinate joint meetings of SDM EXCO and SDA Board | EXCO and SDA Board joint meetings | 0 | Number of meetings held | Office of the Municipal Manager | 2 meetings
|  |  | To improve the liquidity of the municipality | To ensure that the liquidity of the municipality is positive | By excersisng budgtary controls | improved liquidity ratio | 0 | % improvmement in liquidity | Office of the Municipal Manager | 50%
|  |  | Facilitate the implementation of Bulwer Dam | To cordinate the stakeholders forum in the implementation of the Bulwer Dam | By ensuring that stakeholders forum meetings sit as scheduled | Bulwer Dam | 0 | Number of meetings held | Office of the Municipal Manager | 4 meetings

## MM Office DRAFT SDBIP 1718
Outcome 9 |  | Administrative and financial capabilities
NKPA |  | Municipal financial viability and management
IDP Objective Ref. No. 05 FIN 15 |  | To improve the financial affairs and viability of the municiplaity in order to have a self sustainable institution
B2B REF NO. | Focus Area or Key Challenge | Strategic Objective | Strategy | Projects |  |  | Budget Estimate | KPI | Responsible department |  | OFFICE OF THE MUNICIPAL MANAGER 2017-2018 DRAFT SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
[5 empty] | Locality / Regional indicator | Source of funding |  |  |  | 2016-2017 | Quarter 1 Planned Target | Quarter 1 Evidence | Quarter 2 Planned Target | Quarter 2 Evidence | Quarter 3 Planned Target | Quarter 3 Evidence | Quarter 4 Planned Target | Quarter 4 Evidence | 2017-2018
| Municipal Video System | To have an updated municipal Video system to showcase municipal service and programmes | By updating of the municipal Videography system | Videography | HGDM | Equitable share/ internal funding | R150 000 00 | 5.1. Number of recorded Videos | Office of the Municipal Manager | 5.1.5. 4 videos updated | [8 empty] | 4 videos recorded
| Public Relations | To show case Harry Gwala Infrastructure, LED and tourism projects | By conducting Media tour with the local and mainstream media | Media Tour | HGDM | Equitable share/ internal funding | R 500 000 | 5.2. Number of media tours conducted | Office of the Municipal Manager | 5.2.5. 2 Media tours conducted | [8 empty] | 2 Media tours conducted
|  | To improve the image of the municipality and enhance social cohesion |  | Marketing and Branding | HGDM | Equitable share/ internal funding | R400 000 00 | 5.3.1. Number of banners procured | Office of the Municipal Manager | 5.3.1.5 20 banners procured | [8 empty] | 5.3.1.5 20 banners procured
[5 empty] | HGDM | Equitable share/ internal funding | 145000 | Number of municipal flags procured | Office of the Municipal Manager | 0 | [8 empty] | 24 flags procured
[5 empty] | HGDM | Equitable share/ internal funding | 115000 | 5.3.2. Number folders procured | Office of the Municipal Manager | 5.3.2.5. 4000 folders procured | [8 empty] | 2000 folders procured
|  |  |  | Mayoral Slots | HGDM | Equitable share/ internal funding | R 1 500 000 | 5.4. Number of Mayoral slots in SABC Radio stations booked | Office of the Municipal Manager | 5.4.5. 12 mayoral slots booked at SABC radio station | [8 empty] | 12 mayoral slots booked at SABC radio station
|  |  |  | Nyusi Volume | HGDM | Equitable share/ internal funding | R 2 000 000 | 5.5. Number of Nyusi volume event held by December 2016 | Office of the Municipal Manager | 5.5.5. 1 Nyusi volume event held on December 2016 | [8 empty] | 1 Nyusi volume event held on December 2017
|  |  |  | Media Briefings | HGDM | Equitable share/ internal funding | R200 000 00 | 5.6. Number of Press Conference and Media Briefing held | Office of the Municipal Manager | 5.6.5. 4 Press Conferences and media briefings held | [8 empty] | 4 Media briefings held
| HIV & AIDS | To implement all HIV and AIDS programs to combat the scourge of the diseases in the District | By ensuring that all HV & AIDS programmes and projects are implemented | HIV/AIDS Awareness | HGDM | Equitable share/ internal funding | R1 000 000 00 | 5.7.1. Number of HIV/AIDS awareness programmes held 5.7.2 Number of District World Aids day event held | Office of the Municipal Manager | 5.7.5.1. 4 HIV/AIDS awareness programmes held 5.7.5.2. 1 District World Aids day event held | [8 empty] | 5.7.5.1. 4 HIV/AIDS awareness programmes held 5.7.5.2. 1 District World Aids day event held
| SUKUMA SAKHE | To implement Sukuma Sakhe programs in order to fight poverty and hunger | By ensuring that all Sukuma Sakhe programs are implemented | Operation Sukuma Sakhe | HGDM | Equitable share/ internal funding | R1 000 000 00 | 5.8. Number of Local and District Operation Mbo held | Office of the Municipal Manager | 5.8.5. 3 Local and 1 Operation Sukuma Sakh held | [8 empty] | 3 Local and 1 Operation Sukuma Sakh held
|  | To enhance democracy through public participation | By conducting Mayoral imbizo | Mayoral Imbizo | HGDM | Equitable share/ internal funding | R 1 000 000 | 5.9. Number of Mayoral Imbizo held | Office of the Municipal Manager | 5.9.5. 18 Mayoral Imbizo held | [8 empty] | 4 Mayoral Imbizo held
B2B REF NO. | Focus Area | Strategic Objective | Strategy | Projects | Locality / Regional indicator |  | Budget Estimate | KPI | Responsible department
[6 empty] | Source of funding |  |  |  | 2016-2017 | Quarter 1 Planned Target | Quarter 1 Evidence | Quarter 2 Planned Target | Quarter 2 Evidence | Quarter 3 Planned Target | Quarter 3 Evidence | Quarter 4 Planned Target | Quarter 4 Evidence | 2017-2018
|  | To create an environment that discourages fraudulent and corrupt activities |  | Review the fraud prevention policy and strategy |  |  |  | Approval of the fraud prevention policy and strategy by Council April 2017 | Office of the Municipal Manager | [9 empty] | 1 Approved fraud prevention policy by Council by June 2018
| Enterprise Risk Management | To provide a comprehensive approach to better integrate risk management into strategic decision making and day to day operations | By providing a methodology for managing institution-wide risks in a comprehensive and integrated manner. | Review and approval of Risk Management Policy |  |  | 300 000 00 | 5.10. Date on which risk management policy is reviewed by Council | Office of the Municipal Manager | 5.10.5. 1 Approved risk management policy by Council by June 2017 | [8 empty] | 1 Approved risk management policy by Council by June 2018
|  |  |  | Review and approval of Risk Management strategy |  |  |  | 5.11. Date on which risk management policy is reviewed by Council | Office of the Municipal Manager | 5.11.5. 1 Approved risk management strategy by Council by June 2017 | [8 empty] | 1 Approved risk management strategy by Council by June 2018
|  |  |  | Implementation of a Risk Management Framework and Strategy and Plan |  |  |  | 5.11 Number of reports submitted to the RISK/MANCO and Audit Committee | Office of the Municipal Manager | 5.11.5. 8- Reports submitted to RISK/MANCO 4- Reports submitted to Audit Committee | [8 empty] | 8- Reports submitted to RISK/MANCO 4- Reports submitted to Audit Committee
|  | To monitor compliance related risks and provide assurance over compliance |  | Develop a municipal statutory compliance framework |  |  |  | Approved municipal statutory compliance framework | Office of the Municipal Manager | [9 empty] | 1 Reviewed and approved municipal statutory compliance framework by 2018
B2B REF NO. | Focus Area | Strategic Objective | Strategy | Projects | Locality / Regional indicator | Source of funding | Budget Estimate | KPI | Responsible department | 2016-2017 | Quarter 1 Planned Target | Quarter 1 Evidence | Quarter 2 Planned Target | Quarter 2 Evidence | Quarter 3 Planned Target | Quarter 3 Evidence | Quarter 4 Planned Target | Quarter 4 Evidence | 2017-2018
| Implementation of effective risk monitoring processes | To identify potential risks that may affect the institution, evaluate and address risks on a continuous basis before such risks can impact negatively on the institution's service delivery capacity. |  | 1. Conduct risk and control self assessment workshop |  |  |  | 5.12.1. Date on which the Operational risk assessment report is approved by Audit committee June 2017 | Office of the Municipal Manager | 5.12.5.1 Approved Operational risk assessment report by June 2016. | [8 empty] | 1 Operational risk assessment report submitted to Audit Committee
| Implementation of effective risk monitoring processes |  |  | 1. Conduct risk and control self assessment workshop |  |  |  | 5.12.1. Date on which the process risk assessment report is approved by Audit committee April 2017 | Office of the Municipal Manager | 5.12.5.1 Approved process risk assessment report by June 2016. | [8 empty] | 1 process risk assessment report submitted to Audit Committee for approval
| Implementation of effective risk monitoring processes |  |  | 1. Conduct risk and control self assessment workshop |  |  |  | 5.12.1. Approval of the Strategic risk assessment by Audit committee April 2017 | Office of the Municipal Manager | 5.12.5.1 Approved Strategic Risk assessment report by June 2016. | [8 empty] | 1 Reports submitted to Audit Committee for approval
B2B REF NO. | Focus Area | Strategic Objective | Strategy | Projects | Locality / Regional indicator | Source of funding | Budget Estimate | KPI | Responsible department | Outcome | Quarter 1 Planned Target | Quarter 1 Evidence | Quarter 2 Planned Target | Quarter 2 Evidence | Quarter 3 Planned Target | Quarter 3 Evidence | Quarter 4 Planned Target | Quarter 4 Evidence | 2017-2018
2016-2017
| Audit Committee | To assist the municipality and the accounting officer in fulfilling its oversight responsibility with regard to the integrity of internal control and accounting function, internal auditing and external auditing and reporting practices of the municipality and other such duties as may be directed by the Council and Accounting Officer | By convening audit committee meetings | Audit Committee |  |  | 700 000 00 | 5.13 Number of audit committee meetings held | Office of the Municipal Manager | 5.13.5. 4 Audit Committee meetings held | [8 empty] | 4 Audit Committee meetings held
|  | To provide comprehensive and integrated value - added internal audit services | By bringing a systematic, disciplined approach to evaluate and improve the effectiveness of risk management, control and governance process | Development and approval of a risk- based internal audit plan |  |  | 500 000 00 | 5.14.1. Approval of the Risk based Internal Audit plan by the Audit committee in August 2017 | Office of the Municipal Manager | 5.14.5.1. Risk based Internal Audit plan is approved by the Audit committee in August 2016 | [8 empty] | 1 Approved risk based Internal Audit plan by August 2017
|  |  |  | Implementation of the risk - based internal audit plan 3) Report to the audit committee regularly |  |  |  | 5.15 Number of quarterly Internal Audit reports completed as per the approved audit plan submitted to Audit Committee | Office of the Municipal Manager | 5.15.5. 4 quarterly Internal audit reports completed submitted to Audit committee as per approved internal audit plan | [8 empty] | 4 quarterly Internal audit reports completed submitted to Audit committee as per approved internal audit plan
B2B REF NO. | Focus Area | Strategic Objective | Strategy | Projects | Locality / Regional indicator | Source of funding | Budget Estimate | KPI | Responsible department |  | Quarter 1 Planned Target | Quarter 1 Evidence | Quarter 2 Planned Target | Quarter 2 Evidence | Quarter 3 Planned Target | Quarter 3 Evidence | Quarter 4 Planned Target | Quarter 4 Evidence
[10 empty] | 2016-2017 | [8 empty] | 2017-2018
| Legal Services | To strengthen the legal unit to ensure that it fulfils its mandate which is to provide legal services efficiently and effectively |  | Provision of legal services | HGDM | Equitable share/ Internal funding | Salaries | 5.16. Completion of provisioning of human capital for legal services unit by March 2017 | Office of the Municipal Manager | 5.16.5. Establishment of legal services and labour relations unit completed by March 2017. | [8 empty] | Provisioning of human capital for legal services is completed by 2017
|  | To draft new bylaws, Vet agreements and Policies | By receiving policy /information for drafting a new bylaws/ receive draft bylaws from relevent department | Draft vet agreements, policies and managing By-laws | HGDM | Equitable share/ Internal funding | 1000000 | 5.17. Completion and submission of the draft bylaws, vet agreements and policies to the Council by January 2017 | Office of the Municipal Manager | 5.17.5. Draft bylaws, vet agreements and policies completed and submitted to Council by January 2016 | [8 empty] | 5.17.5. Vet agreements and policies completed and submitted to Council by January 2017
|  | To scrutinise debt collection files reaching point of exhaustion | By liaising with debtors on settlement of claims and recommend writes off. | Debt recovery | HGDM | Equitable share/ Internal funding | 2000000 | 5.18. Percentage of defaulting debtors files scrutinised | Office of the Municipal Manager | 5.18.5. 0 debtors files scrutinised | [8 empty] | 100% of defaulting debtors files scrutinised
|  | To ensure compliance and provision of legal support to the municipality. | By update Management and Excutive Committee on Policy issues and the reviewal of all policies derived from legislation, repeals / ammendments | Municipal policies | HGDM | Equitable share/ Internal funding | Salaries | 5.19.The approval of municipal policies by Council in May/June 2017 | Office of the Municipal Manager | 5.19.5. Municipal policies approved by Council in June 2016 | [8 empty] | Municipal policies approved by Council in June 2017
|  | To formulate Service Level Agreements for contracted Service Providers to avoid unnecessary claims. | By ensuring that all Service Level agrreements are being signed by both parties | Service level agreements | HGDM | Equitable share/ Internal funding | 500000 | 5.20. Percentage of binding service level agreements completed. | Office of the Municipal Manager | 5.20.5.100% of Binding service level agreement completed by June 2016 | [8 empty] | 5.20.5.100% of Binding service level agreement completed by June 2017
Note on I36: Msizi Mazibuko: To be included at the corporate services operational plan

## INFRA AND WATER DRAFT SDBIP1718
OUTCOME:O9 | Households progresively receive access to sustainable and reliable basic (water, sanitation, electricity and refuse removal) services
NKPA | Basic Service Delivery
IDP OBJECTIVE REF NO. 01 BSD 2015 | To improve the coverage, quality, efficiency and susutainability of water and sanitation services in all urban and rural communities
B2B REF NO. | Focus Area or Key Challenge | STRATEGIC OBJECTIVE | Strategy | PROJECTS | Locality / Regional indicator | Source of funding | BUDGET ESTIMATE | KPI | RESPONSIBLE DEPARTMENT | BASELINE | WATER AND INFRASTRUCTURE SERVICES 2017-2018 DRAFT SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
[10 empty] | 2016-2017 | Quarter 1 Planned Target | Quarter 1 Evidence | Quarter 2 Planned Target | Quarter 2 Evidence | Quarter 3 Planned Target | Quarter 3 Evidence | Quarter 4 Planned Target | Quarter 4 Evidence | 2017-2018
| Water conservation, Health and Hygiene promotion | To improve customer relations management, Water conservation Health Hygene promotion and revenue enhancement Through community outreach programmes |  | Water conservation, Health and Hygiene educational programs | HGDM | Equitable share | R400 000 00 | 4.1 Number of awareness campaigns conducted in Water conservation, Health and Hygiene educational programs | Water Services (Customer Care) | 4.1.5. 23 awareness campaigns conducted in Health and Hygiene educational programs | [8 empty] | 20 awareness campaigns conducted in Health and Hygiene educational programs
|  | Improve consultation with stakeholders that have been established in the Water Services Forums |  | Stakeholder Consultation Meetings | HGDM | Equitable share | R10 550 | 4.2. Number of Stakeholder Meetings conducted | Water Services (Customer Care) | 4.2.5. 4 Stakeholder Meetings Conducted | [8 empty] | 4 Stakeholder Meetings Conducted
B2B REF NO. | Focus Area or Key Challenge | Strategic Objective | Strategy | PROJECTS | Locality / Regional indicator | Source of funding | BUDGET ESTIMATE | KPI | RESPONSIBLE DEPARTMENT | OUTCOME | [8 empty] | 2017-2018
2016-2017
|  | Ensuring that WSA is fully complying to its mandate as set by the Departement of water and sanitation |  | Development and reviewal of Water policies, By-laws | HGDM | Equitable share / internal funding | R 600 000 | Completion of water policies and By-laws by June 2018 | Water services | Water policies and By-laws adopted | [8 empty] | Credit control and by-laws are reviewed by June 2017
|  |  |  | Monitoring compliance to Blue drop and green drop | HGDM | Equitable share/ internal funding | R4000000 | Percentage improvement in the Blue drop and Green drop status |  | 4.29.1 Percentage improvement in the Blue drop and Green drop status 4.29.2. Completion of analysis BDS, GDS and implemenation of analysis BDS and GDS Action plan
RESEARCH PLANNING AND DESIGN
|  | To have an updated water and sanitation strategic plan |  | Development of (WSDP, water and sanitation master plan | HGDM | Equitable share/Internal funding | R19 000 000 | 4.6.1 Completion of the Development of the WSDP by June 2017 |  | 2011 Water Services Development Plan ( WSDP) and water and sanitaion master plan | [8 empty] | Water Services Development Plan ( WSDP) developed by 2018
OPERATIONS AND MAINTENANCE
B2B REF NO. | Focus Area or Key Challenge | Activity | Strategy | Projects | Locality / Regional indicator | Source of funding | BUDGET ESTIMATE | KPI | Responsible Department | 2016-2017 | Quarter 1 Planned Target | Quarter 1 Evidence | Quarter 2 Planned Target | Quarter 2 Evidence | Quarter 3 Planned Target | Quarter 3 Evidence | Quarter 4 Planned Target | Quarter 4 Evidence | 2017-2018
|  | To maintain full functionality of water and sanitation schemes as per maintenance plan |  | maintenance of water and sanitation infrastructure | HGDM | Equitable share/Internal funding | R 50 000 000 | Turnaround time to respond to reported complaints. | Water services | Respond to reported complaints within 24 hours | [8 empty] | Respond to reported complaints within 24 hours
|  |  |  | Refurbishment of water and sanitation infrastructure | HGDM | Equitable share/Internal funding | R 20 000 000 | Number of water and sanitation schemes refurbished |  | 0
INFRASTRUCTURE SERVICES
|  | To implement and upgrade water infrastructure projects |  | Water |  | MIG,WSIG | 1515265942 | Number of households accessing potable clean drinkable water for the first time | Infrastructure Services | 6377 | [8 empty] | 9119
|  | To implement and upgrade water infrastructure projects |  | Water |  |  | 1515265942 | Number of households accessing potable clean drinkable water for the first time | Infrastructure Services | 6377 | [8 empty] | 9119
|  | To ensure that sanitation dignity is restored within rural communities and promoting health and hygiene |  | Sanitation |  | WSIG | 380000000 | Number of households with dry sanitation | Infrastructure Services | 2358 | [8 empty] | 3409
|  | To implement all the VIP sanitation project identified by the business plan by 2018 |  | Sanitation |  |  |  | Number of VIP units completed | Infrastructure Services
|  | To implement water borne sewer by 2016 |  | water borne sanitation |  | MIG | 75000000 | Number of households with water borne sanitatio | Infrastructure Services | 600 | [8 empty] | 400
|  | To improve water supply in Ingwe and uBuhlebezwe areas |  | Steven Dlamini Dam (Greater Bulwer Donnybrook Regional Bulk Water Supply Scheme) |  |  | 1400000 | Water Resource Infrastructure Development | Infrastructure Services | 2% | [8 empty] | 15%
|  | To improve the socio-economic well being of our communities |  | EPWP |  | EPWP GRANT | 18000000 | Number of jobs created through initiatives including capital projects | Infrastructure Services | 1900 | [8 empty] | 1789
[9 empty] | Infrastructure Services | 599 | [8 empty] | 300
|  | To provide proper disposal of waste |  | Integrated Waste Management Plan | HGDM | Equitable share | R 400 000 | Completion of Intergated Waste Management Plan by 30 May 2018 | Infrastructure Services | N/A | [8 empty] | Developed Intergated Waste Management Plan by 30 May 2018
|  | To maintain full functionality of the water and sanitation |  | Water and sewer upgrades |  |  | Included in Capital Investment | Number of water and sanitation schemes upgraded | Infrastructure Services | 5 | [8 empty] | 7
Note on H22: makwakwab: assumptions 40% MIG Sanitation and 30% WSIG 16/17 294 849 542, 17/18 293 919 000. 18/19 254 497 400 For 1920 2021 20122 rbig will not be there but mig and wisig will remain the same as in 1819
Note on K22: makwakwab: Mnqumeni(Makhaleni,Farm,Khiliva)1229,Mqatsheni P1 338, Mangwaneni 241, Bulwer(Ntokozweni),Mkhunya(Sqndlw,Nkwelet)427,Ufafa P2&3 595, Chibini1162, WSIG NMZ villages identified villages Clysedale 110 house connection, Makhoba Springfontein 400
Note on T22: makwakwab: Mnqumeni(Jericho)600,Mqatsheni P2 1438, KwaSpheni 646,Ufafa P4 465, KwaMeyi/Teekloof 1202, Identified villages NMZ1177, Ncakubana 400, Mariathal Mandilini 355,CentocowMkhazini 300, Mashumi 100, Argylle 100.MbhulelweniNkwezela2000, Stepmore 436
Note on H23: makwakwab: assumptions 40% MIG Sanitation and 30% WSIG 16/17 294 849 542, 17/18 293 919 000. 18/19 254 497 400 For 1920 2021 20122 rbig will not be there but mig and wisig will remain the same as in 1819
Note on K23: makwakwab: Mnqumeni(Makhaleni,Farm,Khiliva)1229,Mqatsheni P1 338, Mangwaneni 241, Bulwer(Ntokozweni),Mkhunya(Sqndlw,Nkwelet)427,Ufafa P2&3 595, Chibini1162, WSIG NMZ villages identified villages Clysedale 110 house connection, Makhoba Springfontein 400
Note on T23: makwakwab: Mnqumeni(Jericho)600,Mqatsheni P2 1438, KwaSpheni 646,Ufafa P4 465, KwaMeyi/Teekloof 1202, Identified villages NMZ1177, Ncakubana 400, Mariathal Mandilini 355,CentocowMkhazini 300, Mashumi 100, Argylle 100.MbhulelweniNkwezela2000, Stepmore 436