## FINANCE (hidden)
HARRY GWAL DISTRICT MUNICIPALITY BUDGET AND TREASURY OFFICE DRAFT 2014/2015 ANNUAL PERFORMANCE REPORT
OUTCOME 9 | National KPA | IDP Objective Ref. No. 05 FIN 2014 | Local KPA/ Key Challenge | Objectives | Strategies | Project Name | Budget Estimate | Adjusted Budget | Municipal Indicator | Baseline | [9 empty] | Revised Target
OUTPUT 6 | [8 empty] | KPI | 2013/14 | Quarter 3 | Quarter 3 Actual | Q3 Evidence | Reason and Corrective Action | Quarter 4 | Quarter 4 Actual | Reason and Corrective Action | Q4 Evidence | ANNUAL TARGET'2014/15
Note: The above quarterly report contains actual performance information as at quarter three. The actual results depicted in the report are based on the portfolio of evidence contained in the departmental files. In some instances the targets may have been met but the evidence is either missing or insufficient or irrelevant, which could mean that these results are not a fair presentation of the operations of HGDM. Management is therefore in the process of collating and filling the required evidence such that credible evidence is available on submission of the Annual Performance Report to the Auditor-General. Once the information is collated and filed, the Draft Annual Performance report will be adjusted accordingly.
Administrative and financial capability | Municipal Financial Viability and Management | To improve the financial affairs and viability of the municipality in order to obtain clean audit by 2014 and beyond | Revenue Management | To maximise debt collection by 2015 and beyond. | By increasing revenue collection | Implementation of credit control and debt collection | 1000000 |  | % of billed income collected | 80% | 75% | 80% of debts collected. | 1. Debtors list , debtors collection schedule and monthly receipts | Target met | 80% | Achieved. 108% of debts collected. |  | 1. Debtors list , debtors collection schedule and monthly receipts | Debt collected 80% Debt collection to be increased by 80%.
[9 empty] | Number of meetings held. | new enabler | 1 meeting held | Target not met Not meeting held | 1. Signed attendance register 2. Signed minutes | The meeting could not be held due to the busy schedule of the Meter Readers and the Director Income and Expenditure. A new date will be arranged in May 2015 | 1 meeting held | Not Achieved, No relevant evidence on file. | Reasons and Corrective Action to be stated | 1. Signed attendance register 2. Signed minutes | 4 meetings held
|  |  | Budgeting, Reporting & Financial Systems | To facilitate the effective and efficient allocation of financial resources by 2015 and beyond. | By coordinating the budget preparation process in line with the approved Schedule of Key deadlines. | Budget preparation | R50 000 00 | 150000 | Date by which 2015/16 budget is approved. | Approved 2014/15 Budget by May 2013. | 2015/16 draft budget tabled to Council | Draft budget tabled to council. | Signed Council resolution | Target met | 2015/16 budget adopted by Council | Not Achieved, No relevant evidence on file. | Reasons and Corrective Action to be stated | Signed Council resolution | 2015/16 budget adopted by Council by May 2015. .
[5 empty] | Preparing monthly financial statements | Accounting Services (AFS) | R 1 300 000 00 | 3245161 | Date by which the AFS are submitted to Auditor General (AG). | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | AFS prepared and submitted to Auditor General by 30 September
|  |  |  | To ensure effective financial systems administration by 2015. | By enhancing finance personnel competencies on financial management system functionalities and system support. | Financial Management Systems Training | R300 000 00 |  | Number of staff trained. | new enabler | 4 staff members trained | Target not met No relevant evidence on file. | 1. Signed attendance register 2. Certificates | Reasons and Corrective Action to be stated | N/A | N/A | N/A | N/A | 8 staff members trained .
|  |  |  | To ensure effective, efficient, economical review and implementation of finance policies and by June 2015 and beyond. | By creating financial management policies implementation plan | Review of financial management policies | 300000 | 195000 | Date by which financial management policy adopted by Council. | 2014-05-31 | Workshop conducted to review financial management policies | Target not met No relevant evidence on file. | Signed attendance register | Reasons and Corrective Action to be stated | Policies adopted by Council | Not Achieved, No relevant evidence on file. | Reasons and Corrective Action to be stated | council resolution | Policy adopted by council by June 2015
|  |  |  | To ensure effective, efficient, economical and compliant procurement of goods and services by 2015 and beyond. | By implementing Supply Chain Management process | Data cleansing | 350000 | 250000 | Number of data cleansing conducted. | new enabler | 1 Data cleansing conducted | Target not met No relevant evidence on file. | Register signed by CFO/delegate | Reasons and Corrective Action to be stated | 1 Data cleansing conducted | Not Achieved, No relevant evidence on file. | Reasons and Corrective Action to be stated | Register signed by CFO/delegate | 4 data cleansing conducted
|  |  |  | To have a credible Asset Register that complies with GRAP by end of June 2015. | By conducting asset assessment. | Asset management | R 500 000 00 | 313181 | Number of monthly reports on acquisition, work in progress and completed projects. | 2 | 3 monthly reports on acquisition, work in progress and completed projects. | Target not met, 2 monthly reports on acquisition and work in progress projects. | 3 monthly reports on acquisition, working progress and completed projects signed by CFO/ delegate | Reasons and Corrective Action to be stated | 3 monthly reports on acquisition, work in progress and completed projects. | Not Achieved, 2 monthly reports on acquisition and work in progress projects. | Reasons and Corrective Action to be stated | 3 monthly reports on acquisition, working progress and completed projects signed by CFO/ delegate | 12 monthly reports on acquisition, working progress and completed projects.
1300000
Note on H7: Mthethunzima Mkatu: Advertising Budget Document Printing Postage to NT

## Infra (hidden)
HARRY GWAL DISTRICT MUNICIPALITY INFRASTRUCTURE SERVICES DEPARTMENT DRAFT 2014/2015 ANNUAL PERFORMANCE REPORT | [10 empty] | HARRY GWAL DISTRICT MUNICIPALITY INFRASTRUCTURE SERVICES DEPARTMENT 2014/2015 QUARTER 3 REPORT
Outcome 9 | NKPA | IDP Objective Ref. No. 01 INFR 2014 | Focus Area or Key Challenge |  |  | Project Name | Municipality | Commencement Date | End Date | Number of Households to be served by completed project
Output No. 2 |  |  |  | Objectives | Strategies | [5 empty] | TOTAL PROJECT BUDGET | Adjusted Budget | KPI | Baseline 13FY14 | Quarter 3 | Quarter 3 Actual | Evidence Q 3 | Comments/ Reasons and Corrective action | Quarter 4 | Quarter 4 Actual | Evidence Q 4 | Comments/ Reasons and Corrective action | Annual Target | Adjusted Target
Note: The above quarterly report contains actual performance information as at quarter three. The actual results depicted in the report are based on the portfolio of evidence contained in the departmental files. In some instances the targets may have been met but the evidence is either missing or insufficient or irrelevant, which could mean that these results are not a fair presentation of the operations of HGDM. Management is therefore in the process of collating and filling the required evidence such that credible evidence is available on submission of the Annual Performance Report to the Auditor-General. Once the information is collated and filed, the Draft Annual Performance report will be adjusted accordingly.
Households progressively gain access to sustainable and reliable basic (water, sanitation, electricity and refuse removal) services | Basic Service Delivery and Infrastructure | To improve the coverage, quality, efficiency and sustainability of water and sanitation services in all urban and rural communities. | Water | To supply 241 households with clean portable water by 2014-15 | By constantly monitoring the implementation of the water project | Enhlanhleni Water Project | KwaSani |  | 2015-05-01 | 241 | 1000000 | 854570 | Roofing of the reservoir completed - Yes/No and number of meters of rising main completed | Design report completed | Foundation completed and 40 % reservoir walls completed | Target not met ( foundation completed and 0% reservoir walls completed). | 1. Progress report with photos 2. Project plan | Reason and corrective action | Completed roofing of the reservoir and 400m rising main | Not achieved, 400m rising main 100% completed but no evidence of completed reservoir roofing | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate | Reason and corrective action | Yes - roofing of the reservoir completed and 400m of rising main completed | N/A
|  |  | Water | To implement bulk water supply for augmentation of existing water supply by June 2015 |  | Underberg Bulk Water Supply Upgrade Phase 2 | KwaSani | not yet approved | 2016-05-01 | 3085 | 4580053 | R - | Number of kms of water pipe line completed | Design report completed | Site handover | Target not met ( the appointment of the contractor was done in this quarter) | 1.Signed Site Minutes and / or register 2. Signed Engineers report and Photos. | There were delays in the SCM processes. The project will be expedited in quarter four. | Laying of 1.5km water pipe line | Not achieved, laying of the 1.5km water pipe line is 0% | Progress report with photos signed by Engineer | Reason and corrective action | Laying of 1.5km water pipe line | Laying of 1.5km water pipe line
|  |  | Water | To implement bulk water to benefit 1400 households by December 2014 |  | Makhoba Housing Water Project | GKM | not yet approved | 2015-06-01 | 1400 | 4170979 | 2288612 | Commissioning and project hand over of Springfontein and Argyll completed - Yes/No | Under construction | Commissioning and project hand over of Springfontein | Target not met (project Commissioning and hand over of Springfontein is not done) | 1. Progress report with photos signed by contractor 2. Project plan 3. Practical completion certificate 4. Proof of handover | Reason and corrective action | Commissioning and project hand over of Argyll | Not achieved, project Commissioning and hand over of Argyll is not done, project is 90% | 1. Progress report with photos signed by contractor 2. Project plan 3. Practical completion certificate 4. Proof of handover | Reason and corrective action | Yes - commissioning and project hand over of Springfontein and Argyll completed | N/A
|  |  | Water | To implement water supply scheme to service 641 households by June 2016 |  | Khukhulela Water Supply | Ingwe | not yet approved | Not yet approved | 641 | 3425287 | 499333 | Number of meters pipelines completed | Design report completed for the last phase (3). 641 HH are already benefitting | N/A |  | N/A |  | N/A |  | N/A |  | Complete construction of 500m pipe line 641 households to be served by the completed Khukhulela Water Supply (500m pipe line) | The project was re-prioritized for 2015/2016 financial year
|  |  | Water | To implement water supply to service 5944 households by 2030 |  | Greater Kilimon Water Supply Project | Ingwe | not yet approved | 2015-06-01 | 5944 | 16935900 | R 13 783 163. 00 | Number of MLs of reservoir completed, number of KLs of reservoir completed, pump station completed - Yes/No, and number of meters of pipeline completed | Under construction | Construction of 700m pipeline and completion of reservoir walls | Target not met (consultant report shows previous year's progress and states that the contractor is slow on site). | 1. Progress report with dated photos signed by contractor 2. Project plan | Reason and corrective action | Completion of 300kl reservoir and pump station | Not Achieved, setting out, site clearance are 100% with excavation at 10% Erection and fencing is at 0% | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate | Reason and corrective action | Construction of 300ML Reservoir and 300kl reservoir, Yes - pump station and 1400m pipeline completed | N/A
|  |  | Water | To implement water supply scheme to service 1654 households by July 2016 |  | Greater Nomandlovu Water Supply Scheme | Ingwe |  | 2015-06-01 | 1654 | 13477216 | R 6 220 353. 00 | Number of kms of pipeline completed | Construction of weir, 2ML reservoir and a package plant | Construction of 1.5km pipeline | Construction of 1.5km pipe in progress | 1. Progress report with dated photos signed by contractor 2. Project plan | Target met | Construction of 2km pipeline | Not achieved, 1800m and 200mm of steel pipe is in construction | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate | Reason and corrective action | Construction of 3.5km pipeline completed | N/A
|  |  | Water | To implement water supply scheme by 2017 |  | Bulwer to Nkelabantwana and Nkumba Water | Ingwe |  | 2015-06-01 |  | 7593686 | 5425949 | Completion of phase 1 Rudimentary - Yes/No. Appointment of Phase 2 contractor and site hand over - Yes/No. | Reticulation in the form of spring protection | Rudimentary reticulation will be 90% complete for phase 1. Advertisement of Phase 2 | Rudimentary reticulation 100% completed and advert for phase 2 sent out | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate 4. Copy of advertisement | Target met | Completion of phase 1 Rudimentary. Appointment of Phase 2 contractor and site hand over. |  | Not achieved, only appointment for phase 2 was done. | Reason and corrective action | Yes - phase 1 Rudimentary completed. Yes - appointment of Phase 2 contractor and site hand over completed. | Completion of phase 1 Rudimentary. Site hand over of phase 2
|  |  | Water | To implement water supply scheme by 2017 |  | Greater Mbhulelweni Water Supply Project | Ingwe | 2012/03/16 | 2015-11-01 | 5841 | 3000000 | 2465417 | Number of meters of bulk pipeline constructed | Existing reservoir | 50% reservoir foundation and trench excavation at 40%. | 50% reservoir foundation and trench excavation at 40% Pipe laid and backfield | 1. Progress report with dated photos signed by contractor 2. Project plan | Target met | Construction of 6000m pipeline completed | Not achieved, pipeworks are in-progress at 84% (Upvc pipe) and 56% (110mm uPVC) | 1. Progress report with dated photos signed by contractor 2. Project plan | Reason and corrective action | Construction of 6000m pipeline completed | Construction of 6000m pipeline completed
|  |  | Water | To implement water supply scheme by 2017 |  | Ixopo - Marianthal Water Supply Project | uBuhlebezwe | not yet approved | 2015-06-01 | 1517 | 4240199 | 9157635 | Number of MLs of reservoir completed and number of water treatment plants completed. | Under construction of2ML reservoir and water treatment works | Site establishment for phase 3. | Target not met (no evidence of site establishment) | 1. Progress report with dated photos signed by contractor 2. Project plan | Reason and corrective action | Phase 2 completion of 1 water treatment works and 2ML reservoir. | Not achieved, no relevant evidence of treatment plant | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate |  | 2ML reservoir and 1 water treatment plant completed | N/A
|  |  | Water | To implement water supply scheme by 2017 |  | Ithubalethu Water Supply | uBuhlebezwe | not yet approved | 2015-07-01 | 3226 | 8691523 | R 537 095. 00 | Phase 1 completed - Yes/No, and % completion of reservoir walls for phase 2 | Abstraction and bulk line for raw water | Site establishment for Phase 2. 100% earthworks for reservoir | site established and earthworks for reservoir 100% completed | 1. Progress report with photos signed by contractor 2. Project plan | Target met | Completion of reservoir foundation and 40% reservoir walls for Phase 2. | Achieved, reservoir foundation completed and 60% 600kl reservoir walls completed | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate |  | Yes - reservoir foundation completed and 40% completion reservoir walls for phase 2 | Completion of reservoir foundation and 40% reservoir walls for Phase 2.
|  |  | Water | To implement water supply scheme by June 2015 |  | Ncakubana Water Supply Project | uBuhlebezwe | not yet approved | 2015-06-01 | 1004 | 5832164 | 7815472 | % completion of foundation and slabs for the package plant. % completion of reservoir walls | 4500000 | 50% Complete foundation of reservoirs. 50% concrete slab for the package plant. | Target not met (although foundation of reservoirs and concrete slab for the package plant is 50% complete, there is no credible evidence, i.e. contractor/consultant report to support this). | 1. Progress report with photos signed by contractor 2. Project plan |  | 100% complete foundation and slabs for the package plant. 20% reservoir walls |  | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate |  | 100% complete foundation and slabs for the package plant. 20% reservoir walls | 100% complete foundation and slabs for the package plant. 20% reservoir walls
|  |  | Water | To implement water supply scheme by 2015 and beyond |  | Chibini Water Supply Project | uBuhlebezwe | not yet approved | 2015-11-01 | 1162 | 1363371 | 5603916 | Number of kms of reticulation pipeline completed. | Construction of bulk pipeline and a 2ML reservoir | Site establishment and construction of 2km reticulation pipeline | Target not met ( construction of 2km reticulation pipeline in progress) | 1. Progress report with photos signed by contractor 2. Project plan |  | Construction of 6km reticulation pipeline. | Achieved, 19km of reticulation pipeline constructed | 1. Progress report with photos signed by contractor 2. Project plan | Comments required | Construction of 6km reticulation pipeline completed. | Construction of 6km reticulation pipeline.
|  |  | Water | To implement water supply scheme by 2015 and beyond |  | Ufafa Water Supply Project | uBuhlebezwe | not yet approved | 2015-11-01 | 1060 | 13399165 | 4860423 | Number of meters of Bulk pipe line completed from Chibini reservoir to Ntakama reservoir, number of kms of water reticulation completed. | Detailed designs are completed | Site establishment and laying of 500m bulk pipeline | (site established and 2.5km bulk pipeline laid) | 1. Progress report with photos signed by contractor 2. Project plan | Target met | Construction of 1500m Bulk pipeline and 2km water reticulation. | Not achieved, no evidence of laying 1000m bulk pipeline and 2km water reticulation. | 1. Progress report with photos signed by contractor 2. Project plan |  | Completion of 1500m Bulk pipe line from Chibini reservoir to Ntakama reservoir, completion of 2km water reticulation. | Completion of 1500m Bulk pipe line from Chibini reservoir to Ntakama reservoir, completion of 2km water reticulation.
|  |  | Water | To implement water supply scheme by June 2015 |  | Clydesdale Water Reticulation (Umzimkulu Bulk Supply) | uMzimkhulu | not yet approved | 2015-06-01 | 635 | 1772346 | 3673947 | Number of stand pipes completed and advertisement of another 50 stand pipes - Yes/No. | Construction of bulk pipeline and a 2ML reservoir and a reticulation | Completion of 635 household connections | Target not Met (no evidence of 635 connections) | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate 4. signed confirmation from connected households |  | Advertisement for the construction of 1ML reservoir and installation of 50 stand pipes | Achieved, bid notice with closing date of 12 June 2015 | Bid notice/Advert | Reason and corrective action | Completion of 635 stand pipes and Advertisement of another 50 stand pipes. | Completion of 635 stand pipes and Advertisement of another 50 stand pipes.
|  |  | Water | To implement water supply scheme by June 2015 |  | Mnqumeni (Santombe) Water Supply Project Phase | uMzimkhulu | not yet approved | 2015-10-01 | 2834 | 20647708 | 16875399 | Number of MLs and kls of reservoir foundation completed | 25000000 | Site establishment and completion of reservoir excavation. | site established and trench excavation 00% completed | 1. Progress report with photos signed by contractor 2. Project plan | Target met | Completion of 2ML and 100kl reservoir foundation | Not achieved, 2ML and 100kl reservoir foundation 80% complete | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate | Reason and corrective action | Completion of 2ML and 100kl reservoir foundation | Completion of 2ML and 100kl reservoir foundation
|  |  | Water | To implement water supply scheme by 2020 |  | Greater Summerfield Water Project | uMzimkhulu | not yet approved | 2015-09-01 | 4985 | 10000000 | 10000000 | Number of kms bulk pipeline completed and number of MLs of reservoir foundation completed | 15000000 | Site establishment. Excavation of 2ML reservoir foundation completed | site established, excavation of 2ML reservoir foundation completed | 1. Progress report with photos signed by contractor 2. Project plan | Target met | Laying of 3km bulk pipeline completed. 2ML Reservoir foundation. | Not achieved, bulk pipe trenches 50% complete and 2ml reservoir foundation not completed. | 1. Progress report with photos signed by contractor 2. Project plan | Reason and corrective action | Completion of 3km bulk pipeline and 2ML reservoir foundation | Completion of 3km bulk pipeline and 2ML reservoir foundation
|  |  | Water | To implement water supply scheme to service 62 households by June 2014 |  | KwaTshaka Rural Water Supply (MACHUNWINI) | uMzimkhulu | not yet approved | 2015-03-01 | 62 | 1 487 496 | R 1 255 070. 00 | Number of kms of bulk water pipeline completed and pump house completed - Yes/No. | Reticulation lines in the form of spring protection | Commissioning and Technical hand over | Target not met completion certificate dated 25 June 2013 | Practical Completion certificate. | Reason and corrective action | N/A |  | N/A |  | Complete 3.05km bulk water pipeline and Yes - pump house completed. | N/A
|  |  | Water | To plan and implement water supply by June 2015 |  | KwaMayi-Theekloof Water Supply | uMzimkhulu | 2009/08/01 | 2015-11-01 | 1202 | 18000000 | 14435660 | Yes - reservoir foundation completed. Number of kms of pipeline completed. | Tender stage | Site establishment and 7.3km pipe laying from Ibisi plant to Ethembeni reservoir. | Minutes refer to a site meeting held on 1 December 2014. Laying of 7.3km pipe line is in progress | 1. Progress report with photos signed by contractor 2. Project plan | Target met | Completion of reservoir foundation. Completion of 7.3km pipeline. | Not achieved, no evidence of reservoir foundation and completion of 7.3km pipeline | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate | Reason and corrective action | Completion of 2 reservoir foundation. Completion of 7.3km pipeline | Completion of 2 reservoir foundation. Completion of 7.3km pipeline
|  |  | Water | To implement water supply scheme by 2015 |  | Mangwaneni Water Supply Project | Ingwe |  | 2015-07-01 | 700 | 8045483 | 7668798 | Construction of weir reservoir completed -Yes/No, and % of the water treatment plant completion | Construction of weir, bulk pipeline and reticulation | Completion of reservoir | Target not met reservoir is 80% completed | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate | Reason and corrective action | Completion of base for concrete weir and platform slab for water treatment works | Not achieved, no evidence of completion of base for concrete weir and platform slab for water treatment works | 1. Progress report with photos signed by contractor 2. Project plan | Reason and corrective action | Yes - construction of weir and reservoir completed and 80% of water treatment plant completed | Construction of weir, reservoir and 80% of water treatment plant
|  |  | Water | To implement water supply scheme by June 2015 |  | Pakkies Ext Phase 2 | GKM |  | 2015-06-01 | 334 | R 3.856.315 | 1110033 | Number of kms of reticulation pipeline completed and number of communal standpipes completed | Tender stage | Completion of snag list | Target not met (no evidence of completion of snag list) | 1. Progress report with photos signed by contractor 2. Completion certificate | Reason and corrective action | Complete 7km reticulation pipeline and 20 communal standpipes | Not achieved, V-box protection, installation of stand pipes and steel pipe at Willowdale and Ekuthuleni is 100% complete respectively. But Jojo tank stand is 50% complete and placing of Jojo tank is 0% | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate | Reason and corrective action | Complete 7km reticulation pipeline and 20 communal standpipes | Complete 7km reticulation pipeline and 20 communal standpipes
|  |  | Water | To implement water supply scheme by June 2015 |  | Mqatsheni Water Supply Project | KwaSani |  | 2015-06-01 | 1874 | 9000000 | 8737065 | Number of kms of Mqatsheni reticulation pipeline completed and number of stand pipes installed | Construction of bulk pipelines | Site establishment (Pilcon T/A Sizabonke), 5km pipeline excavation and laying | Target not met (excavation of pipeline is in-progress, laying of pipeline has not been started) | 1. Progress report with photos signed by contractor 2. Project plan | Reason and corrective action | Completion of 23km Mqatsheni reticulation pipeline and installation of 40 stand pipes | Not achieved, the pipeline is on average 85% complete and the 89 stand pipes are 45% complete (none is mentioned about the planned 40 stand pipes) | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate | Reason and corrective action | Completion of 23km Mqatsheni reticulation pipeline and installation of 40 stand pipes | Completion of 23km Mqatsheni reticulation pipeline and installation of 40 stand pipes
|  |  | Water | To implement water supply scheme by June 2015 and beyond |  | Mkhunya Water Project | Ubuhlebezwe |  | 2015-06-01 | 2482 | 5800000 | 8809212 | Number of kls of galvanized reservoir completed, Upgrade of water package plant completed- Yes/No and number of meters of pipe laid. | Currently at detailed design | Laying of 6500m water pipeline. 70% completion of pump station. | 7800m of water pipeline 100% completed. Pump station is at 95% | 1. Progress report with photos signed by contractor 2. Project plan | Target met | Installation of 250kl galvanized reservoir, Upgrade of water package plant and pipe laying of 7800m | Not achieved, galvanized reservoir 100% completed, laying of 7800m pipe is 100%. But there is no evidence of upgrade of water package plant | Engineer`s report with photos 1. Progress report with photos signed by contractor 2. Project plan | Reason and corrective action | Installation of 250kl galvanized reservoir, Upgrade of water package plant and pipe laying of 7800m | N/A
|  |  | Water | To implement water supply scheme by June 2015 and beyond |  | Greater Paninkukhu Water Project | Umzimkhulu |  | 2015-06-01 | 321 | 6000000 | 10153438 | Number of rudimentary water supply schemes completed at Zadungeni, Esicelweni, Nyanisweni and KwaMaduna and number of boreholes equipped at KwaSenti and Bomvini /Mncweba for drought relief. | 1742000 | Completion of 4 Rudimentary schemes at Zadungeni, Esicelweni, Nyanisweni and KwaMaduna. | Target not met there is no evidence of completion of the 4 rudimentary schemes | 1. Progress report with photos signed by contractor 2. Project plan | Reason and corrective action | Sitting, drilling and equipping of 2 boreholes at KwaSenti and Bomvini /Mncweba | Not achieved, there is no evidence that the 2 boreholes at KwaSenti and Bomvini /Mncweba have been equipped | 1. Progress report with photos signed by contractor 2. Project plan | Reason and corrective action | Completion of 4 Rudimentary water supply schemes at Zadungeni, Esicelweni, Nyanisweni and KwaMaduna and equipping 2 boreholes KwaSenti and Bomvini /Mncweba for drought relief. | Completion of 4 Rudimentary water supply and equipping 2 boreholes for drought relief.
|  |  | Bulk water | To improve water supply in I Ingwe and uBuhlebezwe areas by 2015 and beyond | By ensuring the construction of advanced infrastructure for Stephen Dlamini dam | Stephen Dlamini dam |  |  | Not yet approved | 15947 | 28 200 000 00 | 58200000 | % completion of gauging weir for the Bulwer emergency intervention water supply and number of advanced infrastructure contractors appointed | Baseline to be captured | Advertisement of 4 contractors. Application for Stephen Dlamini dam construction license by DWS | Target not met (bid notice for appointment of contractors prepared with closing date of 20 February 204. There is no evidence of license application by DWS). | Advert/bid notice and construction license approval by DWS | Reason and corrective action | 100% completion of gauging weir for the Bulwer emergency intervention water supply and appointment of 4 contractors for advance infrastructure construction relating to Stephen Dlamini dam | Not achieved, 4 contractors have been appointed and 0% completion of the gauging weir for the Bulwer emergency intervention water supply | 1. Progress report with photos signed by contractor 2. Project plan 3. Signed appointment letters | Reason and corrective action | 100% completion of gauging weir for the Bulwer emergency intervention water supply and appointment of 4 advanced infrastructure contractors | 100% completion of gauging weir for the Bulwer emergency intervention water supply and appointment of 4 advanced infrastructure contractors
|  |  | Sanitation | To implement water borne sewer by 2016 | By providing improved waterborne sewer system | Horseshoe Sanitation Project - New | GKM | not yet approved | 2015-06-01 | 1462 | 3551670 | R 3 638 718. 00 | Number of HH connected to sewer system | Phase 2 under construction | N/a | Site establishment was done in this quarter however this was carried forward from quarter two | 1. Progress report with photos signed by contractor 2. Project plan | Target met | Connection of 150 HH to sewer system | Not achieved, there is no evidence of connection of 150 HH | 1. Progress report with photos signed by contractor 2. Project plan 3. Beneficiary confirmations signed by beneficiaries | Reason and corrective action | Connection of 150 HH to sewer system | Connection of 150 HH to sewer system
|  |  | Sanitation | To upgrade existing infrastructure to service 1392 households by June 2016 |  | Umzimkulu Sewer Upgrade Phase 2 | uMzimkhulu | not yet approved | not yet approved | 1392 | 7000000 | 1675835 | Number of meters of reticulation completed and upgrading of sewer pump station - Yes/No. | Designs are under development | N/A | N/A | N/A | N/A | N/A |  | N/A |  | Complete 5500m reticulation and Yes - upgrading of sewer pump station completed. | The project was re-prioritized for 2015/2016 financial year
|  |  | Sanitation | To implement all the VIP sanitation project identified by the business plan by 2017 | By providing improved ventilated pits toilets | Ingwe Households Sanitation Project | Ingwe |  | 2015-06-01 | 15656 | 101,402,919 | 5847814 | Number of VIP units installed | Under construction already 10 063 | 200 unit installed | Achieved, 757 units constructed. | 1. Beneficiary list 2. Signed beneficiary confirmations | Target met | 484 units constructed | Not Achieved, no relevant evidenced on file | 1. Beneficiary list 2. Signed beneficiary confirmations | Reason and corrective action | 1044 VIP units installed | N/A
|  |  | Sanitation | To implement all the VIP sanitation project identified by the business plan by 2020 |  | Greater Umzimkulu Sanitation Project | uMzimkhulu | not yet approved | 2015-03-01 | 25612 | R 7.455.307 00 | 11083620 | Number of VIP units installed | 2360 HH have benefitted | 92 units constructed |  | 1. Beneficiary list 2. Signed beneficiary confirmations |  | N/A |  | N/A |  | 1112 VIP units installed | 1092 units completed
|  |  | Sanitation | To implement all the VIP sanitation project identified by the business plan by 2017 |  | Ubuhlebezwe Sanitation backlog eradication | Ubuhlebezwe |  | 2015-06-01 | 9842 | 8000000 | 5213540 | Number of VIP units installed | Currently 980 HH have been served | 250 unit constructed | 305 units installed | 1. Beneficiary list 2. Signed beneficiary confirmations | Target met | 150 units constructed | Achieved, 215 units installed | 1. Beneficiary list 2. Signed beneficiary confirmations |  | 600 units installed | 600 units will be constructed
|  |  | Building | To construct disaster management centre by June 2014 | By ensuring proper management of disaster incidents | Disaster Management Centre | Ubuhlebezwe |  | 2015-06-01 | ALL | R 7.252.399m | R 7.252.399m | Percentage Completion of construction of the Disaster management centre | Construction currently at 60% | N/A | N/A | N/A | N/A | N/A |  | N/A |  | 100% complete Disaster Management Centre by October 2014 | N/A
Note on M5: mchunuk: Budget to be adjusted to 2.5m because the contractor was not appointed in 2013/2014
Note on M13: mchunuk: Upwards Budget Adjustment from Mkhnunya(4m)to make it 8.2 m.
Note on M16: mchunuk: Adjusted upwards to 5.3m

## SDA (hidden)
Outcome 9 | NKPA | IDP Objective Ref. No. 01 INFR 2014 | Local KPA | Objective | Strategies | Projects | Locality | Budget Estimate | KPI | Responsible department | Baseline | Annual Target | MTEF Target Date and Budget
Output No. 2 |  |  | Key Challenge | [7 empty] | 2012-2013 | 2013-2014 | Q1 | Q2 | Q3 | Q4
|  |  | Tourism | To develop additional disrtict tourism events on Rail Tourism | By creating a tourism event calender for the disrtict | 1.Tourism Month Celebration 2. Aloe festival | District Wide | 1.R 200 000 2. R 50 000 | Number of tourism events held/supported | Tourism Unit | New enabler | 2 Rail tourism events held/supported | 2 Rail tourism events held/supported | None
|  |  |  | To establish a district tourism marketing programme to market the district | To attennd marketing exhibishion shows | Tourism Exhibition Shows |  | 68000 | Number of tourism exihibition shows attended | Tourism Unit | New enabler | 4 Tourism shows attended | Exhibit at the Gataway Show | None | Exhibit at the Cape Town Gataway Show | Exbhibit at a Tourism Indaba and Royal show
[5 empty] | To develop a Tourism broucher DVD | Tourism broucher DVD | District Wide | 60000 | Approved Developed DVD | Tourism Unit | New enabler | Completed DVD | Engage service providers through the SCM processes for the development of a tourism brochure DVD | Tourism Brochure DVD is developed | None
[5 empty] | Inserts in various tourism sector specific publications | Marketing of SDA tourism and investment opportunities and/or products | District Wide | 70000 | Number of Inserts posted in sector specific publications | Tourism Unit |  | 3 inserts in various marketing publications | Prepare and post insert for inclusion in the East Cape publishersTourism directory | Prepare inserts in Explore SA and Country Live Magazine. | Post inserts in SA Explore and Country Live Magazine | none
|  |  |  | To promote community involvement and general tourism awareness and tourism initiative | By conducting tourism awareness campaings amongst the tourism trade, local communities and schools | Conducting tourism awarness campaign | District Wide | 40000 | Number of tourism awarness campaings held | Tourism Unit |  | 5 tourism awareness campaigns held | 1 tourism awarness held | 2 tourism awarness held | 1 tourism awarness held | 1 tourism awarness held
|  |  |  | To provide art and craft support | To develop an arts curio Shop within the Sisonke Farmers Market | district art and craft curio shop | District Wide | 100000 | Arts and Craft Curio shop operational | Tourism Unit |  | Operational art and craft curio shop | Seivice provider is appointed in line with SCM policy and procedures | Arts and craft shop is developed |  | Arts and Craft Curio Shop is operational
[5 empty] | Identification and approval of 10 Crafters for training on trend design & Product Presentation | Training of Crafters | District Wide | 100000 | Number of crafters trained | Tourism Unit |  | 10 Crafters trained on Trend Design and Product Presentation | Identification and Selection of crafters to be trained | Engage service providers through the SCM Processes | Training of the 10 selected crafters in Trend Design and Product Presentation
|  |  |  | To provide after care support upport to Ntsikeni Eco- Tourism Enterprise | Monitor the operations of the business | Ntsikeni Eco Tourism Project. | District Wide | 300000 | SLA Signed and R300 000 transferred | Tourism Unit | New enabler | Signed SLA with new Operator and transfer funding. | monitor signing of funding Tripatide agreement and signing agreement is in place |  | Monitor operation of the lodges | Monitor operation of the lodges
|  |  |  | To facilitate the development of district tourism master plan for 5 years | By developing a comprehensive District tourism master plan | Tourism master plan | District Wide | NIL | Date on which the Tourism master plan is adopted by the SDA board of directors | Tourism Unit | New enabler | Adopted District Tourism Strategy and Plan | Engage service providers through the SCM processes for the development of the district Tourism Strategy and Plan | Development of District Tourism Master Plan |  | None
|  |  |  | To develop a tourism mentorship programme | by mentor 5 established tourism enterprises | Tourism mentorship programme | District Wide | NIL | No of enterprises mentored | Tourism Unit | New enabler | 5 tourism enterprises mentored | Identification and Selection 5 Tourism enteprise for mentoring | 5 tourism enterprises are mentored | monitor and report outsomes of the mentorship programme
Outcome 9 | NKPA | IDP Objective Ref. No. 01 INFR 2014 | Local KPA | Objective | Strategies | Projects | Locality | Estimated Budget | KPI | Responsible Department | Baseline | Annual Target | Target Date (2013/2014)
Output No. 2 | [10 empty] | 2012/2013 | 2013-2014 | Q1 | Q2 | Q3 | Q4
|  |  | BR& E | To establish an animal feeds plant in the district to meet the rapidly increasing demand for feed | By developing a business plan to source funding for the establishment of the feeds plant. | Animal Feeds Plant | Kokstad | 200000 | Bankable Business Plan for the establishment of the plant | Trade and Investment | New Enabler | Business and Implementation Plan | Advert and appointment of service provider | Business plan development and PSC establishment | Engagements with Investors | Social facilitation/Site identification
|  |  |  | To set up a Concrete products manufacturing plant to leverage opportunities for major civil works within the district | By developing a business and implementation plan,establish a Concrete manufacturing Plant,conclude a MOU with a concrete products manufacturer | Concrete products manufacturing | Umzimkhulu | 150000 | Operational Concrete Products manufacturing plant | Trade and Investment | New Enabler | Concrete Products Manufacturing Plant | Busines Plan,MOU with the Co-op,Procurement of Block Making Machinery,Cement,(MOU with Conloo) | Development of an enhanced Business Plan | Engagements with a private partner for mentoring and possible cooperation(Conloo has already been approached) | Fully operational Concrete manufacturing plant launched
|  |  |  | To build a vibrant Chemical Industry in Sisonke | By engaging in research,commercial planting,pilot projects and procurement of Distillation Plant | Sisonke Essential Oils Project | Umzimkhulu | 500000 | Irrigation infrastructure,Essential Oils,Environmental Impact Assessment | Trade and Investment | New Enabler | Completed Business Plan | Appoint a service provider for the development of a business plan | Inception report | Draft Business Plan | Completed Business Plan
|  |  |  | To plant vegetables using hydroponic farming methods | Production of cash crops through out the year to alleviate poverty in the district | Sisonke Hydroponics Farming Project | Ubuhlebezwe | 200000 | Hydroponic expertise and infrastructure | Trade and Investment | New Enabler | Business and Implementation Plan | Advert and Appointment of S.P for Business Plan | Business and Implementation Plan approved to source funding | Engagements with Stakeholders,TIKZN,NEF,IHALA for collaboration | Train coops on running and managing hydroponic farming
|  |  |  | To turn the district into an established manufacturing base for school uniforms and work-wear | By supporting cooperatives within the L.M`s;procuring sewing machines and fabric | Clothing and Textiles | Umzimkhulu | 400000 | Operational Clothing and Textile Hub in uMzimkhulu | Trade and Investment | New Enabler | An operational Clothing and Textiles Hub | Procurement of Embroidery machine and Fabric.Secure premises in Gateway,uMzimkhulu. | Signing of the MOU between supplier of fabric and Co-op to supply on demand. | Commission the Clothing and Textile Hub in uMzimkhulu | 1st production monitoring report
|  |  |  | To set up a Milk Processing plant in Sisonke to produce cheese,yoghurt,powdered milk etc. | By developing a business plan to source funding for the establishment of the milk processing plant. | Milk Processing(Down-stream beneficiation) | Kokstad | 200000 | Bankable Business Plan for the establishment of the plant | Trade and Investment | New Enabler | Business and Implementation Plan | Service Provider to prepare business plan appointed | Business and Implementation Plan approved to source funding | Conduct social facilitatioin with local communities | Engage various investors for funding
|  |  |  | To stimulate economy, encourage growth by retaining and expanding business creating much more needed employment thus inspirering business sector confidence | Facilitate the implementation of the BR& E Programme | BR & E Programme | District Wide | Inhouse | BR&E Programme Launch | Trade and Investment | New Enabler | BR& E Programme Launch | Engage TIKZN for the appontment of the BR& E consultant | BR& E Consultant appointed. | Develoment and approval of a Programme roll out plan | BR& E Programme Launch
ENTERPRISE DEVELOPMENT
Outcome 9 | NKPA | IDP Objective Ref. No. 01 INFR 2014 | KPA | Objective | Strategies | Projects | Locality | Budget Estimate | KPI | Responsible department | Baseline | Annual Target | MTEF Target Date and Budget
Output No. 2 | [10 empty] | 2012-2013 | 2013-2014 | Q1 | Q2 | Q3 | Q4
|  |  | Business Support | To develop LED Implementation Plan | Develop LED Implementation Plan | LED Implementation Plan | District Wide |  | Approved LED Implementation plan | Enterprise Development Unit | New enabler | Aproved LED and SMME Strategy and Implementation Plan | Procure service provider through SCM processes | Draft LED and SMME support Strategy drafted | Final LED and SMME Strategy and Implementation Plan approved | Commence with the implementation of the recommendations from the Strategy
|  |  |  | To prioritise enterprenueship and the advancement of SMMEs as the catalyst to achieving economic growth and development. | Develop an SMME Development Strategy and Implementation Plan | SMME Development Stategy and Implementation Plan | District Wide | 300000 | Approved SMME strategy and Implemenation plan | Enterprise Development Unit | New enabler
[5 empty] | Developing the SMME support Programme | Multi-Sectoral SMME Networking Seminars and SMME Support | 5 Local Municipalities | 100000 | No of Sectoral SMME Networking seminars hosted and SMMEs supported | Enterprise Development Unit | 4 | 2 Seminars and 2 SMMEs supported | 1 Seminar | Support one SMME | 1 Seminar | Support one SMME
|  |  |  | To support emerging contractors | By providing training | Develop and implement a training programme | District Wide | 200000 | No. of contractors under the mentorship programme | Enterprise Development Unit | New enabler | Training of emerging contractors | Database of Small and micro contractors in place | Training programme approved | 50% of the programme activities completed | Training programme implemented in full (100%)
|  |  |  | To profile informal business stakeholders | Design simple excel/Access database template with key relevant fields | SMME, Cooperatives and Unemployed youth database | District Wide |  | Approval of SMMME, Cooperatives and Unemployed youth database | Enterprise Development Unit | New enabler | Updated database | Design the tool for collecting data and commence with collecting data | Data base of Sisonke SMMEs, Cooperatives and Unemployed Youth completed | Date bases in place | Data bases in place
|  |  |  | To improve coordination of economic development planning and implementation across government sectors and non government actors | Facilitate and hold LED and Tourism Coordinating Forum | LED and Tourism Coordinating Forum | District Wide | 80000 | No of LED and Tourism Forum hosted | Enterprise Development Unit | 4 | 4 Forum Hosted | 1 Forum | 1Fforum | 1 Forum | 1Forum
AGRI-BUSINESS
Outcome 9 | NKPA | IDP Objective Ref. No. 01 INFR 2014 | Local KPA | Objective | Strategies | Projects | Locality | Budget Estimate | KPI | Responsible department | Baseline | Annual Target | MTEF Target Date and Budget
Output No. 2 |  |  | Key Challenge | [7 empty] | 2012-2013 | 2013-2014 | Q1 | Q2 | Q3 | Q4
|  |  | Land Reform and Agri-Business Development | To support Emerging Farmers | Provide inputs and market support | Support for emerging farmers | Umzimkhulu Ingwe Ubuhlebezwe | 800000 | 6 commodities produced by emerging farmers for NSNP,over 49 ha approved by DoE | Agri-Business Development | New enabler | Production of 2,134,608 kg`s per annum of 6 commodities for the NSNP | Formulation of farmers and commodity database. Attending to farmers request for funding assistance.provide space in the market for each commodity | Formulate LM's annual crop production plan in line with NSNP | Facilitate process of commodity grouping and signing of agreements/contracts | Monitor production and deliveries to the market to ensure vegitables are available as per NSNP menu
|  |  | Rural Development and Land Reform Support | To support co-operatives for maize massification | Provide inputs and supporting infrustructure | Maize massification | Umzimkhulu | 1000000 | Maize production identified in uMzimkhulu | Agri-Business Development | New enabler | 130 ha prepared,ploughed and planted for massive maize production | Social facilitation,engagements with relevant govt departments,develop productin plans,land preparation | Maize planting,spraying,hoeing.finalise outstanding off-take agreements,signing of MOU`s with govt entities/departments | Facilitate consultations between maize market and maize producers.Harvesting | Monitor production and ensure farmers maize reaches maize milling
|  |  | Rural Development and Land Reform Support | To support Emerging Farmers | Repair and maintain the market,furnish/procure relevant equipment,signed leases | Sisonke Farmers Market | Buhlebezwe | 1000000 | Operational farmers market | Agri-Business Development | New enabler | Furnish the Farmers market and commence operations. | Draw up farmers market business/ operational plan. | Engagements with all relevant stakeholders. Appointment of a service provider for repairs and maintanance and shopfitting | Official launch of the Farmers Makert | Opertaional Farmers Market
|  |  |  | To support the development of large scale commercial agriculture and coordinate effective intergration of farmers with domestic and external markets | To provide post settlement support to land reform beneficiaries | Post settlement support | Umzimkhulu KwaSani Ingwe Ubuhlebezwe Kokstad | 5100000 | Completed CDCs and MICs | Agri-Business Development | New enabler | Facilitate release of DBSA funding and complete CDC and MICs | Identify and finalise sites in all Local Municipalities | Procure service provider through SCM process / Train cooperatives | Shopfitting CDC and MIC equipment | Establish website for the CDCs and MICs.
FINANCE
|  |  | KPA | Objective | Strategies | Projects | Localty | Budget Estimate (Q3 + Q4) | KPI | Responsible department | Baseline | Annual Target | Target Date and Budget (2013/14)
[11 empty] | 2012/13 | 2013/14 | Q1 | Q2 | Q3 | Q4
|  |  | Risk management | Ensure that SDA objectives are achieved | Identify and evaluate the actual and potential risk areas and devise a process of either termination, transfer, tolerance or mitigation of each risk. | n/a | inhouse | 0 | Number of risk reports | Office of the CEO | n/a | Conduct risk assessment and produce reports | N/A | Risk assessment conducted | Risk Management Framework approved. Workshop employees on risk management. | Risk management progress reports produced monthly. 100% awareness
|  |  | Board capacitation | Provide support to the Board to ensure its effectiveness | By facilitating development of board members | n/a | inhouse | 75000 | Effective Board and its committees operating in line with their approved charters | Office of the CEO | N/A | Number of Board meetings and approved charters | Charters developed and approved | Board Secretariat in place | Board development opportunities identified.Take minutes accurately and distribute them in 7 days. Prepared Board packs and distributed 3 days before the meeting. Accurate filing system. | Take minutes accurately and distribute them in 7 days after the meeting. 100% minutes filed and approved as per the number of minutes.Developed checklist for Board Performance.Developed Annual Work Plan for Board.Prepared Board packs and distributed 3 days before the meeting.
|  |  | Support Implementation of an operational and Strategic Internal Audit Plan | To test the efficiency and effectiveness of internal controls | Planning and performing audit assignments as per the the approved operational & strategic internal audit plan | n/a | inhouse | 300000 | Number of audits performed per Quarter as per approved plan | Finance | N/A | Functional Finance Department | Advertised for Internal Audit services | Appoint IA Service Provider | Approved 3 year audit plan and annual audit plan | Annual Audit Plan implemented
|  |  | Revenue Management | To ensure that cash is available to meet SDA financial obligations | To develop budget monitoring policy,debtors and creditors policies | n/a | inhouse | 0 | All SDA financial obligations met when due | F & A | N/A | All SDA financial obligations met. All commitments to be backed by cash by year-end | Development of cash and revenue management policies,namely budget monitoring,debtors and creditors | All Policies approved and workshopped by all staff and implemented. | Implement policies and procedures with no deviation | Monthly reports produced on revenue and expenditure management
|  |  | Budget Reporting and Financial Systems | To provide reliable and timeuos financial information for decision making purposese | By producing financial reports in line with the MFMA and MBRR(Municipal Budgeting & Reporting Regulations) | n/a | inhouse | 150000 | MFMA s87 and s88 reports done | F & A | N/A | Monthly Income & Expenditure reports,Quartely Income & Expenditure reports,MTREF and Financial year end Financial Statements all done at the due dates | N/A | Quartely Income & Expenditure reporting,Quartely Income & Expenditure reporting,MTREF. | 1. Develop comprehensive Management Reporting and Budget formats. 2. Finalise System implementation (Pastel) and population of financial data. | 1. Audit readiness and year-end report preparations. 2. Upgrade system from Pastel Partner to Pastel Evolution (Data Migration).
|  |  | Supply Chain Management | To procure goods and services for the entity in compliance with MFMA | To review and implement SupplyChain Management Policy | n/a | inhouse | 0 | Approved Supply Chain Management Policy | F & A | N/A | Reviewed and approved Supply Chain Management Policy | N/A | Review Supply Chain Management Policy | Develop SCM systems (controls) and implement. | All SCM systems implemented accordingly.
|  |  |  | To ensure that requisitions for goods and services are procured timeously. | Implement efficient standard of responding to procurement requests | n/a | inhouse | 21000 | Turnaround time for procuremtent. | F & A | N/A | Database of service provider in place. | N/A | N/A | 1. Advertise service providers to register on the database. 2. Develop procurement and contract management standards. 3. Train Bid Committees. | Implement procurement and contract management standards
Business Development
|  |  | Human Resource Management | To ensure that the organisation is staffed with the right skills at the right time | Advertise and timeously recruit | n/a | inhouse | + | Turnaround time for advertising, conducting interviews and appointments | F & A | N/A | All vacancies should be filled | N/A | N/A | Advertise all approved vacancies | Fill in all vacancies
|  |  |  | To monitor the organisation's adherence to HR Policies and Industry Best Practice | Review and Implement HR Policies and Practices | n/a | inhouse | 0 | A minimum of three HR related policies to be submitted for approval | F & A | N/A | Compilation of HR Policies | N/A | N/A | Implement HR Policies | Communication and sign off all approved policies
|  |  |  | To facilitate the organisation's performance management system with a view to optimally utilise the human resource | Compile SDBIP for all Departments | n/a | inhouse | + | A produced consolidated SDBIP | F & A | N/A | Consolidated SDBIP for the year | N/A | N/A | Performance Report | Compiled Performance Report and annual SDBIP
[6 empty] | n/a | inhouse
[6 empty] | n/a | inhouse
[6 empty] | n/a | inhouse
0
|  |  | Facilities | To have credible asset register that complies with GRAP | Conduct asset assessment | n/a | inhouse | 0 | All Assets verified | F & A | N/A | Complete assets register | Compile Asset register | All asset purchased barcoded and captured on the asset register. Asset register reconciled monthly to GL | Asset register reconciled to GL. All assets verified for existence and balance to asset register. | Complete assets register which complies with GRAP requirements
|  |  |  | To ensure adequate access control over the Agency's building | Assess and procure security equipment and system | n/a | inhouse | 730000 | Erected boom gate and installed electronic access | F & A | N/A | Improved physcial security | N/A |  | Source provider | Erect the gate
|  |  |  | To have intergrated IT applications, hardware and support | Request closed proposals | n/a | inhouse | 150000 | % down time | F & A | N/A | Improved IT environment | N/A | n/a | Secure service provider | improve the IT infrastructure
Business Development
|  |  | Local KPA | Objective | Strategies | Projects | Locality | Estimated Budget (Revenue) | KPI | Responsible Department | Baseline | Annual Target | Target Date (2013/2014)
[11 empty] | 2012/2013 | 2013-2014 | Q1 | Q2 | Q3 | Q4
|  |  | Business Development | To seek funding for the implementation of the project | By reviewing the business plan to source funding for the implementation of the project. | Hydrophonics | Ixopo |  | Hydroponic expertise and infrastructure | Business Development | New Enabler | Secure funding for the project | N/A | N/A | Review business plan and do presentation to one funder | Available funding and commencement of the Hydrophonic project
|  |  |  | To seek funding for the implementation of the project | By developing a business and implementation plan,secure mentorship from Conloo | Brick Manufacturing | Nzombane, Mzimkulu |  | Operational Concrete Products manufacturing plant | Business Development | New Enabler | Secure funding for the project | N/A | N/A | Establish a block market, curb market and approach Mondi Zimele Fund | Available funding and commencement of Brick Manufacturing project
|  |  |  | To seek funding for the implementation of the project | By shaping the business plan accordingly | Maize mill | Mzimkulu |  | Operational maize mill | Business Development | New Enabler | Secure funding for the project | N/A | N/A | Develop Business Plan | Available funding for the maize mill project
|  |  |  | To seek funding for the implementation of the project | By developing a business plan | DMT Essential Oils | Mzimkulu |  | Essential oils | Business Development | New Enabler | Secure funding for the project | N/A | N/A | Identify potential funders and establish relations | Available funding and commencement of DMT Essential Oils
|  |  |  | To seek funding for the implementation of the project | By developing a business plan | Tourism Master Plan | Mzimkulu |  | Tourism Masterplan | Business Development | New Enabler | Secure funding for the project | N/A | N/A | Prepare funding requests to DEDT andTKZN | Funding for the Tourism Master plan

## Infrastructure
HARRY GWALA DISTRICT MUNICIPALITY INFRASTRUCTURE SERVICES DEPARTMENT 2015/2016 HALF YEAR PERFORMANCE REPORT
Outcome 9 | NKPA | IDP Objective Ref. No. 01 INFR 2014 | Focus Area or Key Challenge |  |  | Project Name |  | Munucipality | Commencement Date | End Date | Number of Households to be served by completed project | Approved Budget |  |  |  | 2015/2016 HALF YEAR PERFORMANCE REPORT
Output No. 2 |  |  |  | Objectives | Strategies | [7 empty] | KPI | Baseline 13FY14 | Baseline | Quarter 1 Target | Quarter 1 Actual | Evidence Q 1 | Reason and Corrective Action | EXPENDITURE TO DATE | Quarter 2 Target | Quarter 2 Actual | Half Year Actual | Evidence | Reason and Corrective Action | EXPENDITURE TO DATE
|  |  | Water | To implement bulk water supply for augmention of existing water supply in oder to avoid continous water interruptions by June 2016 | By providing sustainable bulk water resources | Underberg Bulk Water Supply Upgrade Phase 2 |  | KwaSani | not yet approved | 2016-06-01 | 3085 | R9906766.47 | 6.1.1 Completed pump house, 6.1.2 installed and functional two pumps and one backup diesel generator 6.1.3 Number of KL reinforce Concrete reservoir | Design report completed | The scheme is completed by June 2015 | Complete 1km pipeline and the pumphouse | Target not met Land issue has been resolved and the contractor has started woring | 1.Signed Consultant report 2. Signed Progress report. 3.Dated photos. | Land agreement was signed and revised programme was submitted by the Contractor. | 0 | 2.5km pipeline completed. Installation of mechanical equipment. | Target not met Contractor completed 4.85 km pipeline. | Contractor completed 4.85 km pipeline. The contractor only completed the Pumphouse site clearance. | Infrastructure Committee report and Engineers report | Phase 2 of the project delayed due to land ownership agreements with the Farmer Mr Anderson. The contractor will submit a revised programme. The installation of mechanical equipments will be achieved on the 3rd quarter 2015/2016 financial year. | 1042777.92
|  |  | Water | To implement water supply scheme | To ensure the provision of clean drinkable water | Pakkies Ext Phase 2 water supply (Ekuthuleni,Thuthukani & Willowdale) |  | GKM | 2013-06-01 | 2016-06-01 | 120 | 900000 | 7km water reticulation pipelines and 20 communal standpipes completed |  | 7km water reticulation pipelines and 20 communal standpipes completed | 7000m water pipelines and installation of 20 standpipes 100% completed | 7000m water pipelines and installation of 20 standpipes 100% completed | 1.Professional Engineers Progress report 2. Infrastructure Committee Progress report. | Target met | 0 | Installation of Break Pressure Tanks (BPT's) | Break Pressure Tanks was installed | 7000m water pipelines and installation of 20 standpipes 100% completed. Break Pressure Tanks installed | Infrastructure Committee report and Engineers report | Target met | 174368.87
|  |  | Water | To implement water supply scheme | To ensure the provision of clean drinkable water | Makhoba Housing Water Project |  | GKM | 2012-06-01 | 2016-06-01 | 1400 | 1000000 | Springfontein reservoirs,pump station building complete. Argyll reservoir, pump station and chlorine room complete |  | Springfontein reservoirs,pump station building complete. Argyll reservoir, pump station and chlorine room complete | Springfontein: Reservoirs commissioning and Argyll: pump station and chlorine room 100% complete | Springfontein: Reservoirs commissioning and Argyll: pump station and chlorine room 100% complete | 1.Professional Engineers Progress report 2. Infrastructure Committee Progress report. | Target met | 548603.56 | Repairs/sealing of reservoirs and commissining of mechanical & electrical equipments in Springfontein. Argyll raw water abstraction 30% complete. | Repairs/sealing of reservoirs and commissining of mechanical & electrical equipments in Springfontein was completed. Argyll raw water abstraction is 30% complete. | Springfontein: Reservoirs & pump station commissioning (repairs/sealing of reservoirs complete).Argyll: pump station and chlorine room 100% complete. Argyll raw water abstraction point (pontoom) 30% complete. | Infrastructure Committee report and Engineers report | Target met | 1101728.72
|  |  | Sanitation | To implement water borne sewer by 2016 | By providing improved waterborne sewer system | Emergency sewer intervention in GKM area |  | GKM | 2014-12-01 | 2016-06-01 | 9000 | 9000000 | 6.2.1. Number diameter completed 6.2.2. number of km collector sewer pipe completed |  | New anabler | 1500 sewer connector completed. 200 bulk pipeline completed | Target not met: Land negotiation with Transnet through the Consulting Engineer | 1.Signed Signed Consultant report 2.Signed Progress report. 3.Dated photos. | Phase 2 of this project delayed due to land ownership negotiations with Transnet and also the construction is between houses which makes difficult to utilize plants/machines. The contractor will provide a revised programme since all excavations are done by hand. | 1255892.9814 | 1100 sewer connector completed ( 200 diameter pipeline) | Target not met: 200m sewer pipeline rectification completed | 200m sewer pipeline rectification completed | Infrastructure Committee report and Engineers report | Phase 2 of this project delayed due to land ownership negotiations with Transnet and also the construction is between houses which makes difficult to utilize plants/machines. The contractor will provide a revised programme since all excavations are done by hand. | 6824104.23
|  |  | Sanitation | To implement water borne sewer system by 2016 | By appointing a service provider to assist the implementation of water borne sewer system | Horseshoe Sanitation Project - New |  |  | not yet approved | 2016-06-01 | 1462 | R 9 000 000 00 | 6.3.1. Number of household connected to waterborne sewer system | Phase 2 under construction | Phase 2 under construction | Supply chain process and advertising for the procurement of the service provider | The Contractor LG Construction has been appointed and is steal busy with contractual requirements | 1. Tender document 2. Advert | Target met | 2484063.5 | Appointment of the service provider, Site establishment and site handover | Contractor appointed, site establishment done and 15 VIP toilets converted to waterborne system (flushable toilets) | Contractor appointed, site establishment done and 60 VIP toilets converted to waterborne system (flushable toilets) | 1.Appointment letter. 2. Register. 3. Project progress report | Target Exceeded | 4440460.3
|  |  | Water | To implement water supply scheme to service 641 householes by June 2016 | By constantly monitoring implementation of the water project | Khukhulela Water Supply |  | Ingwe | not yet approved | not yet approved | 641 |  | 6.4.1. Number of Water abstraction system and Teatment Facility Completion | Design report completed for the last phase (3). 641 HH are already benefitting | Construction of a sustainable water source | None | N/A | N/A | N/A | 0 |  | N/A | N/A | N/A | N/A | 0
|  |  | Water | To implement water supply to service 5944 householdes by 2030 | By constantly monitoring implementation of the water project | Greater Kilimon Water Supply Project |  | Ingwe | not yet approved | 2016-06-01 | 5944 | R20437475.47 | 6.5.1. Number KM pipeline Completed 6.5.2 Number of weir Completed 6.5.3 Number of pump station completed . | Under construction | Construction of abstraction point and bulk lines | Complete 7km pipeline and base of the pump house | 9.5km pipeline completed and Pump house structure is complete | 1.Signed Consultant report 2. Signed Progress report. 3.Dated photos. | Target Exceeded | 0 | Complete 8km pipeline and pump house | 20.824km pipeline andPump house structure is 100% complete | Contractor completed 20.824km pipeline and Pump house structure is 100% complete | 1. Infrastructure Committee report and 2. Engineers report | Target met | 6398249.07
|  |  | Water | To implement water supply scheme to service 1654 householdes by July 2016 | By constantly monitoring implementation of the water project | Greater Nomandlovu Water Supply Scheme |  | Ingwe |  | 2015-09-15 | 1654 | R2024484.94 | 6.6.1 number of km Reticulation Pipeline and interim storage facility completed | Construsction of weir, 2ML resevour and a package plant | Construsction of a package plant and introduction of a bulk pipe line and reticulation | Commisioning and practical hand over | Target not met 1. Rising main completed. 2. 200 kl reservoir completed. 3. Electromechenical works. | Practical completion certificate | Fastrack the pressure testing of steel pipe then handover the project | 5274363.9228 | Commisioning and practical hand over | Target not met 1. Rising main completed. 2. 200 kl reservoir completed. 3. Electromechenical works. | The project is partially completed. | 1. Infrastructure Committee report and 2. Engineers report | Delays due to shortage of water to do pressure testing on pipework before commissioning and practical handover of the entire scheme. The project will be handed over in 3rd quarter. | 14061059.68
|  |  | Sanitation | To implement all the VIP sanitation project identified by the business plan by 2017 | By installing 800 improved ventilated pits toilets | Ingwe Households Sanitation Project |  | Ingwe |  | 2016-06-01 | 800 units | R 3 000 000 00 | 6.7.1 number of units completed | Under construction already 10 063 | 1077 HH will benefit from sanitation facilities by June 2015 | Supply chain process and advertising for the procurement of the service provider | Target met The project was advertised awaiting for appointment of the Service provider in the next quarter | 1. Tender document 2. Advert | Target met | 1309689.98 | Appointment of the service providers and 150 units constructed | Target not met (Appointment of the service providers) | Appointment of contractors has been finalised | Appointment letters and Beneficiary list | Delays due to supply chain process. The 150 units will be achieved on the 3rd quarter 2015/16 | 2281895.76
|  |  | Water | To implement water supply scheme to serve households by 2017 | By constructing 2ML reservoir and 7km bulk pipeline | Bulwer to Nkelabantwana and Nkumba Water |  | Ingwe |  | 2016-06-01 | 2702 | R8000000 | 6.8.1 number of Reservoirs Completed 6.8.2 number of bulk km pipeline. | Reticulation in the form of spring protection | Construction of bulk pipeline and resevour | Site establishment and Reservoir earthworks | pipelaying is 1.8 km air valves are at 75% and scour valves at 70% | 1.Signed Consultant report 2. Signed Progress report. 3.Dated photos. | Target Exceeded met | 1769931.8862 | 1. Complete foundation of the Reservoir and steel reinforcement of wall. 2. Completion of 2km bulk pipeline. | Target not met (Contractor completed 2.3km bulk pipeline and the Contractor is busy with steel fixing of base fondation) | 1. Contractor is busy with steel fixing of base fondation. 2. Contractor completed 4.1km bulk pipeline, air valves are at 75% and scour valves at 70% | 1. Infrastructure Committee report and 2. Engineers report | The contractor that is construction Reservoir is behind programme due to land issue. The land issue has been finalised and the Contractor has started construction. | 6398249.07
|  |  | Water | To implement water supply scheme to serve 5841 households by 2016 | By constantly monitoring implementation of the water project | Greater Mbhulelweni Water Supply Project |  | Ingwe | 2012/03/16 | 2014/10/15 | 5841 | R10266329.78 | 6.9.1 number of kl reservoir completed 6.9.2 number of pump house completed 6.9.3 number of km pipeline completed | Exsting resevour | Equiping of boreholes and construction of bulk pipeline 500m | Completion of 500kl reservoir and 6km bulk pipeline. | 500kl reservoir completed, 9.3 km pumphouse is at 85% | 1.Signed Consultant report 2.Signed Progress report. 3.Dated photos. | Target met | 532156.9476 | Completion of pumphouse and 6 km bulk pipeline. | 100% Completion of pumphouse and 9.5 km bulk pipeline. | 1. Pumphouse is 100% complete 2. 18.5 km bulk pipeline completed 3. 500kl reservoir completed | 1. Infrastructure Committee report and 2. Engineers report | Target met | 19261767.18
|  |  | Water | To implement all the VIP sanitation project identified by the business plan by 2016 | By installing 588 improved ventilated pits toilets | Ubuhlebezwe Sanitation backlog eradication |  | Ubuhlebezwe | 2015-07-01 | 2016-06-01 | 588 units | 2500000 | 6.10.1 number of units completed | Currently 980 HH have been served | 1000 units constructed | Supply chain process and advertising for the procurement of the service provider | Target met The project was advertised awaiting for appointment of the Service provider in the next quarter | 1. Tender document 2. Advert | Target met | 243392.98 | Appointment of the service providers and 100 units constructed | Target not met | Appointment of contractors has been finalised | Appointment letters and Beneficiary list | Delays due to supply chain process. The 100 units will be achieved on the 3rd quarter 2015/16 | 243392.98
|  |  | Water | To implement water supply scheme 2017 | By ensuring adequate bulk water supply | Ixopo - Marianthal Water Supply Project |  | Ubuhlebezwe | 2012-07-01 | 2016-06-01 | 3226 | 2000000 | Total number of Households to be served |  | 2Ml reservoir and water treatment plant completed | Phase 2: 2ML reservoir & Package plant 100% complete. Phase 3: 1,7km water pipeline complete | Phase 2: 2ML reservoir & Package plant 100% complete. Phase 3: 1,7km water pipeline complete | 1.Professional Engineers Progress report 2. Infrastructure Committee Progress report. | Target met | 659114.02 | Commisioning of 2 Ml reservoir and water treatment plant, complete 4km water pipeline | Commisioning of 2 Ml reservoir and water treatment plant, complete 4km water pipeline | Phase 2: 2ML reservoir & Package plant 100% complete. Phase 3: 4,2km water pipeline complete | Infrastructure Committee report and Engineers report | Target met | 1338912
|  |  | Water | To implement water supply scheme | By ensuring sustainable water supply | Ncakubana Water Supply Project |  | Ubuhlebezwe | 2014-07-01 | 2016-06-01 | 1004 | 4500000 | Total number of Households to be served |  | 500kl & 200kl reservoir foundations and concrete walls completed, package plant slab 50% complete | Completion of WTP, Phase AFA to include Mahhehle | Concrete walls of a reservoir and chlorine room completed | 1.Professional Engineers Progress report 2. Infrastructure Committee Progress report. | The MIG funding was exhausted and no money to pay the contractor that resulted to slow progress on site. WTP will be completed within the quarter 2 of 2015/16 | 2291232.01 | Completion of WTP buildings | 500Kl,200Kl reservoirs complete, chlorine room,pump house and 1 Ml package plant (WTP) concrete slab complete. | 500Kl,200Kl reservoirs complete, chlorine room,pump house and 1 Ml package plant (WPT) concrete slab complete. | Infrastructure Committee report and Engineers report | Target met | 3168964.76
|  |  | Water | To implement water supply scheme that will serve 1060 households by 2016 | By constantly monitoring implementation of the water project | Ithubalethu Water Supply |  | uBuhlebezwe | 2015-01-01 | 2015-07-01 | 3226 | R 9 654 876. 78 | 6.11.1 number of kl reservoir completed | Abstraction and bulk line for raw water | Completion of reservoir foundation and 40% reservoir walls for Phase 2. | Completion of 600kl reservoir | 600kl reservoir is complete | 1.Signed Consultant report 2. Signed Progress report. 3.Dated photos. | Target met | 3897203.82 | Commisioning and practical hand over | 600Kl reservoir complete, pipework,bulk meter chambers 80% complete and commissioning | 600Kl reservoir complete, pipework,bulk meter chambers 80% complete and commissioning | Infrastructure Committee report and Engineers report | Target met | 8684953.9
|  |  | Water | To implement water supply scheme that will serve 1060 households by 2016 | By constantly monitoring implementation of the water project | Chibini Water Supply Project |  | uBuhlebezwe | 2015-01-01 | 2015-11-01 | 1162 | R 9 000 000 00 | 6.12.1 Number of Households served with clean drinkable water 6.12.2 number of standpipes with potable water) | Construction of bulk pipeline and a 2ML resevour | Construction of 6km reticulation pipeline. | Completion of 10km pipeline | 31km pipeline and 29 stand pipes completed | 1.Signed Consultant report 2. Signed Progress report. 3.Dated photos. | Target met | 2086982.5 | 17 km pipeline completed | 34km water reticulation pipelines completed and 115 standpipes completed | 34km water reticulation pipelines completed and 144 standpipes completed | Infrastructure Committee report and Engineers report | Target met | 6266589.57
|  |  | Water | To implement water supply scheme that will serve 1060 households by 2016 | By constantly monitoring implementation of the water project | Ufafa Water Supply Project |  | uBuhlebezwe | 2015-01-01 | 2015-11-01 | 1060 | R 14 469 191. 38 | 6.13.1 number of km bulk pipeline 6.13.2 number of standpipes completed | Detailed designs are completed | Completion of 1500m Bulk pipe line from Chibini reservoir to Ntakama reservoir, completion of 2km water reticulation. | 6000m bulk pipe line completed | 17.8 km pipeline and completed 12.2 km testing | 1.Signed Consultant report 2. Signed Progress report. 3.Dated photos. | Target met | 4611424.94 | 9000m bulk pipeline and pump house completed | 18900m bulk pipeline and pump house completed | 18900m bulk pipeline and pump house completed and tested 17950m of water pipelines | Infrastructure Committee report and Engineers report | Target met | 10607020.7
|  |  | Water | To implement water supply scheme that will serve 3562 households by 2017 | By constantly monitoring implementation of the water project | Clydesdale Water Reticulation (Umzimkulu Bulk Supply) |  | uMzimkhulu | not yet approved | not yet approved | 3562 |  | 6.14.1 Number of ML Reservoir Completed | Construction of bulk pipeline and a 2ML resevour and a reticulation | Construction of bulk pipeline and a 2ML resevour and a reticulation | Site Handover | Site was handed over | 1. Registers 2.Signed Project Profile | Target Met, | 0 | Complete the steel fixing for the reservoir concrete walls | steel fixing for the reservoir concrete walls was completed. The contractor is currenly busy with the roof of the reservoir | Site was handed over and the contractor is currenly busy with the roof of the reservoir | 1. Engineers report with photos. 2. Infrastructure Committee report | Target met | 576840
|  |  | Water | To implement water supply scheme to serve 2834 households by june 2016 | By constructing 2ML and 100kl reservoir completed. 16km bulk pipeline completed, 42 standpipes installed and pumphouse | Mnqumeni Water Supply Project Phase |  | uMzimkhulu | 2015-01-01 | 2016-06-01 | 2834 | R 19 000 000 00 | 6.15.1 number of ML and 100kl reservoir completed 6.15.2. km bulk pipeline completed 6.15.6 number of standpipes installed and pumphouse completed | 25000000 | Completion of 2ML and 100kl reservoir foundation | Completion of reservoir concrete walls and 8km reticulation pipeline | Concrete walls of a reservoir completed and 8km reticulation pipeline | 1.Signed Consultant report 2. Progress report. 3.Dated photos. | Target Met | 8655073.173 | Complete the remaining 8km of reticulation and complete the installation of 80 standpipes | 8km of reticulation and the installation of 80 standpipes completed | Concrete walls of a reservoir completed and 16km reticulation pipeline and installation of 80 standpipes. | Infrastructure Committee report and engineers report | Target met | 15361120.43
|  |  | Sanitation | to implement all the VIP sanitation project identified by the business plan by 2020 | By providing of ventilated improved pitlatrines | Greater Umzimkulu Sanitation Project |  | uMzimkhulu | 2015-07-01 | 2016-03-01 | 25612 | 5000000 | 6.17.1 number of units completed | 2360 HH have benefitted | 2400 HH to benefit | Supply chain process and advertising for the procurement of the service provider | The project was advertised awaiting for appointment of the Service provider in the next quarter | 1. Tender document 2. Advert | Target met | 0 | Appointment of the service providers and 300 units constructed | Target not met (service providers were appointed ) | Appointment of contractors has been finalised | Appointment letters and Beneficiary list | Delays due to supply chain process. The 300 units will be achieved on the 3rd quarter 2015/16 | 1296544.14
|  |  | Water | To implement water supply scheme to serve 4985 households by 2016 | By constructing 2ML reservoir and 3.6km bulk pipeline. | Greater Summerfield Water Project |  | uMzimkhulu | 2014-11-01 | 2016-06-01 | 4985 | R18068662.92 | 6.18.1 number of ML reservoir 6.18.2 number of km bulk pipeline completed. 6.18.3 Appointment of a WTP and Abstraction contractor | 15000000 | Completion of 3km bulk pipeline and 2ML reservoir foundation | Completion of 3.6km bulk pipeline. Reservoir walls completed. | 6.6km bulk pipeline completed and the reservoir is complete up to the roof | 1.Signed Consultant report 2. Signed Progress report. 3.Dated photos. | Target exceeded | 910244.4 | Reservoir roof completed. Commisioning and practical hand over | Target not met Reservoir roof completed. | 6.6km bulk pipeline completed .Reservoir roof slab is 100% complete. | Infrastructure Committee report and Engineers report | The project delayed due to late arrival of steel fittings material supply . The contractor is currently busy finishing the steel pipe work. Commissioning and practical handover will be achieved on the 3rd quarter of 2015/2016. | 14848330.71
|  |  | Water | To implement water supply scheme to service 1202 househlods by june 2016 | By constructing 1.5 and 1ML reservoirs, 1.5 ML upgraded Ibisi treatment plant. 171 reticulation pipeline for phase 4. 401 stand pipes installed | KWAMEYI/TEEKLOOF Water Supply |  | uMzimkhulu | 2015-01-01 | 2016-06-01 | 1202 | R23064689.31 | 6.19.1 number of ML reservoirs completed. 6.19.2 number of ML upgraded Ibisi treatment plant. 6.19.3 number of reticulation pipeline for phase 4 completed 6.19.4stand pipes installed | Tender stage | Completion of 2 reservoir foundation ( 1ML and 1.5ML). Completion of 14.6km pipeline | Completion of concrete reservoir walls. Completion of pumphouse | Target Not Met, contractor has not started with the pump house neither the completion of reservoir concrete walls due to non payement by the municipality | 1.Signed Consultant report 2. Signed Progress report. 3.Dated photos. | Contractor under performed and has been called to a meeting by the municipality | 1909035.7122 | Completion of reservoir roofs. Upgrading of Ibisi water treatment works( sedimentation tanks, filtors and pumps 20% complete). Appointment and site establishment of contractor for phase 4 | Target not met The reservoir roof is 15% complete and the Water Treatment works is 10% complete. | TThe appointment of new contractor and site establishment done. The reservoir roof is 15% complete and the Water Treatment works is 10% complete. | 1. Infrastructure Committee report 2. Engineers report and 3. Appointment letter | The contractor is behind programme due to poor perfomance. Municipality to instruct the engineer to issue the second non performance certifcate which will lead to termination. | 2344976.07
MWIG
|  |  | Water | To implement water supply scheme to service 2482 househlods by june 2016 | By constructing 100kl reservoir, 23 600 reticulation pipeline, Installing 55 stand pipes | Mkhunya Water Project |  | Ubuhlebezwe | 2015-04-01 | 2016-06-01 | 2482 | 9532992 | 6.21.1 number of kl reservoir completed 6.21.2 number of reticulation pipeline completed. 6.21.3 number of stand pipes installed. | Currently at detailed design | Complete of package plant, pipe laying of 7800m bulk water pipeline and reservoir. | Site establishment and base of steel reservoir completed. 10 000m reticulation pipeline | Target Not Met draft advert for phase 3 and 14000m bulk pipeline completed for phase 2 | 1.Signed Consultant report 2.Signed Progress report. 3.Dated photos. | Delays in Supply chain processes therefore fastrck the appointment of Service provider | 1966668.2754 | Completion of 13 600m reticulation. Istallation of galvanized reservoir. | 21 140m water reticulation, 100Kl galvanised reservoir and 55 standpipes completed | 21 140m water reticulation, 100Kl galvanised reservoir and 55 standpipes completed | Infrastructure Committee report and Engineers report | Target met | 5535849
RBIG
|  |  |  | To improve water supply in Ingwe and uBuhlebezwe areas | By ensuring the construction of advanced infrastructure for Stephen Dlamini dam | Stephen Dlamini dam |  | Ingwe | 2015-06-01 | 2016-06-01 | 15947 | R 58 200 000 00 | 6.22.1 Complete access road. 6.22.2 Advance excavation 6.22.3 bush clearing complete 6.22.4 Number of box culvet completed |  | 100% completion of gauging weir for the Bulwer emegency intervention water supply and apponintment of 4 advanced infrastructure contracts | Construction of 800m access road completed and 50% bush clearing | Target Not Met Land Agreement has been signed by the Paradise falls | 1.Signed Consultant report 2. Signed Progress report. 3.Dated photos. 4. Land Agreements | Contractors to submit revised programmes | 0 | 1700m construction of access road completed and 50% bush clearing completed | Contractor completed 6016.5m of access road and 51% of Bush clearing completed | 1. Contractor completed 6016.5m of access road and 51% of Bush clearing completed 2.Land Agreement has been signed. | Infrastructure Committee report and Engineers report | Target met
HARRY GWALA DISTRICT MUNICIPALITY
2015/2016 First Quarter Report
Municipal Manager:
Mrs A.N. Dlamini
Note on T5: mbovum: this is comment. What is the actual achieved?
Note on Q6: mchunuk: How many km completed
Note on R6: mchunuk: How many km completed