## FINANCE (hidden)
HARRY GWAL DISTRICT MUNICIPALITY BUDGET AND TREASURY OFFICE DRAFT 2014/2015 ANNUAL PERFORMANCE REPORT
OUTCOME 9 | National KPA | IDP Objective Ref. No. 05 FIN 2014 | Local KPA/ Key Challenge | Objectives | Strategies | Project Name | Budget Estimate | Adjusted Budget | Municipal Indicator | Baseline | [9 empty] | Revised Target
OUTPUT 6 | [8 empty] | KPI | 2013/14 | Quarter 3 | Quarter 3 Actual | Q3 Evidence | Reason and Corrective Action | Quarter 4 | Quarter 4 Actual | Reason and Corrective Action | Q4 Evidence | ANNUAL TARGET'2014/15
Note: The above quarterly report contains actual performance information as at quarter three. The actual results depicted in the report are based on the portfolio of evidence contained in the departmental files. In some instances the targets may have been met but the evidence is either missing or insufficient or irrelevant, which could mean that these results are not a fair presentation of the operations of HGDM. Management is therefore in the process of collating and filling the required evidence such that credible evidence is available on submission of the Annual Performance Report to the Auditor-General. Once the information is collated and filed, the Draft Annual Performance report will be adjusted accordingly.
Administrative and financial capability | Municipal Financial Viability and Management | To improve the financial affairs and viability of the municipality in order to obtain clean audit by 2014 and beyond | Revenue Management | To maximise debt collection by 2015 and beyond. | By increasing revenue collection | Implementation of credit control and debt collection | 1000000 |  | % of billed income collected | 80% | 75% | 80% of debts collected. | 1. Debtors list , debtors collection schedule and monthly receipts | Target met | 80% | Achieved. 108% of debts collected. |  | 1. Debtors list , debtors collection schedule and monthly receipts | Debt collected 80% Debt collection to be increased by 80%.
[9 empty] | Number of meetings held. | new enabler | 1 meeting held | Target not met Not meeting held | 1. Signed attendance register 2. Signed minutes | The meeting could not be held due to the busy schedule of the Meter Readers and the Director Income and Expenditure. A new date will be arranged in May 2015 | 1 meeting held | Not Achieved, No relevant evidence on file. | Reasons and Corrective Action to be stated | 1. Signed attendance register 2. Signed minutes | 4 meetings held
|  |  | Budgeting, Reporting & Financial Systems | To facilitate the effective and efficient allocation of financial resources by 2015 and beyond. | By coordinating the budget preparation process in line with the approved Schedule of Key deadlines. | Budget preparation | R50 000 00 | 150000 | Date by which 2015/16 budget is approved. | Approved 2014/15 Budget by May 2013. | 2015/16 draft budget tabled to Council | Draft budget tabled to council. | Signed Council resolution | Target met | 2015/16 budget adopted by Council | Not Achieved, No relevant evidence on file. | Reasons and Corrective Action to be stated | Signed Council resolution | 2015/16 budget adopted by Council by May 2015. .
[5 empty] | Preparing monthly financial statements | Accounting Services (AFS) | R 1 300 000 00 | 3245161 | Date by which the AFS are submitted to Auditor General (AG). | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | AFS prepared and submitted to Auditor General by 30 September
|  |  |  | To ensure effective financial systems administration by 2015. | By enhancing finance personnel competencies on financial management system functionalities and system support. | Financial Management Systems Training | R300 000 00 |  | Number of staff trained. | new enabler | 4 staff members trained | Target not met No relevant evidence on file. | 1. Signed attendance register 2. Certificates | Reasons and Corrective Action to be stated | N/A | N/A | N/A | N/A | 8 staff members trained .
|  |  |  | To ensure effective, efficient, economical review and implementation of finance policies and by June 2015 and beyond. | By creating financial management policies implementation plan | Review of financial management policies | 300000 | 195000 | Date by which financial management policy adopted by Council. | 2014-05-31 | Workshop conducted to review financial management policies | Target not met No relevant evidence on file. | Signed attendance register | Reasons and Corrective Action to be stated | Policies adopted by Council | Not Achieved, No relevant evidence on file. | Reasons and Corrective Action to be stated | council resolution | Policy adopted by council by June 2015
|  |  |  | To ensure effective, efficient, economical and compliant procurement of goods and services by 2015 and beyond. | By implementing Supply Chain Management process | Data cleansing | 350000 | 250000 | Number of data cleansing conducted. | new enabler | 1 Data cleansing conducted | Target not met No relevant evidence on file. | Register signed by CFO/delegate | Reasons and Corrective Action to be stated | 1 Data cleansing conducted | Not Achieved, No relevant evidence on file. | Reasons and Corrective Action to be stated | Register signed by CFO/delegate | 4 data cleansing conducted
|  |  |  | To have a credible Asset Register that complies with GRAP by end of June 2015. | By conducting asset assessment. | Asset management | R 500 000 00 | 313181 | Number of monthly reports on acquisition, work in progress and completed projects. | 2 | 3 monthly reports on acquisition, work in progress and completed projects. | Target not met, 2 monthly reports on acquisition and work in progress projects. | 3 monthly reports on acquisition, working progress and completed projects signed by CFO/ delegate | Reasons and Corrective Action to be stated | 3 monthly reports on acquisition, work in progress and completed projects. | Not Achieved, 2 monthly reports on acquisition and work in progress projects. | Reasons and Corrective Action to be stated | 3 monthly reports on acquisition, working progress and completed projects signed by CFO/ delegate | 12 monthly reports on acquisition, working progress and completed projects.
1300000
Note on H7: Mthethunzima Mkatu: Advertising Budget Document Printing Postage to NT

## Infra (hidden)
HARRY GWAL DISTRICT MUNICIPALITY INFRASTRUCTURE SERVICES DEPARTMENT DRAFT 2014/2015 ANNUAL PERFORMANCE REPORT | [10 empty] | HARRY GWAL DISTRICT MUNICIPALITY INFRASTRUCTURE SERVICES DEPARTMENT 2014/2015 QUARTER 3 REPORT
Outcome 9 | NKPA | IDP Objective Ref. No. 01 INFR 2014 | Focus Area or Key Challenge |  |  | Project Name | Municipality | Commencement Date | End Date | Number of Households to be served by completed project
Output No. 2 |  |  |  | Objectives | Strategies | [5 empty] | TOTAL PROJECT BUDGET | Adjusted Budget | KPI | Baseline 13FY14 | Quarter 3 | Quarter 3 Actual | Evidence Q 3 | Comments/ Reasons and Corrective action | Quarter 4 | Quarter 4 Actual | Evidence Q 4 | Comments/ Reasons and Corrective action | Annual Target | Adjusted Target
Note: The above quarterly report contains actual performance information as at quarter three. The actual results depicted in the report are based on the portfolio of evidence contained in the departmental files. In some instances the targets may have been met but the evidence is either missing or insufficient or irrelevant, which could mean that these results are not a fair presentation of the operations of HGDM. Management is therefore in the process of collating and filling the required evidence such that credible evidence is available on submission of the Annual Performance Report to the Auditor-General. Once the information is collated and filed, the Draft Annual Performance report will be adjusted accordingly.
Households progressively gain access to sustainable and reliable basic (water, sanitation, electricity and refuse removal) services | Basic Service Delivery and Infrastructure | To improve the coverage, quality, efficiency and sustainability of water and sanitation services in all urban and rural communities. | Water | To supply 241 households with clean portable water by 2014-15 | By constantly monitoring the implementation of the water project | Enhlanhleni Water Project | KwaSani |  | 2015-05-01 | 241 | 1000000 | 854570 | Roofing of the reservoir completed - Yes/No and number of meters of rising main completed | Design report completed | Foundation completed and 40 % reservoir walls completed | Target not met ( foundation completed and 0% reservoir walls completed). | 1. Progress report with photos 2. Project plan | Reason and corrective action | Completed roofing of the reservoir and 400m rising main | Not achieved, 400m rising main 100% completed but no evidence of completed reservoir roofing | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate | Reason and corrective action | Yes - roofing of the reservoir completed and 400m of rising main completed | N/A
|  |  | Water | To implement bulk water supply for augmentation of existing water supply by June 2015 |  | Underberg Bulk Water Supply Upgrade Phase 2 | KwaSani | not yet approved | 2016-05-01 | 3085 | 4580053 | R - | Number of kms of water pipe line completed | Design report completed | Site handover | Target not met ( the appointment of the contractor was done in this quarter) | 1.Signed Site Minutes and / or register 2. Signed Engineers report and Photos. | There were delays in the SCM processes. The project will be expedited in quarter four. | Laying of 1.5km water pipe line | Not achieved, laying of the 1.5km water pipe line is 0% | Progress report with photos signed by Engineer | Reason and corrective action | Laying of 1.5km water pipe line | Laying of 1.5km water pipe line
|  |  | Water | To implement bulk water to benefit 1400 households by December 2014 |  | Makhoba Housing Water Project | GKM | not yet approved | 2015-06-01 | 1400 | 4170979 | 2288612 | Commissioning and project hand over of Springfontein and Argyll completed - Yes/No | Under construction | Commissioning and project hand over of Springfontein | Target not met (project Commissioning and hand over of Springfontein is not done) | 1. Progress report with photos signed by contractor 2. Project plan 3. Practical completion certificate 4. Proof of handover | Reason and corrective action | Commissioning and project hand over of Argyll | Not achieved, project Commissioning and hand over of Argyll is not done, project is 90% | 1. Progress report with photos signed by contractor 2. Project plan 3. Practical completion certificate 4. Proof of handover | Reason and corrective action | Yes - commissioning and project hand over of Springfontein and Argyll completed | N/A
|  |  | Water | To implement water supply scheme to service 641 households by June 2016 |  | Khukhulela Water Supply | Ingwe | not yet approved | Not yet approved | 641 | 3425287 | 499333 | Number of meters pipelines completed | Design report completed for the last phase (3). 641 HH are already benefitting | N/A |  | N/A |  | N/A |  | N/A |  | Complete construction of 500m pipe line 641 households to be served by the completed Khukhulela Water Supply (500m pipe line) | The project was re-prioritized for 2015/2016 financial year
|  |  | Water | To implement water supply to service 5944 households by 2030 |  | Greater Kilimon Water Supply Project | Ingwe | not yet approved | 2015-06-01 | 5944 | 16935900 | R 13 783 163. 00 | Number of MLs of reservoir completed, number of KLs of reservoir completed, pump station completed - Yes/No, and number of meters of pipeline completed | Under construction | Construction of 700m pipeline and completion of reservoir walls | Target not met (consultant report shows previous year's progress and states that the contractor is slow on site). | 1. Progress report with dated photos signed by contractor 2. Project plan | Reason and corrective action | Completion of 300kl reservoir and pump station | Not Achieved, setting out, site clearance are 100% with excavation at 10% Erection and fencing is at 0% | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate | Reason and corrective action | Construction of 300ML Reservoir and 300kl reservoir, Yes - pump station and 1400m pipeline completed | N/A
|  |  | Water | To implement water supply scheme to service 1654 households by July 2016 |  | Greater Nomandlovu Water Supply Scheme | Ingwe |  | 2015-06-01 | 1654 | 13477216 | R 6 220 353. 00 | Number of kms of pipeline completed | Construction of weir, 2ML reservoir and a package plant | Construction of 1.5km pipeline | Construction of 1.5km pipe in progress | 1. Progress report with dated photos signed by contractor 2. Project plan | Target met | Construction of 2km pipeline | Not achieved, 1800m and 200mm of steel pipe is in construction | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate | Reason and corrective action | Construction of 3.5km pipeline completed | N/A
|  |  | Water | To implement water supply scheme by 2017 |  | Bulwer to Nkelabantwana and Nkumba Water | Ingwe |  | 2015-06-01 |  | 7593686 | 5425949 | Completion of phase 1 Rudimentary - Yes/No. Appointment of Phase 2 contractor and site hand over - Yes/No. | Reticulation in the form of spring protection | Rudimentary reticulation will be 90% complete for phase 1. Advertisement of Phase 2 | Rudimentary reticulation 100% completed and advert for phase 2 sent out | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate 4. Copy of advertisement | Target met | Completion of phase 1 Rudimentary. Appointment of Phase 2 contractor and site hand over. |  | Not achieved, only appointment for phase 2 was done. | Reason and corrective action | Yes - phase 1 Rudimentary completed. Yes - appointment of Phase 2 contractor and site hand over completed. | Completion of phase 1 Rudimentary. Site hand over of phase 2
|  |  | Water | To implement water supply scheme by 2017 |  | Greater Mbhulelweni Water Supply Project | Ingwe | 2012/03/16 | 2015-11-01 | 5841 | 3000000 | 2465417 | Number of meters of bulk pipeline constructed | Existing reservoir | 50% reservoir foundation and trench excavation at 40%. | 50% reservoir foundation and trench excavation at 40% Pipe laid and backfield | 1. Progress report with dated photos signed by contractor 2. Project plan | Target met | Construction of 6000m pipeline completed | Not achieved, pipeworks are in-progress at 84% (Upvc pipe) and 56% (110mm uPVC) | 1. Progress report with dated photos signed by contractor 2. Project plan | Reason and corrective action | Construction of 6000m pipeline completed | Construction of 6000m pipeline completed
|  |  | Water | To implement water supply scheme by 2017 |  | Ixopo - Marianthal Water Supply Project | uBuhlebezwe | not yet approved | 2015-06-01 | 1517 | 4240199 | 9157635 | Number of MLs of reservoir completed and number of water treatment plants completed. | Under construction of2ML reservoir and water treatment works | Site establishment for phase 3. | Target not met (no evidence of site establishment) | 1. Progress report with dated photos signed by contractor 2. Project plan | Reason and corrective action | Phase 2 completion of 1 water treatment works and 2ML reservoir. | Not achieved, no relevant evidence of treatment plant | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate |  | 2ML reservoir and 1 water treatment plant completed | N/A
|  |  | Water | To implement water supply scheme by 2017 |  | Ithubalethu Water Supply | uBuhlebezwe | not yet approved | 2015-07-01 | 3226 | 8691523 | R 537 095. 00 | Phase 1 completed - Yes/No, and % completion of reservoir walls for phase 2 | Abstraction and bulk line for raw water | Site establishment for Phase 2. 100% earthworks for reservoir | site established and earthworks for reservoir 100% completed | 1. Progress report with photos signed by contractor 2. Project plan | Target met | Completion of reservoir foundation and 40% reservoir walls for Phase 2. | Achieved, reservoir foundation completed and 60% 600kl reservoir walls completed | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate |  | Yes - reservoir foundation completed and 40% completion reservoir walls for phase 2 | Completion of reservoir foundation and 40% reservoir walls for Phase 2.
|  |  | Water | To implement water supply scheme by June 2015 |  | Ncakubana Water Supply Project | uBuhlebezwe | not yet approved | 2015-06-01 | 1004 | 5832164 | 7815472 | % completion of foundation and slabs for the package plant. % completion of reservoir walls | 4500000 | 50% Complete foundation of reservoirs. 50% concrete slab for the package plant. | Target not met (although foundation of reservoirs and concrete slab for the package plant is 50% complete, there is no credible evidence, i.e. contractor/consultant report to support this). | 1. Progress report with photos signed by contractor 2. Project plan |  | 100% complete foundation and slabs for the package plant. 20% reservoir walls |  | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate |  | 100% complete foundation and slabs for the package plant. 20% reservoir walls | 100% complete foundation and slabs for the package plant. 20% reservoir walls
|  |  | Water | To implement water supply scheme by 2015 and beyond |  | Chibini Water Supply Project | uBuhlebezwe | not yet approved | 2015-11-01 | 1162 | 1363371 | 5603916 | Number of kms of reticulation pipeline completed. | Construction of bulk pipeline and a 2ML reservoir | Site establishment and construction of 2km reticulation pipeline | Target not met ( construction of 2km reticulation pipeline in progress) | 1. Progress report with photos signed by contractor 2. Project plan |  | Construction of 6km reticulation pipeline. | Achieved, 19km of reticulation pipeline constructed | 1. Progress report with photos signed by contractor 2. Project plan | Comments required | Construction of 6km reticulation pipeline completed. | Construction of 6km reticulation pipeline.
|  |  | Water | To implement water supply scheme by 2015 and beyond |  | Ufafa Water Supply Project | uBuhlebezwe | not yet approved | 2015-11-01 | 1060 | 13399165 | 4860423 | Number of meters of Bulk pipe line completed from Chibini reservoir to Ntakama reservoir, number of kms of water reticulation completed. | Detailed designs are completed | Site establishment and laying of 500m bulk pipeline | (site established and 2.5km bulk pipeline laid) | 1. Progress report with photos signed by contractor 2. Project plan | Target met | Construction of 1500m Bulk pipeline and 2km water reticulation. | Not achieved, no evidence of laying 1000m bulk pipeline and 2km water reticulation. | 1. Progress report with photos signed by contractor 2. Project plan |  | Completion of 1500m Bulk pipe line from Chibini reservoir to Ntakama reservoir, completion of 2km water reticulation. | Completion of 1500m Bulk pipe line from Chibini reservoir to Ntakama reservoir, completion of 2km water reticulation.
|  |  | Water | To implement water supply scheme by June 2015 |  | Clydesdale Water Reticulation (Umzimkulu Bulk Supply) | uMzimkhulu | not yet approved | 2015-06-01 | 635 | 1772346 | 3673947 | Number of stand pipes completed and advertisement of another 50 stand pipes - Yes/No. | Construction of bulk pipeline and a 2ML reservoir and a reticulation | Completion of 635 household connections | Target not Met (no evidence of 635 connections) | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate 4. signed confirmation from connected households |  | Advertisement for the construction of 1ML reservoir and installation of 50 stand pipes | Achieved, bid notice with closing date of 12 June 2015 | Bid notice/Advert | Reason and corrective action | Completion of 635 stand pipes and Advertisement of another 50 stand pipes. | Completion of 635 stand pipes and Advertisement of another 50 stand pipes.
|  |  | Water | To implement water supply scheme by June 2015 |  | Mnqumeni (Santombe) Water Supply Project Phase | uMzimkhulu | not yet approved | 2015-10-01 | 2834 | 20647708 | 16875399 | Number of MLs and kls of reservoir foundation completed | 25000000 | Site establishment and completion of reservoir excavation. | site established and trench excavation 00% completed | 1. Progress report with photos signed by contractor 2. Project plan | Target met | Completion of 2ML and 100kl reservoir foundation | Not achieved, 2ML and 100kl reservoir foundation 80% complete | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate | Reason and corrective action | Completion of 2ML and 100kl reservoir foundation | Completion of 2ML and 100kl reservoir foundation
|  |  | Water | To implement water supply scheme by 2020 |  | Greater Summerfield Water Project | uMzimkhulu | not yet approved | 2015-09-01 | 4985 | 10000000 | 10000000 | Number of kms bulk pipeline completed and number of MLs of reservoir foundation completed | 15000000 | Site establishment. Excavation of 2ML reservoir foundation completed | site established, excavation of 2ML reservoir foundation completed | 1. Progress report with photos signed by contractor 2. Project plan | Target met | Laying of 3km bulk pipeline completed. 2ML Reservoir foundation. | Not achieved, bulk pipe trenches 50% complete and 2ml reservoir foundation not completed. | 1. Progress report with photos signed by contractor 2. Project plan | Reason and corrective action | Completion of 3km bulk pipeline and 2ML reservoir foundation | Completion of 3km bulk pipeline and 2ML reservoir foundation
|  |  | Water | To implement water supply scheme to service 62 households by June 2014 |  | KwaTshaka Rural Water Supply (MACHUNWINI) | uMzimkhulu | not yet approved | 2015-03-01 | 62 | 1 487 496 | R 1 255 070. 00 | Number of kms of bulk water pipeline completed and pump house completed - Yes/No. | Reticulation lines in the form of spring protection | Commissioning and Technical hand over | Target not met completion certificate dated 25 June 2013 | Practical Completion certificate. | Reason and corrective action | N/A |  | N/A |  | Complete 3.05km bulk water pipeline and Yes - pump house completed. | N/A
|  |  | Water | To plan and implement water supply by June 2015 |  | KwaMayi-Theekloof Water Supply | uMzimkhulu | 2009/08/01 | 2015-11-01 | 1202 | 18000000 | 14435660 | Yes - reservoir foundation completed. Number of kms of pipeline completed. | Tender stage | Site establishment and 7.3km pipe laying from Ibisi plant to Ethembeni reservoir. | Minutes refer to a site meeting held on 1 December 2014. Laying of 7.3km pipe line is in progress | 1. Progress report with photos signed by contractor 2. Project plan | Target met | Completion of reservoir foundation. Completion of 7.3km pipeline. | Not achieved, no evidence of reservoir foundation and completion of 7.3km pipeline | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate | Reason and corrective action | Completion of 2 reservoir foundation. Completion of 7.3km pipeline | Completion of 2 reservoir foundation. Completion of 7.3km pipeline
|  |  | Water | To implement water supply scheme by 2015 |  | Mangwaneni Water Supply Project | Ingwe |  | 2015-07-01 | 700 | 8045483 | 7668798 | Construction of weir reservoir completed -Yes/No, and % of the water treatment plant completion | Construction of weir, bulk pipeline and reticulation | Completion of reservoir | Target not met reservoir is 80% completed | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate | Reason and corrective action | Completion of base for concrete weir and platform slab for water treatment works | Not achieved, no evidence of completion of base for concrete weir and platform slab for water treatment works | 1. Progress report with photos signed by contractor 2. Project plan | Reason and corrective action | Yes - construction of weir and reservoir completed and 80% of water treatment plant completed | Construction of weir, reservoir and 80% of water treatment plant
|  |  | Water | To implement water supply scheme by June 2015 |  | Pakkies Ext Phase 2 | GKM |  | 2015-06-01 | 334 | R 3.856.315 | 1110033 | Number of kms of reticulation pipeline completed and number of communal standpipes completed | Tender stage | Completion of snag list | Target not met (no evidence of completion of snag list) | 1. Progress report with photos signed by contractor 2. Completion certificate | Reason and corrective action | Complete 7km reticulation pipeline and 20 communal standpipes | Not achieved, V-box protection, installation of stand pipes and steel pipe at Willowdale and Ekuthuleni is 100% complete respectively. But Jojo tank stand is 50% complete and placing of Jojo tank is 0% | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate | Reason and corrective action | Complete 7km reticulation pipeline and 20 communal standpipes | Complete 7km reticulation pipeline and 20 communal standpipes
|  |  | Water | To implement water supply scheme by June 2015 |  | Mqatsheni Water Supply Project | KwaSani |  | 2015-06-01 | 1874 | 9000000 | 8737065 | Number of kms of Mqatsheni reticulation pipeline completed and number of stand pipes installed | Construction of bulk pipelines | Site establishment (Pilcon T/A Sizabonke), 5km pipeline excavation and laying | Target not met (excavation of pipeline is in-progress, laying of pipeline has not been started) | 1. Progress report with photos signed by contractor 2. Project plan | Reason and corrective action | Completion of 23km Mqatsheni reticulation pipeline and installation of 40 stand pipes | Not achieved, the pipeline is on average 85% complete and the 89 stand pipes are 45% complete (none is mentioned about the planned 40 stand pipes) | 1. Progress report with photos signed by contractor 2. Project plan 3. Completion certificate | Reason and corrective action | Completion of 23km Mqatsheni reticulation pipeline and installation of 40 stand pipes | Completion of 23km Mqatsheni reticulation pipeline and installation of 40 stand pipes
|  |  | Water | To implement water supply scheme by June 2015 and beyond |  | Mkhunya Water Project | Ubuhlebezwe |  | 2015-06-01 | 2482 | 5800000 | 8809212 | Number of kls of galvanized reservoir completed, Upgrade of water package plant completed- Yes/No and number of meters of pipe laid. | Currently at detailed design | Laying of 6500m water pipeline. 70% completion of pump station. | 7800m of water pipeline 100% completed. Pump station is at 95% | 1. Progress report with photos signed by contractor 2. Project plan | Target met | Installation of 250kl galvanized reservoir, Upgrade of water package plant and pipe laying of 7800m | Not achieved, galvanized reservoir 100% completed, laying of 7800m pipe is 100%. But there is no evidence of upgrade of water package plant | Engineer`s report with photos 1. Progress report with photos signed by contractor 2. Project plan | Reason and corrective action | Installation of 250kl galvanized reservoir, Upgrade of water package plant and pipe laying of 7800m | N/A
|  |  | Water | To implement water supply scheme by June 2015 and beyond |  | Greater Paninkukhu Water Project | Umzimkhulu |  | 2015-06-01 | 321 | 6000000 | 10153438 | Number of rudimentary water supply schemes completed at Zadungeni, Esicelweni, Nyanisweni and KwaMaduna and number of boreholes equipped at KwaSenti and Bomvini /Mncweba for drought relief. | 1742000 | Completion of 4 Rudimentary schemes at Zadungeni, Esicelweni, Nyanisweni and KwaMaduna. | Target not met there is no evidence of completion of the 4 rudimentary schemes | 1. Progress report with photos signed by contractor 2. Project plan | Reason and corrective action | Sitting, drilling and equipping of 2 boreholes at KwaSenti and Bomvini /Mncweba | Not achieved, there is no evidence that the 2 boreholes at KwaSenti and Bomvini /Mncweba have been equipped | 1. Progress report with photos signed by contractor 2. Project plan | Reason and corrective action | Completion of 4 Rudimentary water supply schemes at Zadungeni, Esicelweni, Nyanisweni and KwaMaduna and equipping 2 boreholes KwaSenti and Bomvini /Mncweba for drought relief. | Completion of 4 Rudimentary water supply and equipping 2 boreholes for drought relief.
|  |  | Bulk water | To improve water supply in I Ingwe and uBuhlebezwe areas by 2015 and beyond | By ensuring the construction of advanced infrastructure for Stephen Dlamini dam | Stephen Dlamini dam |  |  | Not yet approved | 15947 | 28 200 000 00 | 58200000 | % completion of gauging weir for the Bulwer emergency intervention water supply and number of advanced infrastructure contractors appointed | Baseline to be captured | Advertisement of 4 contractors. Application for Stephen Dlamini dam construction license by DWS | Target not met (bid notice for appointment of contractors prepared with closing date of 20 February 204. There is no evidence of license application by DWS). | Advert/bid notice and construction license approval by DWS | Reason and corrective action | 100% completion of gauging weir for the Bulwer emergency intervention water supply and appointment of 4 contractors for advance infrastructure construction relating to Stephen Dlamini dam | Not achieved, 4 contractors have been appointed and 0% completion of the gauging weir for the Bulwer emergency intervention water supply | 1. Progress report with photos signed by contractor 2. Project plan 3. Signed appointment letters | Reason and corrective action | 100% completion of gauging weir for the Bulwer emergency intervention water supply and appointment of 4 advanced infrastructure contractors | 100% completion of gauging weir for the Bulwer emergency intervention water supply and appointment of 4 advanced infrastructure contractors
|  |  | Sanitation | To implement water borne sewer by 2016 | By providing improved waterborne sewer system | Horseshoe Sanitation Project - New | GKM | not yet approved | 2015-06-01 | 1462 | 3551670 | R 3 638 718. 00 | Number of HH connected to sewer system | Phase 2 under construction | N/a | Site establishment was done in this quarter however this was carried forward from quarter two | 1. Progress report with photos signed by contractor 2. Project plan | Target met | Connection of 150 HH to sewer system | Not achieved, there is no evidence of connection of 150 HH | 1. Progress report with photos signed by contractor 2. Project plan 3. Beneficiary confirmations signed by beneficiaries | Reason and corrective action | Connection of 150 HH to sewer system | Connection of 150 HH to sewer system
|  |  | Sanitation | To upgrade existing infrastructure to service 1392 households by June 2016 |  | Umzimkulu Sewer Upgrade Phase 2 | uMzimkhulu | not yet approved | not yet approved | 1392 | 7000000 | 1675835 | Number of meters of reticulation completed and upgrading of sewer pump station - Yes/No. | Designs are under development | N/A | N/A | N/A | N/A | N/A |  | N/A |  | Complete 5500m reticulation and Yes - upgrading of sewer pump station completed. | The project was re-prioritized for 2015/2016 financial year
|  |  | Sanitation | To implement all the VIP sanitation project identified by the business plan by 2017 | By providing improved ventilated pits toilets | Ingwe Households Sanitation Project | Ingwe |  | 2015-06-01 | 15656 | 101,402,919 | 5847814 | Number of VIP units installed | Under construction already 10 063 | 200 unit installed | Achieved, 757 units constructed. | 1. Beneficiary list 2. Signed beneficiary confirmations | Target met | 484 units constructed | Not Achieved, no relevant evidenced on file | 1. Beneficiary list 2. Signed beneficiary confirmations | Reason and corrective action | 1044 VIP units installed | N/A
|  |  | Sanitation | To implement all the VIP sanitation project identified by the business plan by 2020 |  | Greater Umzimkulu Sanitation Project | uMzimkhulu | not yet approved | 2015-03-01 | 25612 | R 7.455.307 00 | 11083620 | Number of VIP units installed | 2360 HH have benefitted | 92 units constructed |  | 1. Beneficiary list 2. Signed beneficiary confirmations |  | N/A |  | N/A |  | 1112 VIP units installed | 1092 units completed
|  |  | Sanitation | To implement all the VIP sanitation project identified by the business plan by 2017 |  | Ubuhlebezwe Sanitation backlog eradication | Ubuhlebezwe |  | 2015-06-01 | 9842 | 8000000 | 5213540 | Number of VIP units installed | Currently 980 HH have been served | 250 unit constructed | 305 units installed | 1. Beneficiary list 2. Signed beneficiary confirmations | Target met | 150 units constructed | Achieved, 215 units installed | 1. Beneficiary list 2. Signed beneficiary confirmations |  | 600 units installed | 600 units will be constructed
|  |  | Building | To construct disaster management centre by June 2014 | By ensuring proper management of disaster incidents | Disaster Management Centre | Ubuhlebezwe |  | 2015-06-01 | ALL | R 7.252.399m | R 7.252.399m | Percentage Completion of construction of the Disaster management centre | Construction currently at 60% | N/A | N/A | N/A | N/A | N/A |  | N/A |  | 100% complete Disaster Management Centre by October 2014 | N/A
Note on M5: mchunuk: Budget to be adjusted to 2.5m because the contractor was not appointed in 2013/2014
Note on M13: mchunuk: Upwards Budget Adjustment from Mkhnunya(4m)to make it 8.2 m.
Note on M16: mchunuk: Adjusted upwards to 5.3m

## SDA (hidden)
Outcome 9 | NKPA | IDP Objective Ref. No. 01 INFR 2014 | Local KPA | Objective | Strategies | Projects | Locality | Budget Estimate | KPI | Responsible department | Baseline | Annual Target | MTEF Target Date and Budget
Output No. 2 |  |  | Key Challenge | [7 empty] | 2012-2013 | 2013-2014 | Q1 | Q2 | Q3 | Q4
|  |  | Tourism | To develop additional disrtict tourism events on Rail Tourism | By creating a tourism event calender for the disrtict | 1.Tourism Month Celebration 2. Aloe festival | District Wide | 1.R 200 000 2. R 50 000 | Number of tourism events held/supported | Tourism Unit | New enabler | 2 Rail tourism events held/supported | 2 Rail tourism events held/supported | None
|  |  |  | To establish a district tourism marketing programme to market the district | To attennd marketing exhibishion shows | Tourism Exhibition Shows |  | 68000 | Number of tourism exihibition shows attended | Tourism Unit | New enabler | 4 Tourism shows attended | Exhibit at the Gataway Show | None | Exhibit at the Cape Town Gataway Show | Exbhibit at a Tourism Indaba and Royal show
[5 empty] | To develop a Tourism broucher DVD | Tourism broucher DVD | District Wide | 60000 | Approved Developed DVD | Tourism Unit | New enabler | Completed DVD | Engage service providers through the SCM processes for the development of a tourism brochure DVD | Tourism Brochure DVD is developed | None
[5 empty] | Inserts in various tourism sector specific publications | Marketing of SDA tourism and investment opportunities and/or products | District Wide | 70000 | Number of Inserts posted in sector specific publications | Tourism Unit |  | 3 inserts in various marketing publications | Prepare and post insert for inclusion in the East Cape publishersTourism directory | Prepare inserts in Explore SA and Country Live Magazine. | Post inserts in SA Explore and Country Live Magazine | none
|  |  |  | To promote community involvement and general tourism awareness and tourism initiative | By conducting tourism awareness campaings amongst the tourism trade, local communities and schools | Conducting tourism awarness campaign | District Wide | 40000 | Number of tourism awarness campaings held | Tourism Unit |  | 5 tourism awareness campaigns held | 1 tourism awarness held | 2 tourism awarness held | 1 tourism awarness held | 1 tourism awarness held
|  |  |  | To provide art and craft support | To develop an arts curio Shop within the Sisonke Farmers Market | district art and craft curio shop | District Wide | 100000 | Arts and Craft Curio shop operational | Tourism Unit |  | Operational art and craft curio shop | Seivice provider is appointed in line with SCM policy and procedures | Arts and craft shop is developed |  | Arts and Craft Curio Shop is operational
[5 empty] | Identification and approval of 10 Crafters for training on trend design & Product Presentation | Training of Crafters | District Wide | 100000 | Number of crafters trained | Tourism Unit |  | 10 Crafters trained on Trend Design and Product Presentation | Identification and Selection of crafters to be trained | Engage service providers through the SCM Processes | Training of the 10 selected crafters in Trend Design and Product Presentation
|  |  |  | To provide after care support upport to Ntsikeni Eco- Tourism Enterprise | Monitor the operations of the business | Ntsikeni Eco Tourism Project. | District Wide | 300000 | SLA Signed and R300 000 transferred | Tourism Unit | New enabler | Signed SLA with new Operator and transfer funding. | monitor signing of funding Tripatide agreement and signing agreement is in place |  | Monitor operation of the lodges | Monitor operation of the lodges
|  |  |  | To facilitate the development of district tourism master plan for 5 years | By developing a comprehensive District tourism master plan | Tourism master plan | District Wide | NIL | Date on which the Tourism master plan is adopted by the SDA board of directors | Tourism Unit | New enabler | Adopted District Tourism Strategy and Plan | Engage service providers through the SCM processes for the development of the district Tourism Strategy and Plan | Development of District Tourism Master Plan |  | None
|  |  |  | To develop a tourism mentorship programme | by mentor 5 established tourism enterprises | Tourism mentorship programme | District Wide | NIL | No of enterprises mentored | Tourism Unit | New enabler | 5 tourism enterprises mentored | Identification and Selection 5 Tourism enteprise for mentoring | 5 tourism enterprises are mentored | monitor and report outsomes of the mentorship programme
Outcome 9 | NKPA | IDP Objective Ref. No. 01 INFR 2014 | Local KPA | Objective | Strategies | Projects | Locality | Estimated Budget | KPI | Responsible Department | Baseline | Annual Target | Target Date (2013/2014)
Output No. 2 | [10 empty] | 2012/2013 | 2013-2014 | Q1 | Q2 | Q3 | Q4
|  |  | BR& E | To establish an animal feeds plant in the district to meet the rapidly increasing demand for feed | By developing a business plan to source funding for the establishment of the feeds plant. | Animal Feeds Plant | Kokstad | 200000 | Bankable Business Plan for the establishment of the plant | Trade and Investment | New Enabler | Business and Implementation Plan | Advert and appointment of service provider | Business plan development and PSC establishment | Engagements with Investors | Social facilitation/Site identification
|  |  |  | To set up a Concrete products manufacturing plant to leverage opportunities for major civil works within the district | By developing a business and implementation plan,establish a Concrete manufacturing Plant,conclude a MOU with a concrete products manufacturer | Concrete products manufacturing | Umzimkhulu | 150000 | Operational Concrete Products manufacturing plant | Trade and Investment | New Enabler | Concrete Products Manufacturing Plant | Busines Plan,MOU with the Co-op,Procurement of Block Making Machinery,Cement,(MOU with Conloo) | Development of an enhanced Business Plan | Engagements with a private partner for mentoring and possible cooperation(Conloo has already been approached) | Fully operational Concrete manufacturing plant launched
|  |  |  | To build a vibrant Chemical Industry in Sisonke | By engaging in research,commercial planting,pilot projects and procurement of Distillation Plant | Sisonke Essential Oils Project | Umzimkhulu | 500000 | Irrigation infrastructure,Essential Oils,Environmental Impact Assessment | Trade and Investment | New Enabler | Completed Business Plan | Appoint a service provider for the development of a business plan | Inception report | Draft Business Plan | Completed Business Plan
|  |  |  | To plant vegetables using hydroponic farming methods | Production of cash crops through out the year to alleviate poverty in the district | Sisonke Hydroponics Farming Project | Ubuhlebezwe | 200000 | Hydroponic expertise and infrastructure | Trade and Investment | New Enabler | Business and Implementation Plan | Advert and Appointment of S.P for Business Plan | Business and Implementation Plan approved to source funding | Engagements with Stakeholders,TIKZN,NEF,IHALA for collaboration | Train coops on running and managing hydroponic farming
|  |  |  | To turn the district into an established manufacturing base for school uniforms and work-wear | By supporting cooperatives within the L.M`s;procuring sewing machines and fabric | Clothing and Textiles | Umzimkhulu | 400000 | Operational Clothing and Textile Hub in uMzimkhulu | Trade and Investment | New Enabler | An operational Clothing and Textiles Hub | Procurement of Embroidery machine and Fabric.Secure premises in Gateway,uMzimkhulu. | Signing of the MOU between supplier of fabric and Co-op to supply on demand. | Commission the Clothing and Textile Hub in uMzimkhulu | 1st production monitoring report
|  |  |  | To set up a Milk Processing plant in Sisonke to produce cheese,yoghurt,powdered milk etc. | By developing a business plan to source funding for the establishment of the milk processing plant. | Milk Processing(Down-stream beneficiation) | Kokstad | 200000 | Bankable Business Plan for the establishment of the plant | Trade and Investment | New Enabler | Business and Implementation Plan | Service Provider to prepare business plan appointed | Business and Implementation Plan approved to source funding | Conduct social facilitatioin with local communities | Engage various investors for funding
|  |  |  | To stimulate economy, encourage growth by retaining and expanding business creating much more needed employment thus inspirering business sector confidence | Facilitate the implementation of the BR& E Programme | BR & E Programme | District Wide | Inhouse | BR&E Programme Launch | Trade and Investment | New Enabler | BR& E Programme Launch | Engage TIKZN for the appontment of the BR& E consultant | BR& E Consultant appointed. | Develoment and approval of a Programme roll out plan | BR& E Programme Launch
ENTERPRISE DEVELOPMENT
Outcome 9 | NKPA | IDP Objective Ref. No. 01 INFR 2014 | KPA | Objective | Strategies | Projects | Locality | Budget Estimate | KPI | Responsible department | Baseline | Annual Target | MTEF Target Date and Budget
Output No. 2 | [10 empty] | 2012-2013 | 2013-2014 | Q1 | Q2 | Q3 | Q4
|  |  | Business Support | To develop LED Implementation Plan | Develop LED Implementation Plan | LED Implementation Plan | District Wide |  | Approved LED Implementation plan | Enterprise Development Unit | New enabler | Aproved LED and SMME Strategy and Implementation Plan | Procure service provider through SCM processes | Draft LED and SMME support Strategy drafted | Final LED and SMME Strategy and Implementation Plan approved | Commence with the implementation of the recommendations from the Strategy
|  |  |  | To prioritise enterprenueship and the advancement of SMMEs as the catalyst to achieving economic growth and development. | Develop an SMME Development Strategy and Implementation Plan | SMME Development Stategy and Implementation Plan | District Wide | 300000 | Approved SMME strategy and Implemenation plan | Enterprise Development Unit | New enabler
[5 empty] | Developing the SMME support Programme | Multi-Sectoral SMME Networking Seminars and SMME Support | 5 Local Municipalities | 100000 | No of Sectoral SMME Networking seminars hosted and SMMEs supported | Enterprise Development Unit | 4 | 2 Seminars and 2 SMMEs supported | 1 Seminar | Support one SMME | 1 Seminar | Support one SMME
|  |  |  | To support emerging contractors | By providing training | Develop and implement a training programme | District Wide | 200000 | No. of contractors under the mentorship programme | Enterprise Development Unit | New enabler | Training of emerging contractors | Database of Small and micro contractors in place | Training programme approved | 50% of the programme activities completed | Training programme implemented in full (100%)
|  |  |  | To profile informal business stakeholders | Design simple excel/Access database template with key relevant fields | SMME, Cooperatives and Unemployed youth database | District Wide |  | Approval of SMMME, Cooperatives and Unemployed youth database | Enterprise Development Unit | New enabler | Updated database | Design the tool for collecting data and commence with collecting data | Data base of Sisonke SMMEs, Cooperatives and Unemployed Youth completed | Date bases in place | Data bases in place
|  |  |  | To improve coordination of economic development planning and implementation across government sectors and non government actors | Facilitate and hold LED and Tourism Coordinating Forum | LED and Tourism Coordinating Forum | District Wide | 80000 | No of LED and Tourism Forum hosted | Enterprise Development Unit | 4 | 4 Forum Hosted | 1 Forum | 1Fforum | 1 Forum | 1Forum
AGRI-BUSINESS
Outcome 9 | NKPA | IDP Objective Ref. No. 01 INFR 2014 | Local KPA | Objective | Strategies | Projects | Locality | Budget Estimate | KPI | Responsible department | Baseline | Annual Target | MTEF Target Date and Budget
Output No. 2 |  |  | Key Challenge | [7 empty] | 2012-2013 | 2013-2014 | Q1 | Q2 | Q3 | Q4
|  |  | Land Reform and Agri-Business Development | To support Emerging Farmers | Provide inputs and market support | Support for emerging farmers | Umzimkhulu Ingwe Ubuhlebezwe | 800000 | 6 commodities produced by emerging farmers for NSNP,over 49 ha approved by DoE | Agri-Business Development | New enabler | Production of 2,134,608 kg`s per annum of 6 commodities for the NSNP | Formulation of farmers and commodity database. Attending to farmers request for funding assistance.provide space in the market for each commodity | Formulate LM's annual crop production plan in line with NSNP | Facilitate process of commodity grouping and signing of agreements/contracts | Monitor production and deliveries to the market to ensure vegitables are available as per NSNP menu
|  |  | Rural Development and Land Reform Support | To support co-operatives for maize massification | Provide inputs and supporting infrustructure | Maize massification | Umzimkhulu | 1000000 | Maize production identified in uMzimkhulu | Agri-Business Development | New enabler | 130 ha prepared,ploughed and planted for massive maize production | Social facilitation,engagements with relevant govt departments,develop productin plans,land preparation | Maize planting,spraying,hoeing.finalise outstanding off-take agreements,signing of MOU`s with govt entities/departments | Facilitate consultations between maize market and maize producers.Harvesting | Monitor production and ensure farmers maize reaches maize milling
|  |  | Rural Development and Land Reform Support | To support Emerging Farmers | Repair and maintain the market,furnish/procure relevant equipment,signed leases | Sisonke Farmers Market | Buhlebezwe | 1000000 | Operational farmers market | Agri-Business Development | New enabler | Furnish the Farmers market and commence operations. | Draw up farmers market business/ operational plan. | Engagements with all relevant stakeholders. Appointment of a service provider for repairs and maintanance and shopfitting | Official launch of the Farmers Makert | Opertaional Farmers Market
|  |  |  | To support the development of large scale commercial agriculture and coordinate effective intergration of farmers with domestic and external markets | To provide post settlement support to land reform beneficiaries | Post settlement support | Umzimkhulu KwaSani Ingwe Ubuhlebezwe Kokstad | 5100000 | Completed CDCs and MICs | Agri-Business Development | New enabler | Facilitate release of DBSA funding and complete CDC and MICs | Identify and finalise sites in all Local Municipalities | Procure service provider through SCM process / Train cooperatives | Shopfitting CDC and MIC equipment | Establish website for the CDCs and MICs.
FINANCE
|  |  | KPA | Objective | Strategies | Projects | Localty | Budget Estimate (Q3 + Q4) | KPI | Responsible department | Baseline | Annual Target | Target Date and Budget (2013/14)
[11 empty] | 2012/13 | 2013/14 | Q1 | Q2 | Q3 | Q4
|  |  | Risk management | Ensure that SDA objectives are achieved | Identify and evaluate the actual and potential risk areas and devise a process of either termination, transfer, tolerance or mitigation of each risk. | n/a | inhouse | 0 | Number of risk reports | Office of the CEO | n/a | Conduct risk assessment and produce reports | N/A | Risk assessment conducted | Risk Management Framework approved. Workshop employees on risk management. | Risk management progress reports produced monthly. 100% awareness
|  |  | Board capacitation | Provide support to the Board to ensure its effectiveness | By facilitating development of board members | n/a | inhouse | 75000 | Effective Board and its committees operating in line with their approved charters | Office of the CEO | N/A | Number of Board meetings and approved charters | Charters developed and approved | Board Secretariat in place | Board development opportunities identified.Take minutes accurately and distribute them in 7 days. Prepared Board packs and distributed 3 days before the meeting. Accurate filing system. | Take minutes accurately and distribute them in 7 days after the meeting. 100% minutes filed and approved as per the number of minutes.Developed checklist for Board Performance.Developed Annual Work Plan for Board.Prepared Board packs and distributed 3 days before the meeting.
|  |  | Support Implementation of an operational and Strategic Internal Audit Plan | To test the efficiency and effectiveness of internal controls | Planning and performing audit assignments as per the the approved operational & strategic internal audit plan | n/a | inhouse | 300000 | Number of audits performed per Quarter as per approved plan | Finance | N/A | Functional Finance Department | Advertised for Internal Audit services | Appoint IA Service Provider | Approved 3 year audit plan and annual audit plan | Annual Audit Plan implemented
|  |  | Revenue Management | To ensure that cash is available to meet SDA financial obligations | To develop budget monitoring policy,debtors and creditors policies | n/a | inhouse | 0 | All SDA financial obligations met when due | F & A | N/A | All SDA financial obligations met. All commitments to be backed by cash by year-end | Development of cash and revenue management policies,namely budget monitoring,debtors and creditors | All Policies approved and workshopped by all staff and implemented. | Implement policies and procedures with no deviation | Monthly reports produced on revenue and expenditure management
|  |  | Budget Reporting and Financial Systems | To provide reliable and timeuos financial information for decision making purposese | By producing financial reports in line with the MFMA and MBRR(Municipal Budgeting & Reporting Regulations) | n/a | inhouse | 150000 | MFMA s87 and s88 reports done | F & A | N/A | Monthly Income & Expenditure reports,Quartely Income & Expenditure reports,MTREF and Financial year end Financial Statements all done at the due dates | N/A | Quartely Income & Expenditure reporting,Quartely Income & Expenditure reporting,MTREF. | 1. Develop comprehensive Management Reporting and Budget formats. 2. Finalise System implementation (Pastel) and population of financial data. | 1. Audit readiness and year-end report preparations. 2. Upgrade system from Pastel Partner to Pastel Evolution (Data Migration).
|  |  | Supply Chain Management | To procure goods and services for the entity in compliance with MFMA | To review and implement SupplyChain Management Policy | n/a | inhouse | 0 | Approved Supply Chain Management Policy | F & A | N/A | Reviewed and approved Supply Chain Management Policy | N/A | Review Supply Chain Management Policy | Develop SCM systems (controls) and implement. | All SCM systems implemented accordingly.
|  |  |  | To ensure that requisitions for goods and services are procured timeously. | Implement efficient standard of responding to procurement requests | n/a | inhouse | 21000 | Turnaround time for procuremtent. | F & A | N/A | Database of service provider in place. | N/A | N/A | 1. Advertise service providers to register on the database. 2. Develop procurement and contract management standards. 3. Train Bid Committees. | Implement procurement and contract management standards
Business Development
|  |  | Human Resource Management | To ensure that the organisation is staffed with the right skills at the right time | Advertise and timeously recruit | n/a | inhouse | + | Turnaround time for advertising, conducting interviews and appointments | F & A | N/A | All vacancies should be filled | N/A | N/A | Advertise all approved vacancies | Fill in all vacancies
|  |  |  | To monitor the organisation's adherence to HR Policies and Industry Best Practice | Review and Implement HR Policies and Practices | n/a | inhouse | 0 | A minimum of three HR related policies to be submitted for approval | F & A | N/A | Compilation of HR Policies | N/A | N/A | Implement HR Policies | Communication and sign off all approved policies
|  |  |  | To facilitate the organisation's performance management system with a view to optimally utilise the human resource | Compile SDBIP for all Departments | n/a | inhouse | + | A produced consolidated SDBIP | F & A | N/A | Consolidated SDBIP for the year | N/A | N/A | Performance Report | Compiled Performance Report and annual SDBIP
[6 empty] | n/a | inhouse
[6 empty] | n/a | inhouse
[6 empty] | n/a | inhouse
0
|  |  | Facilities | To have credible asset register that complies with GRAP | Conduct asset assessment | n/a | inhouse | 0 | All Assets verified | F & A | N/A | Complete assets register | Compile Asset register | All asset purchased barcoded and captured on the asset register. Asset register reconciled monthly to GL | Asset register reconciled to GL. All assets verified for existence and balance to asset register. | Complete assets register which complies with GRAP requirements
|  |  |  | To ensure adequate access control over the Agency's building | Assess and procure security equipment and system | n/a | inhouse | 730000 | Erected boom gate and installed electronic access | F & A | N/A | Improved physcial security | N/A |  | Source provider | Erect the gate
|  |  |  | To have intergrated IT applications, hardware and support | Request closed proposals | n/a | inhouse | 150000 | % down time | F & A | N/A | Improved IT environment | N/A | n/a | Secure service provider | improve the IT infrastructure
Business Development
|  |  | Local KPA | Objective | Strategies | Projects | Locality | Estimated Budget (Revenue) | KPI | Responsible Department | Baseline | Annual Target | Target Date (2013/2014)
[11 empty] | 2012/2013 | 2013-2014 | Q1 | Q2 | Q3 | Q4
|  |  | Business Development | To seek funding for the implementation of the project | By reviewing the business plan to source funding for the implementation of the project. | Hydrophonics | Ixopo |  | Hydroponic expertise and infrastructure | Business Development | New Enabler | Secure funding for the project | N/A | N/A | Review business plan and do presentation to one funder | Available funding and commencement of the Hydrophonic project
|  |  |  | To seek funding for the implementation of the project | By developing a business and implementation plan,secure mentorship from Conloo | Brick Manufacturing | Nzombane, Mzimkulu |  | Operational Concrete Products manufacturing plant | Business Development | New Enabler | Secure funding for the project | N/A | N/A | Establish a block market, curb market and approach Mondi Zimele Fund | Available funding and commencement of Brick Manufacturing project
|  |  |  | To seek funding for the implementation of the project | By shaping the business plan accordingly | Maize mill | Mzimkulu |  | Operational maize mill | Business Development | New Enabler | Secure funding for the project | N/A | N/A | Develop Business Plan | Available funding for the maize mill project
|  |  |  | To seek funding for the implementation of the project | By developing a business plan | DMT Essential Oils | Mzimkulu |  | Essential oils | Business Development | New Enabler | Secure funding for the project | N/A | N/A | Identify potential funders and establish relations | Available funding and commencement of DMT Essential Oils
|  |  |  | To seek funding for the implementation of the project | By developing a business plan | Tourism Master Plan | Mzimkulu |  | Tourism Masterplan | Business Development | New Enabler | Secure funding for the project | N/A | N/A | Prepare funding requests to DEDT andTKZN | Funding for the Tourism Master plan

## SSDP
0
Outcome 9 | NKPA | IDP Objective Ref. No. 04 LEDSOC 2014 | Focus Area | Objective | Strategies | Projects | Approved Budget | KPI | Baseline | 2015-2016 Half-Year Performance Report | [9 empty] | Expenditure to Date
Output No 3 | [8 empty] | 2014-2015 | Quarter 1 | Quarter 1 Actual | Q1 Evidence | Reason and Corrective Action | Expenditure to Date | Q2 Target | Q2 Actual | Half-Year Actual | Evidence | Reason and Corrective Action
| LOCAL ECOMIC AND SOCIAL DEVELOPMENT | To increase the GDP of HGDM by 3% by 2030 so as to improve the socio-economic welbeing of it citizens | Disaster Management equipment (Gym) | To faciliate the procurement of additional equipment for the DMC | By deloping the specification and submitting to SCM unit to facilitate the procurement | Disaster Managemnt Equipment. | R200 000 00 | 4.1. Date in which the gym equipment for the disaster centre is procured | New enabler | Appoint a service proviver to assist in the procument of a gym | the service provider was not appointed and the gym was not equipment procured | N/A | This project was put on hold since the gym was no longer a priority in relation to critical challenges faced by the district e.g drought | R0- | N/A | N/A | N/A | N/A | N/A | R0-
|  |  | Fire beaters | To Facillitate Procurement of Fire Beaters | By deloping the specification and submitting to SCM unit to facilitate the procurement | Procurement of Fire Beaters | 80 000 00 | 4.2. Number of Fire Beaters procured and distributed to relevant stakeholders | 50 | Procurement of 100 fire beater | 100 fire beaters procured | 1.Invoice |  |  | Awareness, training and distribution of 100 fire beaters |  |  |  |  | 29980
[13 empty] | Target met | 29980 |  | Awareness, training and distribution of 100 fire beaters | 200 fire beaters were procured | 1. Atendance register 2.Photos 3. Invoice | Target not met
|  |  | Disaster incidents | To respond and conduct assessments within 5 hours | By engaging DMV depending on the magnitude of the incidents | Effective response to disasters | 100 000 00 | 4.3.Turnaround time in response to disaster incidents occurred and reported | Within 5 Hours | Respond within 5 hours | 41 incidents were responded to within 5 hours and assessed | Assessment forms |  |  | Respond within 5 hours |  |  |  |  | 6000
[13 empty] | Target met | 6000 |  | All incidents were responded to within 5 hours | All incidents were responded to within 5 hours | Assessment forms | Target met
|  |  | Disaster relief material | To acquire Disaster Relief Material | By deloping the specification and submitting to SCM unit to facilitate the procurement | Acquisition of Relief Material | 700 000 00 | 4.4. 1. Number of blankest 4.4.2. Number of mattresses. 4.4.3. Number of plastic sheets and 4.4.4. Number of food parcels | 600 blankest, 600 mattresses, 600 plastic sheets and 90 food parcels | 400 blankest, 300 mattresses, 25 plastic sheets and 50 food parcels | specification for the procurement of disaster relief material has been developed and submitted to SCM, however disaster material could be procured because there was enoung stock | 1. Invoice 2. Register |  |  | 400 blankest, 300 mattresses, 25 plastic sheets and 50 food parcels |  |  |  |  | 577183
[13 empty] | Target not met. Disaster material could be procured because there was enoung stock | 397230 |  | 300 blankets, 300 mattresses and 60 food parcels were procured | 300 blankets, 300 mattresses and 60 food parcels were procured | 1. Invoice 2. Register | Target met ( We could not procure 400 blankets because there were many blankets that were on stock and COGTA donated plastic sheets )
|  |  | Lightning conducters | Installation of Lightning Conductor Infrastructure | Identification of areas prone to Lightning | Supply and Installation of Lightning Conductors | 200 000 00 | 4.5. Number of lighting conductors intalled | 50 | Supply chain process and Advertising | Terms of reference have been developed. | 1.Terms of Reference 2. Advert 3. Registers |  |  | Appointment of the service provider |  |  |  |  | R0-
[13 empty] | Target not met, due to the change in the instalation method. Amended terms of reference have been submitted to SCM | R0- |  | The services has not yet been appointed | Target not met | 1.Terms of Reference 2. Advert 3. Registers | Terms of reference had to be amended to cater for the method of installation that is cost effective and that will benefit the greater population targeted. The advert will go out in January 2016
MUNICIPAL HEALTH SERVICES UNIT
AN EFFECTIVE CLIMATE CHANGE MITIGATION AND ADAPTATION RESPONSE | LOCAL ECONOMIC AND SOCIAL DEVELOPMENT | To increase the GDP of HGDM by 3% by 2030 so as to improve the socio-economic welbeing of it citizens | Municipal Health by-laws | To amend and gazette municipal health by-laws | By engaging the municipal legal team to assit in amending and gazetting the By-laws | By-laws amendment and gazetting | R30 000 00 | 4.6. Date in which the municipal health by laws are amended | New enabler | Development of Terms of reference, Advertising and supply chain recruitment process | Terms of reference have been developed for the review of bylaws. | Terms of Reference | target met | R0- | Appointing the srvice provider and draft document in place | Service provider has not been appointed | Target not met (Terms of reference have been developed for the review of bylaws). | 1.Terms of Reference | The unit working together with supply chain will fastrack the advert and the appointment of a Service Provider in the 3rd quarter | R0-
|  |  | Health and Hygiene awareness | To conduct 12 Health and Hygiene Awareness Campaigns Annually | By conducting Health and Hygiene Awareness Campaigns to communities prone to communicable diseases | Health and Hygiene Awareness Campaigns | 50 000 00 | 4.7. Number of Health and Hygiene awareness campaigns conducted | 12 | 3 Health and Hygiene awareness campaigns | Five Health & Hygiene awarenesses conducted | Attendance register | target met | R20 500 00 | 3 Health and Hygiene awareness campaigns | 3 Health and Hygiene awareness campaigns were held | 6 Health and Hygiene awareness campaigns were held | Attendance register | Target met | 20500
|  |  | Pauper burial and reburial | To manage, control and monitor exhumations and reburial or disposal of human remains | To attend to all exhumations, burial of pauper and destitute corpses in terms of policy | Disposal Of the dead (Human Remains) | 50 000 00 | 4.8. To attend to all exhumations, reburial, pauper and destitute burial | 100% | To attend 100% of applications received | One request for exhumation of two corpes was processed (100%) | Correspondence received | Target met | R0- | To attend 100% of application received | 100% of all exhumations received were attended to | 100% of all exhumations received were attended to | Correspondence received | Target met | R0-
|  |  | Greenest Municipality competition | To encourage greening and proper waste management practices | By hosting the Greenest Municipal awards ceremony | Greenest Municipal Competition | 350 000 00 | 4.9. Number of Greenest Municipal Competition Held | 1 competition held | Drafting of entry forms and competition criteria and submit to local municipalities | Entry forms sent to all LM's to participate in the Competition and assessments conducted | Entry forms and Proof of submission | target exceeded | R99 500 00 | assessment of all local municipalities that entered the competition | Assessments have been conducted and currently deciding on final scores for all categories | Assessments have been conducted and currently deciding on final scores for all categories | 1.Entry forms and Proof of submission 2.Assessment documents | Target met | 99500
|  |  | Communicable Disease, Food and Chemical Poisoning | To Facllitate Investigation of Reported Communicable Disease, Food and Chemical Poisoning | To work hand in hand with health institutions to investigate reported communicable diseases, Food and Chemical Poisoning | Investigation of Communicable diseases, Food and Chemical Poisoning | R 20 000 00 | 4.10. To attend to all invistigated reported cases | 100% | 100% of cases received | one notice on communicable disease was received and investigated. A Health Education was conducted (100%) | 1. Correspondence Reporting Case 2. Investigation Report & intervention | target met | R0- | 100% of cases received | 100% of all cases received were investigated | 100% of all cases received were investigated | 1. Correspondence Reporting Case 2. Investigation Report | Target met | R0-
|  |  | Training of street Traders | To prevent the spread of communicable diseases and food poisining | By building capacity of street traders on food handling of foodstuffs & hygiene | Capacity building of Food Street Traders | 52900 | 4.11. Number of Food Street Traders Trained on food handling | 16 | Prepare Specification, advertisement and procurement of promotional material & conduct 2 street traders workshops on food safety. | five street traders trainings conducted in all LM's | Signed attendance registers | target exceeded | R0- | Conduct 2 street traders workshops on food safety | 2 street traiders training and workshop were conducted | 7 street traiders and workshops were conducted | Signed attendance registers | Target execeeded | R0-
|  |  | Water quality sampling | To monitor water quality | By taking water samples to laboratory for analysis | Water Samples analysis | R150 000 00 | 4.12. Number of water samples taken for analysis | 200 | 50 water samples taken for analysis | 59 water samples taken for analysis | copies of Water samples results | target met | R0- | 50 water samples taken for analysis | 52 water samples were taken for analysis | 111 water samples were taken for analysis | copies of Water samples results | Target execeeded | 15017
R0-
|  |  | Clean up campaigns | To promote cleanliness in our towns and communities | By conducting clean up and awareness campaigns | Clean up and awareness campaigns | R100 000 00 | 4.13. Number of cleanup campaigns conducted | 4 | 1 clean up campaign conducted | 3 cleanup campaigns held | Signed attendance register and dated photos | target exceeded | R0- | 1 clean up campaign conducted | 1 clean up campaign conducted | 4 clean up campaigns were conducted | Signed attendance register and dated photos | Target met | R0-
YOUTH DEVELOPMENT
PROMOTING SOCIAL COHESION ACROSS SOCIETY | GOOD GOVERNANCE AND PUBLIC PARTICIPATION | To increase the GDP of HGDM by 3% by 2030 so as to improve the socio-economic welbeing of it citizens | Back school drive | To promote the culture of learning | By identifying schools that will be visited and to partner with the local municipalities | Back to School Drive. | 150 000 00 | 4.14. Back to school drive held by January 2016 | 5 | None | N/A | None | N/A | R150 000 00 | Preparatory meetings | Target not met prepreratory meetings were scheduled to sit in 3rd quarter. | Target not met prepreratory meetings were scheduled to sit in 3rd quarter. | Signed attendance registers | Target not met
|  |  | Community Bursaries | To assist learners that can not afford enrollment fees in the institutions of higher learning | By providing financial assistence to the prospective learners | Enrollment fees | 350 000 00 | 4.15.Number learners assisted with finance for enrollemt in Higher Education institutions | 60 learners | None | N/A | None | N/A | R0- | Advertisement for registration fees | Community busaries were advertised and closed on the 31st of December 2015. Currently awaiting shortlisting and awarding | Community busaries were advertised and closed on the 31st of December 2015. Currently awaiting shortlisting and awarding | Advert | Target met
|  |  | Cuban Basaries | To contribute positively towards skills development of our youth and investing in scarse skills | By proving bursaries to derserving and needy learners | CUBAN Bursaries | 180 000 00 | 4.16. Number of deserving and needy learners funded to study medicine in Cuba | 6 learners | None | N/A | None | N/A | R0- | 6 Students Funded to study medicine in Cuba | 5 students studying in Cuba were funded and the 6th one was withdrawn due to some challenges that are currently being addressed | 5 students studying in Cuba were funded and the 6th one was withdrawn due to some challenges that are currently being addressed | Proof of payment | Target met | 150000
|  |  | Youth Development Empowernment Plan | To encourage youth to be involved in the development and implementation of their programmes | By hosting district youth indaba | Youth Development Indaba | R150 000 00 | 4.17. Youth Indaba held by June 2016 | By December 2014 | None | N/A | N/A | N/A | BH | Stakeholders meeting held and submit a report to Portfolio committee | Target was not met (1 meeting was supposed to be held) | Target not met 1 meeting was supposed to be held and the was never held. | Attendance register | The Youth Indaba preperatory meetings will resume in the 3rd quarter | 364012
|  |  | ICT Hub | To promote involvement of Youth in ICT | By procuring computers and payment of monthly stipent for the remaining 6 months | ICT hub | 500 000 00 | 4.18. Youth involved in the ICT hub by June 2016 | By June 2015 | Preparation of Specification to procure ICT Hub computers | Specification to procure ICT Hub computers has been prepared | Specification document | Target met | R0- | Implementation of the ICT Hub by installing computers | Target not met. (Specification was prepared and advertised but currently the ITC Hub has not been implemented) | Specification was prepared and advertised but currently the ITC Hub has not been implemented | Copy of the advert | The ICT Hub could not be implemented in the 2nd quarter because the budget to procure computers was under operation. During the budget udjusment budget it will be moved to capital budget | R0-
SPECIAL PROGRAMMES
PROMOTING SOCIAL COHESION ACROSS SOCIETY | LOCAL ECONOMIC AND SOCIAL DEVELOPMENT | To increase the GDP of HGDM by 3% by 2030 so as to improve the socio-economic welbeing of it citizens | District Senior citizens Golden games | To encourage healthy living and fitness amongs senior citizens | By hosting district golden games and participating in Provincial golden games | Golden Games | R200 000 00 | 4.18.1. Number of District Senior Citizens Golden games and 4.18.2. Number of Provincial games | By July 2014 | By August 2015 | Both District and Provincial games were held in August 2015 at Uthungulu | Signed attendance registers by participants and photos | Target met | R208 940 00 | None | N/A | Both District and Provincial games were held in August 2015 | Signed attendance registers by participants and photos | Target met | 208940
|  |  | Maskhandi Festival | To unearth new talent focusing on maskandi genre | By hosting maskandi festival | Cultural Festival | 300 000 00 | 4.19. Number ofcultural festival held | 1 | 1 preparotory meeting to be held | ? | Attendance register |  | R0- | 1 cultural festival held by Dec 2014 | 1 cultural festivalwas held by Dec 2015 at Ingwe LM Art Centre | Preparatory meetimg was and 1 cultural festivalwas held by Dec 2015 at Ingwe LM Art Centre | Signed minutes and attendance register of the prepatory meetings | Target met | 234000
|  |  | Participation in Umkhosi womhlanga | To promote moral regeneration through Umkhosi womhlanga | Ensure participation of SDM maidens in Umkhosi Womhlanga | Umkhosi Womhlanga | R50 000 00 | 4.20. Date on which the Umkhosi womhlanga event held | 2013-09-01 | Preparotory meetings | Preparatory meeting was held and HGDM participated to Umkhosi Womhlanga in September 2015 | Dated photos | Target met | R44 000 00 | None | N/A | Preparatory meeting was held and HGDM participated to Umkhosi Womhlanga in September 2015 | Dated photos | Target met | 40138
[6 empty] | Disability day | R300 000 00 | 4.21. Date on which the Disability day is held | 2013-11-01 | None | N/A | Attendance register | N/A | R2 854 00 | Disability day held by Dec 2015 | Disability day was held in Dec 2015 | Disability day was held in Dec 2015 | 1. Attendance register 2. photos | Target met | 208172
|  |  |  | To educate men on their social responsibilty within our communities | By hosting an annual men's summit | Men`s summit | R210 000 00 | 4.22. Date on which the men`s summit is held by July 2015 | 2013-07-01 | Hosting of summit by July 2015 | Men's summitt was held on the 31st of July 2015 at Umzimkhulu LM | 1.Attendance register 2. Photos | Target met | R98 872 00 | None | N/A | Men's summitt was held on the 31st of July 2015 at Umzimkhulu LM | 1.Attendance register 2. Photos | Target met | 98872
|  |  | Women`s summit | To host the womens' summit | By hosting an annual women summit | Womens' summit | R200 000 00 | 4.23. Date on which the Womens summit is held | 2014-08-01 | Hosting of women's summit by August 2015 | The women's summit was held together with women's celebration on the 1st of August 2015 | 1.Attendance register 2. Photos | Target met | R199 900 00 | None | N/A | The women's summit was held together with women's celebration on the 1st of August 2015 | 1.Attendance register 2. Photos | Target met | 199900
SPORT AND RECREATION
PROMOTING SOCIAL COHESION ACROSS SOCIETY |  |  |  | To promote rural horse riding within the district | To particpate in the Dundee July | Dundee July | 100 000 00 | 4.24. Date on which the DM participated in Dundee July event | 2013-07-01 | Participating in the Dundee July Event | HGDM particiapated in the Dundee July horse racing | 1. Photos | Target met | R44 000 00 | None | N/A | HGDM particiapated in the Dundee July horse racing | 1. Photos | Target met | 68369
|  |  |  | To promote rural horse riding within the district | To host and participate in the SDM Summer Cup | Summer Cup | R400 000 00 | 4.25. Date on which the Summer Cup is held | 2013-11-01 | 1. Preparatory meeting held | 2 preparatory meetings have been held | 1. Attendance Register 2. Minutes | Target met | R0- | Particiapting in the Summer cup by November 2015 | Summer Cup horse racing was held in November 2015 under Ingwe LM | Summer Cup horse racing was held in November 2015 under Ingwe LM | 1. Photos 2. Attendance register | Target met | 348630
|  |  |  | To host Mayoral games | Identify suitable players that will participate in the games | Mayoral cup | R4000 000 00 | 4.26. Date on which the Mayoral Cup held | 2013-07-01 | Mayoral cup held in preparation of the SALGA games | Mayoral cup was held on the 8th of August 2015 | 1. Photos 2. Attendance register | Target met | R541 531 00 | None | N/A | Mayoral cup was held on the 8th of August 2015 | 1. Photos 2. Attendance register | Target met
|  |  |  | To participate in the Provincial SALGA Games |  | SALGA Games |  | Date in which the District participates in the SALGA Games | 2015-12-01 | None | N/A | N/A | N/A | N/A | Participate in the SALGA Games by December 2015 | HGDM participated in the SALGA Games at Stanger by December 2015 | HGDM participated in the SALGA Games at Stanger by December 2015 | Attendance Register | Target met
|  |  |  | To participate in the IG's tournaments annually. | To coordinate district selection tornamnet and participate in the provinvcial tournament. | Indigenous Games |  | 4.27. Date o which District selections in preparation for the province tournamant held | 2013-08-01 | District selections in preparation for the province tournamant | District selection for the indigenuos games was held in August and further particated in the Provincial games that were held in Mkhanyakude DM | 1. Photos 2. Attendance register | Target met |  | None | N/A | District selection for the indigenuos games was held in August and further particated in the Provincial games that were held in Mkhanyakude DM | 1. Photos 2. Attendance register | Target met
|  |  |  | To encourage youth to partake in sport | By forming the leagues | Club Champoinships | R0- | 4.28. Number of club champioships supported | 4 | Netball tournament | HGDM could not participate in the Netball tournaments due to limited funding | 1. Photos 2. Attendance register | Target not met due to limited funding. The municipality should consider increasing the sport budget | R0- | Dance and Soccer Championships | Only dance that participated at the Championhip held in Port Elizabeth and later in Polokwane and there was no request from Soccer | Only dance that participated at the Championhip held in Port Elizabeth and later in Polokwane and there was no request from Soccer | 1. Photos 2. Attendance register | Target not met
|  |  |  | To develop athletics as a sport code that will that promote healthy living, tourism,social cohesion as well as enabling participants to qualify for the comrades marathon | By Inviting the participants through website and media | Harry Gwala District Marathon | R500 000 00 | 4.29. Date on which the Marathon is held | New enabler | None | N/A | N/A | N/A | R0- | 2 meetings held | 1 meetings was held at Ubuhlebezwe LM | 1meetings were held at Ubuhlebezwe LM | Attendance register or minutes of the meetings | Target not met | 0
PLANNING AND DEVELOPMENT
|  |  | GIS and CAS | To comply with operation license requirements | By improving the operating systems annually | Renewal of GIS and CAD operating system | 200 000 00 | 4.31. Date on which the Operating system is renewed | June 2014 | None |  | None | N/A | R0- | Renew operating license | Target not Met | The system is not yet renewed | Operating license | The posts responsible for this function is still vacant
|  |  | SDF | To review the HGDM SDF | Development of a credible SDF Framework partially in house and in consulatation with relevant stakeholders | SDF review | 250 000 00 | 4.32. Date on which the SDF is reviewed | June 2014 | None | N/A | None | N/A | R0- | Public consultation during IDP/Budget izimbizo | 10 IDP Road-Shows were conducted in 5 LMs under HGDM | 10 IDP Road-Shows were conducted in 5 LMs under HGDM | IDP road shows Attendance register | Target met | 0
|  |  | Umgeni farm detailed layout | To develop a district office Park on Umngeni farm | Appoint a service provider to assist with the town planning, envoronment and architectural design | Preparation of Umngeni Farm Detailed Layout and Township Establishment and Architectural Design | 500000 | 4.33. Date on which the Final Draft is in place | June 2014 | Supply chain process and Advertising | The project Terms of Reference were presented to the Bid-Specification Committee and they were approved together with the advert | Advert | Target met | R0- | Appointment of the service provider and Inception report in place | Target not Met | An advert for the Preparation of Umngeni Farm Detailed Layout and Township Establishment and Architectural Design was done and the matter is now with the Evaluation Committee | Appointment letter and Inception report | The project was advertised and clossed on the 30/10/2015. The matter has not been dealt with by Evaluation Committee
IDP/PMS DIRECTORATE
IMPLEMENT A DIFFERENTIATED APPROACH TO MUICIPAL FINANCE, PLANNING AND SUPPORT | GOOD GOVERNANCE AND PUBLIC PARTICIPATION | TO INCREASE INTERACTION BETWEEN THE MUNICIPALITY AND THE COMMUNITY TO DEPEEN DEMOCRACY AND ENHANCE SOCIAL COHESION | IDP | To review and update the IDP as per the MSA | By adhering to all the legislative prescripts governing the formulation of IDP's. | IDP Alignment meetings | 500 000 00 | 4.34. Number of IDP alignment meetings held | 4 | 1 meeting held | 11 IDP Alignement was hled | Attendance register | Target met | R122 000 00 | 1 meeting held | 1 meeting was held at Ingwe LM on the 18th of November 2015 | 2 IDP meetings were held | Attendance registers |  | 153888
Target met
[6 empty] | IDP |  | 4.35. Number of IDP roadshows held | 14 | None | N/A | N/A | N/A |  | 7 IDP road shows held | 10 IDP Road-Shows were conducted in 5 LMs under HGDM | 10 IDP Road-Shows were conducted in 5 LMs under HGDM |  | Target met
|  |  | PMS Review | To have fully complying and functional PMS | By engaging the service provider | PMS review | 800000 | 4.36. Date in which the PMS is fully functional | By May 2015 | Ensuring full alignment to the IDP and PMS | Only applicable in the 3rd quarter | 1. Matrix 2. SDBIP. 3. Attendance register | N/A | 341172 | Addressing PMS challenges raised by AG | PMS challenges raised by AG were addressed and an action plan was developmed | PMS challenges raised by AG were addressed and an action plan was developmed | 1. Matrix 2. SDBIP. 3. Attendance register 4. Action plan | Target met | 391240
|  |  | ANNUAL REPORT | To ensure that the annual report is submitted on time to the AG, National Treasury and to COGTA | By ensuring that the first draft is submitted by the 31 August and the final draft by the 31 January of each financial year. | Annual Report preparation | 300 000 00 | 4.37. Date in to which the Draft Annual Report is submitted to Council and the Auditor General | 1 Annual report | Submission of the draft Annual report to AG | Draft Annual Report was submitted to the AG in August 2015 | 1. Draft Annual report 2. Signed Acknowledgement letter | Target met | R0- | Submission of the draft Annual report to Council | The draft Annual Report was submitted to Council and the AG in November 2015 and the final copy wil be tabled to Council and other relevant departments in January 2016 | The draft Annual Report was submitted to Council and the AG in November 2015 and the final copy wil be tabled to Council and other relevant departments in January 2016 | Council resolution | Target met | 0